## Certification Cycle
ISMS-CRT-003 ¦ Surveillance Audit Schedule ¦ ISO/IEC 27001:2022 Certification Cycle ¦ MediSync Technologies Pvt. Ltd.
Certificate No. MST-ISO27K-2027-0841 ¦ Certificate valid: 14 April 2027 – 13 April 2030 ¦ Owner: Meera Iyer, ISMS Manager ¦ v1.0 ¦ April 2027 ¦ Annual surveillance audits are mandatory — failure to cooperate will result in certificate suspension. ¦ Classification: Confidential — Internal Use Only
Milestone | Date | Month Offset | CB Document | Description / Focus | MediSync Owner | CB Action Required? | Status | Notes
CERTIFICATION ISSUED (April 2027)
Certificate Issued | 14 Apr 2027 | M+0 | ISMS-CRT-002 | ISO/IEC 27001:2022 certificate issued. MediSync may now publicly claim certification. Certificate added to CB public register and UKAS IAF register. | ISMS Manager | No | COMPLETE | Certificate number: MST-ISO27K-2027-0841
Post-Cert Management Review | Apr / May 2027 | M+1 | ISMS-PEV-008 v2 | First post-certification management review — review ISMS performance since certification, confirm surveillance schedule, update IS objectives for Year 1. Per Decision D-13 from December 2026 management review. | ISMS Manager + CEO | No (internal) | PLANNED | Target: April/May 2027. Must confirm Year 1 surveillance schedule.
SentinelWatch BCDR Test | By Mar 2027 | M-1 | ISMS-OPS-003 (security schedule) | SentinelWatch security schedule condition requires BCDR test by March 2027 (R-021 treatment). Confirm test completed and R-021 risk updated to CLOSED. | ISMS Manager | No | CHECK REQUIRED | Must be confirmed before first surveillance. If overdue — escalate to CISO.
Year 1 — Q1 GRC Report | May 2027 | M+1 | ISMS-SUP-007 I-04 | First monthly GRC status report post-certification. Include: certificate maintenance status, Year 1 surveillance scheduling, any scope changes or significant events since certification. | ISMS Manager | No | PLANNED | Establish the post-certification monitoring cadence immediately.
YEAR 1 — SURVEILLANCE PERIOD (April 2027 – December 2027)
Phishing Simulation Year 2 | Aug / Sep 2027 | M+4/5 | Awareness platform | Third phishing simulation — first of Year 2. Surveillance audit will review results. Target: click rate maintained at or below 8.3% (February 2027 result). Results to be shared with CISO and Steering Committee. | SOC Manager | No (internal) | PLANNED | CB will review at Surveillance 1. Target: ≤10% click rate.
UAE Region DR Test | Oct 2027 | M+6 | ISMS-OPS-008 | First UAE region DR test (Azure UAE North). CI-013 in continual improvement log. Surveillance audit will review test record and confirm UAE RTOs met. India region tested October 2026 (all RTOs met). | Head of Cloud Infra | No (internal) | PLANNED | Surveillance 1 focus item. Must be completed before Dec 2027 surveillance.
A5.36 — Year 2 Review Initiated | By Mar 2028 | M+11 | A5.36 Annual Compliance Review Record v2 | Second annual IS policy and procedures compliance review. Year 1 review completed 28 March 2027. Year 2 review due March 2028. Calendar reminder set in ISMS Manager calendar (February 2028 trigger). | ISMS Manager | No (internal) | PLANNED | Annual cycle. Calendar reminder filed in GRC as evidence of governance.
Surveillance Audit 1 | Dec 2027 | M+8 | ISMS-CRT-003 Tab 2 | First annual surveillance audit. Focus: UAE DR test (Oct 2027), SentinelWatch BCDR, phishing simulation Year 2, DPDP Act rule status, A5.36 second cycle commenced, Head of Procurement knowledge check. See Tab 2 for full plan. | ISMS Manager + CISO | YES — CB action | PLANNED | Target: December 2027. CB to confirm scheduling by September 2027.
SURVEILLANCE AUDIT 1 + POST-SURVEILLANCE (December 2027 – 2028)
Surveillance 1 Corrective Actions (if any) | Jan / Feb 2028 | M+9/10 | ISMS-CRT-003 tracking | If Surveillance 1 raises NCRs: corrective action plans to be submitted within 30 days. Minor NCR CAs to be confirmed effective before Surveillance 2. | ISMS Manager | CB to confirm | CONDITIONAL | Only if NCRs raised at Surveillance 1.
Management Review Year 2 | Dec 2027 / Jan 2028 | M+8/9 | ISMS-PEV-008 v3 | Annual management review — second full cycle. Review Surveillance 1 findings. Update risk register (Year 2). Set IS objectives for Year 2. Confirm Surveillance 2 schedule. | ISMS Manager + CEO | No (internal) | PLANNED | Align with Surveillance 1 so fresh audit data feeds into the management review.
Phishing Simulation Year 3 | Aug / Sep 2028 | M+16/17 | Awareness platform | Fourth phishing simulation — first of Year 3. Surveillance 2 will review results. Target: sustained improvement. | SOC Manager | No (internal) | PLANNED | Surveillance 2 focus item.
SURVEILLANCE AUDIT 2 (December 2028)
Surveillance Audit 2 | Dec 2028 | M+20 | ISMS-CRT-003 | Second annual surveillance audit. Focus: access review Year 2 cycle, awareness programme Year 2 results, risk register annual update, new products/services scope check, Management Review Year 2 outputs. | ISMS Manager + CISO | YES — CB action | PLANNED | Target: December 2028. CB to confirm scheduling by September 2028.
YEAR 3 — RECERTIFICATION PREPARATION AND AUDIT (2029 – 2030)
Management Review Year 3 | Dec 2028 / Jan 2029 | M+20/21 | ISMS-PEV-008 v4 | Third annual management review. Review Surveillance 2 findings. Initiate recertification planning. Confirm recertification audit schedule. | ISMS Manager + CEO | No (internal) | PLANNED | Begin recertification preparation at this review.
Recertification Preparation | Apr–Nov 2029 | M+24–31 | ISMS programme documentation | Recertification audit preparation — equivalent in scope to Stage 2. Update SoA, risk register, internal audit (Audit 3). Confirm all IP controls from the 2027 certification are now FI (A5.29 UAE DR test, A5.31 DPDP Act rules — if published). | ISMS Manager + CISO | No (internal) | PLANNED | Treat as a mini-Stage 1/Stage 2 preparation cycle.
Recertification Audit | Dec 2029 | M+32 | ISMS-RCT-001 (new series) | Full scope recertification audit. Equivalent in scope to Stage 2. Live control demonstrations, knowledge checks, SoA evidence spot-check. DPDP Act compliance expected to be fully determinable by this time. | ISMS Manager + CISO | YES — CB action | PLANNED | Certificate expires 13 April 2030. Recertification must be complete before expiry.
Certificate Renewal | By 13 Apr 2030 | M+36 | New certificate | New 3-year certificate issued if recertification successful. MediSync maintains certification without gap. | ISMS Manager | CB action | PLANNED | Certificate expiry: 13 April 2030.

## Surveillance Audit 1 Plan
ISMS-CRT-003 ¦ Surveillance Audit 1 Plan ¦ December 2027 ¦ MediSync Technologies Pvt. Ltd.
This tab contains MediSync's internal preparation plan for the first surveillance audit (December 2027). ¦ Focus areas are drawn from ISMS-ST2-004 Section 9 (Items for Surveillance Attention) and ISMS-CRT-001 Section 5.4 (Year 1 conditions). ¦ Status: READY = evidence in GRC Repository ¦ IN PROGRESS = being prepared ¦ PLANNED = not yet started
Focus Area | Source | Focus Description | Evidence Required / MediSync Action | Evidence Location (GRC Repository) | Status
SA1-001 | ISMS-ST2-004 Section 9 (Surveillance 1) | A5.36 — Annual compliance review Year 2 cycle | Second annual IS policy and procedures compliance review must have been initiated. Evidence: Year 2 compliance review record (or evidence of initiation with a target completion date). Calendar reminder screenshot as governance evidence. | /Phase 3 — Planning/A5.36_Annual_Compliance_Review_Record_v2_0 | PLANNED (due Mar 2028)
SA1-002 | ISMS-ST2-004 Section 9 + CI-013 | UAE region DR test — first test of Azure UAE North | UAE DR test to be completed October 2027. Evidence: DR test record (ISMS-OPS-008 Appendix B), including: test scenario, RTOs measured vs targets, any findings, and lessons learned. India region all RTOs met — UAE test to confirm same. | /Phase 5 — Operation/ISMS-OPS-008 (Appendix B — UAE Oct 2027) | PLANNED (due Oct 2027)
SA1-003 | ISMS-ST2-004 Section 9 + R-021 | SentinelWatch BCDR test — security schedule condition | SentinelWatch committed to BCDR test by March 2027 as a security schedule condition (R-021 treatment). Confirm test completed. Evidence: SentinelWatch confirmation email or report, update to ISMS-OPS-003 vendor record, R-021 closed in PLN-004. | /Phase 5 — Operation/ISMS-OPS-003 (SentinelWatch — BCDR test confirmation) | CHECK REQUIRED (overdue if not done)
SA1-004 | ISMS-ST2-004 Section 9 + PF-S2-003 | Phishing simulation Year 2 — confirm sustained improvement | Third phishing simulation (August/September 2027) results. CB will check: methodology (same vendor, same template as previous sims for comparability), click rate vs February 2027 (8.3%) and August 2026 baseline (22.1%). Target: sustained below 10%. | /Training Records/Phishing Simulations/PhishSim_Year2_Results | PLANNED (due Sep 2027)
SA1-005 | ISMS-ST2-004 Section 9 + CI-014 | DPDP Act implementation rules — if published before December 2027 | If the Government of India finalises DPDP Act implementation rules before the December 2027 surveillance audit: Legal Register (INI-010) and OPS-005 Track 2 must have been reviewed and updated within 30 days of publication. Evidence: updated documents with change note, Legal register dated update. | /Phase 1 — Initiation/ISMS-INI-010 (updated if rules published) /Phase 5 — Operation/ISMS-OPS-005 (Track 2 updated if rules published) | MONITORING (rules not yet published as at April 2027)
SA1-006 | ISMS-ST2-004 Section 9 + CRT-001 | Head of Procurement (Priya Mehta) — ISMS integration knowledge check | Priya Mehta appointed 17 February 2027. CB will conduct a knowledge check at Surveillance 1: can she describe the procurement-related ISMS responsibilities she holds? Expected: supplier assessment oversight, vendor register, security schedule conditions. MediSync to brief Priya Mehta on these responsibilities before the audit. | In-person knowledge check — no GRC document (brief in /Phase 4 — Support/ISMS-SUP-001) | IN PROGRESS (Priya Mehta onboarding)
SA1-007 | Standard requirements | Internal audit Audit 3 — pre-Surveillance 1 | ISO 27001:2022 Clause 9.2 requires the organisation to conduct internal audits at planned intervals. Audit 3 should be completed before the December 2027 surveillance audit. Programme: ISMS-PEV-003. External audit lead (same IRCA-registered auditor as Audits 1 and 2) to be engaged. | /Phase 6 — Performance/ISMS-PEV-005c (Audit 3 report) | PLANNED (due Oct/Nov 2027)
SA1-008 | Standard requirements | Management review Year 2 — confirm Clause 9.3 compliance maintained | Annual management review (Clause 9.3) must be completed. Management review meeting December 2027 (aligned with surveillance audit). CB will confirm: CEO chaired, all 11 Clause 9.3.2 inputs addressed, outputs documented. Same standard as December 2026 review that was reviewed at Stage 2. | /Phase 6 — Performance/ISMS-PEV-008 v3 (Year 2 MR Minutes) | PLANNED (due Dec 2027)
SA1-009 | Standard requirements | Risk register Year 1 update — confirm current | Risk register (PLN-004) must be reviewed and updated. Annual cycle. Check: R-021 (SentinelWatch BCDR) status — should be closed if BCDR test complete. R-002 (phishing — Finance) status update based on Year 2 phishing simulation results. Any new risks identified in Year 1. | /Phase 3 — Planning/ISMS-PLN-004 (updated — Phase 6 Year 1) | PLANNED (due Q4 2027)
SA1-010 | Standard requirements | SoA Year 1 review — confirm A5.29 and A5.31 status | A5.29 (IS during disruption — UAE DR test) expected to move from IP to FI after October 2027 UAE DR test. A5.31 (legal requirements — DPDP Act) remains IP if rules not published. Update PLN-006 SoA accordingly. Surveillance CB will check IP control status and progress. | /Phase 3 — Planning/ISMS-PLN-006 v1.2 (Year 1 SoA update) | PLANNED (due after Oct 2027 UAE DR test)
SA1-011 | CRT-001 Section 5.2 | Scope change disclosure — confirm no undisclosed changes | Any significant changes since April 2027 certification: new products, new locations, material cloud architecture changes, regulatory notifications. ISMS Manager to review and confirm to CISO. If any changes occurred: confirm they were disclosed to CB within 30 days per certification conditions. | ISMS Manager review — no specific GRC document (changes would be in relevant ISMS documents) | ONGOING (monitor throughout Year 1)

## Obligations and Triggers
ISMS-CRT-003 ¦ Ongoing Obligations and Disclosure Triggers ¦ 3-Year Certification Period ¦ MediSync Technologies Pvt. Ltd.
These are the ongoing obligations that apply throughout the 3-year certification period (April 2027 – April 2030). ¦ Source: ISMS-CRT-001 Section 5 (Conditions and Obligations) and ISO/IEC 27006-1:2022. ¦ Failure to comply with mandatory obligations may result in certificate suspension or withdrawal.
Obligation Ref | Obligation Type | Description | MediSync Action Required | Mandatory?
MANDATORY OBLIGATIONS — failure to comply may result in certificate suspension or withdrawal
OBL-001 | Annual surveillance audit | Annual surveillance audits are mandatory — not optional. The certification body will contact MediSync approximately 3 months before the due date to schedule. MediSync must cooperate with scheduling and provide access to facilities, systems, and staff. | ISMS Manager to respond to CB scheduling contact within 5 business days. Confirm auditee availability for all scheduled sessions. | MANDATORY (suspension if missed)
OBL-002 | Significant change disclosure — 30 days | Any significant change to the ISMS scope, significant security incident, or significant organisational change must be disclosed to the certification body within 30 days. Significant changes include: new product processing personal data within scope; new office location; material cloud architecture change; security incident triggering regulatory notification. | ISMS Manager to notify CB within 30 days of any significant change. CISO to assess whether a change triggers the disclosure obligation. | MANDATORY (withdrawal risk if not disclosed)
OBL-003 | Regulatory notification disclosure | If MediSync triggers a CERT-In, DPDP Act, or UAE PDPL notification obligation, the certification body must be informed. This is separate from the regulatory notification itself. | CISO to notify ISMS Manager immediately on any regulatory notification. ISMS Manager to notify CB within 5 business days. | MANDATORY
OBL-004 | Certificate scope claims accuracy | MediSync may only claim ISO 27001:2022 certification for activities, products, and locations within the certified scope (as stated in ISMS-INI-011). Claims for activities outside the certified scope are prohibited. | Legal and Marketing to confirm all certification claims (website, contracts, proposals) accurately reflect the certified scope. Head of Legal to review contract certification language. | MANDATORY
OBL-005 | Certificate suspension or withdrawal disclosure | If the certificate is suspended or withdrawn, MediSync must immediately cease making certification claims and inform customers as appropriate. MediSync must not represent a suspended certificate as valid. | ISMS Manager and CISO to monitor certificate status on CB public register quarterly. | MANDATORY
OBL-008 | Recertification application — 6 months before expiry | Recertification application must be submitted to the certification body at least 6 months before certificate expiry (13 April 2030). Target application submission: October 2029. Recertification audit: December 2029. | ISMS Manager: calendar reminder set for September 2029 to initiate recertification planning. Treat as a mini Project HealthSec — internal audit (Audit 3), SoA update, management review. | MANDATORY (certificate expires 13 April 2030)
YEAR 1 WATCH ITEMS — focus areas for first surveillance audit (December 2027)
OBL-006 | Year 1 watch item: SentinelWatch BCDR | SentinelWatch security schedule condition: BCDR test by March 2027. This must be confirmed complete before the December 2027 surveillance audit. If overdue, ISMS Manager to escalate to CISO and initiate a corrective action. | ISMS Manager to confirm with SentinelWatch and update OPS-003 by April 2027. If overdue — raise with CISO immediately. | WATCH ITEM (surveillance focus)
OBL-007 | Year 1 watch item: DPDP Act monitoring | DPDP Act implementation rules not yet finalised as at April 2027. ISMS Manager and Head of Legal to monitor MeitY publications quarterly. On publication: Legal Register (INI-010) and OPS-005 Track 2 to be reviewed and updated within 30 days. | Head of Legal: quarterly MeitY monitoring. ISMS Manager: update Legal Register and OPS-005 Track 2 within 30 days of any new rules. Document monitoring even when no changes are required. | WATCH ITEM (surveillance focus)
BEST PRACTICE — not CB requirements but critical for maintaining the quality of management commitment
OBL-009 | Quarterly Steering Committee — ISMS agenda item | The quarterly Steering Committee should maintain an ISMS agenda item throughout the certification period. This is not a CB requirement but is the practice that enabled the CEO to demonstrate genuine management commitment at Stage 2. Losing this practice risks a management commitment finding at surveillance. | ISMS Manager: ISMS status to remain a standing quarterly SC agenda item. Monthly GRC report to continue to be distributed to CISO and Steering Committee. | BEST PRACTICE (management commitment evidence)
OBL-010 | Annual awareness programme review | The security awareness programme (ISMS-SUP-005) should be reviewed annually and updated based on: lessons learned from any incidents, phishing simulation results, changes in the threat environment. Year 2 refresh due June/July 2027 per CI-008. | Head of HR: annual programme review aligned with the July awareness cycle. Incorporate phishing simulation results, incident lessons, and any new regulatory requirements. | BEST PRACTICE (ISMS improvement evidence)