## Incident Register
ISMS-OPS-006 ¦ Incident Log / Register ¦ ISO/IEC 27001:2022 Annex A 5.24–5.28 ¦ Project HealthSec ¦ MediSync Technologies Pvt. Ltd.
Owner: Neha Choudhury, SOC Manager ¦ v1.0 ¦ October 2026 ¦ One row per declared incident, near-miss, or tabletop exercise. ¦ Do not delete rows — amend with correction note if an error is found. ¦ Classification: Confidential — Internal Use Only
Incident ID | Type | Severity | Description | Systems / Data Affected | Detection Method | Detected By | Detection Date/Time | Declaration Date/Time | Incident Commander | CERT-In Notified? | Customer Notified? | Status | Post-Incident Review Date
INC-001 | Near-miss | NEAR-MISS | Phishing email targeting Finance team — payment instruction fraud attempt. Well-crafted email referenced a real vendor negotiation. Billing team member nearly actioned a fraudulent payment redirect. Stopped by a colleague's second review. No payment made. No credential compromise confirmed. | Finance team mailboxes; payment approval workflow. No patient data involved. | Human detection — colleague review | Finance team (billing analyst) | Q4 2024 (exact date not recorded — retrospective logging) | Q4 2024 (handled informally — not formally declared at the time) | Vikram Sundaram (CISO) — retrospective | Not assessed — IR plan did not contain CERT-In path at time of incident. Retroactively confirmed: not reportable (no patient data breach; payment fraud attempt, not a cyber incident per CERT-In Rules 2022). | N/A — no patient data breach | Closed (retrospective) | Retrospective PIR incorporated into ISMS-OPS-005 v1.0 design. Not a formal PIR — prior to ISMS programme.
INC-002 | Near-miss | NEAR-MISS | Cloud storage bucket misconfiguration — S3 bucket containing de-identified but sensitive analytics data left with broader access permissions than intended during a data science experiment. Configuration error remained in place for approximately 3 months before discovery. No confirmed external access. Discovered by internal review, not by monitoring. | AWS ap-south-1 — S3 analytics bucket (de-identified analytics data, not live patient records). No Restricted-classified data confirmed exposed. | Human detection — internal cloud storage review | Cloud Infrastructure team (internal review) | Q3 2024 (exact date not recorded — retrospective logging) | Q3 2024 (handled informally by Engineering — not formally declared at the time) | Vikram Sundaram (CISO) — retrospective | Not assessed — IR plan did not contain CERT-In path at time of incident. Retroactively confirmed: monitoring gap meant the duration of exposure was unknown. De-identified data — likely not reportable under CERT-In Rules 2022. Legal confirmed no mandatory notification required. | N/A — de-identified data; no patient data breach confirmed | Closed (retrospective) | Retrospective PIR incorporated into ISMS-OPS-005 v1.0 design. Cloud config baseline (OPS-001 D-02) and Sentinel drift alerts created in direct response to this near-miss.
INC-003 | Tabletop exercise | TABLETOP | Planned tabletop exercise — phishing-based credential compromise scenario escalating to potential patient data exposure. Scenario: Finance staff member clicks phishing link, enters credentials; attacker uses credentials to attempt access to hospital-facing admin accounts; SOC detects anomalous login; CISO declares incident; CERT-In 6-hour clock assessed. | Simulated: Entra ID (hospital-facing admin accounts); EHR-CORE patient records (India). No real systems or data affected — exercise only. | Tabletop exercise (planned) | Neha Choudhury (SOC Manager — exercise facilitator) | 20 Oct 2026 09:00 IST | 20 Oct 2026 09:00 IST (exercise start) | Vikram Sundaram (CISO — exercise participant) | Exercise only — CERT-In notification was simulated. Key finding: CERT-In 6-hour assessment was not triggered until 90 minutes into the exercise. See ISMS-OPS-005 Section 12 for full findings. | Exercise only — customer notification simulated | Closed (exercise complete) | 20 Oct 2026 — findings documented in ISMS-OPS-005 Section 12. Five procedure changes made.
INC-004 | [Type] | [Severity] | [Description of what happened — include: how the incident started, what actions were taken by the attacker or what error occurred, what was affected, what was NOT affected] | [Systems and data categories affected — reference asset register IDs from ISMS-PLN-003 where applicable] | [Detection method — Sentinel alert / CrowdStrike / staff report / vendor notification / customer report] | [Who detected / reported] | [DD Mon YYYY HH:MM IST] | [DD Mon YYYY HH:MM IST] | [Name of Incident Commander] | [Y — filed DD Mon YYYY HH:MM IST / N — not required / Assessing] | [Y — notified DD Mon YYYY / N — not required / Assessing] | [Open / Monitoring / Under review / Closed] | [DD Mon YYYY — or "Pending" if not yet completed]
Severity key: CRITICAL (red) ¦ HIGH (orange-red) ¦ MEDIUM (orange) ¦ LOW (amber) ¦ NEAR-MISS (blue) ¦ TABLETOP (purple) ¦ Status: green=Closed ¦ red=Open ¦ amber=Under review ¦ blue=Monitoring ¦ CERT-In: Y=notification filed; N=assessed as not required; Assessing=assessment in progress ¦ Retention: per ISMS-SUP-010 — life of ISMS plus 3 years

## Regulatory Notification Log
ISMS-OPS-006 ¦ Regulatory Notification Log ¦ Record of all regulatory notifications submitted under ISMS-OPS-005
Every CERT-In, DPDP Act, and UAE PDPL notification submitted by MediSync is logged here. ¦ Log entry must be made within 1 business day of submission. ¦ CERT-In acknowledgement reference is recorded when received.
Log ID | Incident Ref | Notification Track | Submitted To | Submission Date/Time | Submission Method | CERT-In / Ref Number | Notification Content Summary | Follow-up Required? | Status
NTF-001 | INC-003 (exercise) | CERT-In — Track 1 (SIMULATED) | CERT-In — simulated only | 20 Oct 2026 (simulated — exercise only) | Tabletop exercise — portal submission simulated | N/A — exercise | Simulated CERT-In notification filed as part of tabletop exercise. Key finding: notification clock assessment started 90 minutes late. See ISMS-OPS-005 Section 12. | Yes — procedure updated to address clock trigger issue | Closed — exercise finding incorporated
NTF-TEMPLATE | [INC-XXX] | [CERT-In Track 1 / DPDP Act Track 2 / UAE PDPL Track 3] | [CERT-In / Affected hospital customer / UAE Data Protection Office] | [DD Mon YYYY HH:MM IST] | [Portal + email / Written notice / Official submission] | [CERT-In reference number received in response — or "Pending" if not yet received] | [Brief summary of notification content — data categories, affected systems, actions taken] | [Y — detail of follow-up required / N] | [Submitted / Acknowledged / Follow-up in progress / Closed]
CRITICAL: CERT-In 6-hour clock runs from the Detection Date/Time in the Incident Register (Tab 1) — not from this notification log entry. ¦ A CERT-In notification filed at hour 5.5 is within the window. A notification filed at hour 6.5 is a regulatory breach. ¦ If the 6-hour window is at risk: CISO submits immediately with preliminary information, supplementary notification follows within 24 hours. ¦ Log the submission timestamp accurately — do not round or estimate.

## Lessons Learned
ISMS-OPS-006 ¦ Lessons Learned Summary ¦ Aggregated improvements from incidents and exercises
One row per lesson. Lessons feed into: (1) ISMS-PLN-004 Risk Register; (2) ISMS-OPS-005 IR Procedure updates; (3) ISMS-SUP-005 Awareness Programme; (4) ISMS-OPS-001 Operational Procedures. ¦ Reviewed at each management review cycle (ISMS-PEV-008).
Lesson ID | Source Incident | Lesson Summary | Improvement Action | Document Updated | Owner | Target Date | Status
LL-001 | INC-002 (2024 cloud config near-miss) | Cloud misconfiguration was not detected by monitoring — it was found by accident during an internal review 3 months after it was introduced. Monitoring had no alert rule for public bucket exposure. | Sentinel alert rule for public S3/Azure Blob access created (OPS-001 D-02.3). Cloud configuration baseline documented (OPS-001 D-02.1). Change review process for cloud security settings implemented (PLN-009). | ISMS-OPS-001 D-02 ISMS-PLN-009 | Sana Al Farsi (Head of Cloud Infra) | Oct 2026 | Complete
LL-002 | INC-001 (2024 phishing near-miss) | Finance staff had no phishing awareness training. The near-miss was stopped by a colleague's intuition, not by any trained awareness. 290 non-Engineering staff had received no awareness training. | Security awareness programme (ISMS-SUP-005) launched Phase 4 covering all ~430 staff. Finance anti-phishing module (TNA-002) mandatory for Finance and payment-handling staff. Phishing simulation (Aug 2026) confirmed click-rate reduction. | ISMS-SUP-005 ISMS-SUP-004 | Priya Subramaniam (Head of HR) | Jul 2026 | Complete
LL-003 | INC-001 and INC-002 (both 2024 near-misses) | Neither 2024 incident was formally declared, logged, or reviewed. No evidence trail was created. When the ISMS programme began, there was no record of either incident beyond informal notes. The IR plan (pre-2024) was never used. | Formal incident declaration and logging process established in ISMS-OPS-005 and ISMS-OPS-006. Retroactive logging of both near-misses as INC-001 and INC-002 (this register). Post-incident review now mandatory for all declared incidents. | ISMS-OPS-005 ISMS-OPS-006 | Neha Choudhury (SOC Manager) | Oct 2026 | Complete
LL-004 | INC-003 (Oct 2026 tabletop) | CERT-In 6-hour clock assessment was not triggered until 90 minutes after detection because the SOC analyst waited for a confirmed classification. This effectively reduced the available notification window from 6 hours to 4.5 hours. | ISMS-OPS-005 Section 5 updated: detection time is the start of the incident timeline regardless of classification. Section 7 updated: CERT-In 6-hour assessment triggered by MEDIUM or above classification — not by confirmed breach. | ISMS-OPS-005 Sections 5 and 7 | Neha Choudhury (SOC Manager) | Oct 2026 | Complete
LL-005 | INC-003 (Oct 2026 tabletop) | DPDP Act notification escalation to Legal was delayed because both SOC Manager and CISO assumed the other had initiated contact with the Head of Legal. No single owner was named. | ISMS-OPS-005 Section 7.2 updated: Head of Legal is the sole notification owner for the DPDP Act track. CISO is responsible for initiating the Legal notification — not assuming it has happened. Escalation contacts table (Section 11) updated. | ISMS-OPS-005 Sections 7.2 and 11 | Vikram Sundaram (CISO) | Oct 2026 | Complete
LL-006 | INC-003 (Oct 2026 tabletop) | SentinelWatch MSSP escalation number was stored in a spreadsheet rather than a documented channel. Analyst had to search during a simulated time-pressure scenario. | ISMS-OPS-005 Section 11 updated to reference the SentinelWatch security schedule as the authoritative source for the escalation number. SentinelWatch security schedule is the document to update when the number changes — not this procedure. | ISMS-OPS-005 Section 11 | Neha Choudhury (SOC Manager) | Oct 2026 | Complete
LL-007 | INC-003 (Oct 2026 tabletop) | Cloud misconfiguration containment steps did not include "preserve CloudTrail log as CERT-In evidence" before correcting the misconfiguration. An analyst corrected the configuration before checking logs in the exercise. | ISMS-OPS-005 Section 8.1 (cloud misconfiguration containment) updated: "Do NOT delete access logs — they are CERT-In evidence" is now the second step, before any configuration correction. | ISMS-OPS-005 Section 8.1 | Neha Choudhury (SOC Manager) | Oct 2026 | Complete
LL-008 | INC-003 (Oct 2026 tabletop) | Post-incident review was understood to be optional for LOW severity incidents. This means incidents that reveal procedural gaps could close without a formal review. | ISMS-OPS-005 Section 10 updated: post-incident review is mandatory for every declared incident. Scope and depth are proportionate to severity; the review is not optional for any declared incident. | ISMS-OPS-005 Section 10 | Neha Choudhury (SOC Manager) | Oct 2026 | Complete
Total lessons logged: 8 ¦ All 8 from 2024 near-misses (retrospective) and Oct 2026 tabletop exercise. ¦ At each management review: ISMS Manager presents lessons-learned summary — confirming improvements are complete and sustained. Any lesson with a risk register implication should be cross-referenced to the relevant risk entry in ISMS-PLN-004.