## Change Register
ISMS-OPS-010 ¦ Change Management Log ¦ ISO/IEC 27001:2022 Clause 6.3 + Annex A 8.32 ¦ Project HealthSec ¦ MediSync Technologies Pvt. Ltd.
Owner: Vikram Sundaram, CISO ¦ v1.0 ¦ October 2026 ¦ Records all changes to ISMS-scope systems from Phase 4 onward. ¦ STANDARD=pre-approved low-risk pattern ¦ NORMAL=risk-assessed, CISO approval for HIGH-impact ¦ EMERGENCY=expedited — see Tab 2 ¦ Classification: Confidential — Internal Use Only
Change ID | Type | Change Description | System / Component | Requestor | Security Impact | CISO Approval Required? | Approved By | Planned Date | Implemented Date | Pre-change Test? | Post-impl. Verification | Rollback Plan? | Rollback Executed? | Status | Related Risk / Gap
PHASE 4 — ISMS BASELINE CHANGES (retrospective, Apr–Jul 2026)
CHG-001 | NORMAL | Entra ID Conditional Access — enforce MFA for all accounts, disable legacy authentication | Microsoft Entra ID (all accounts) | Vikram Sundaram (CISO) | HIGH | Yes | CISO (COO informed) | Mar 2026 | Apr 2026 | Yes — tested in staging tenant | Yes — MFA prompt confirmed for all test account types | Yes — Conditional Access policy reversion | No | Completed | G-04; R-002
CHG-002 | NORMAL | GitHub Advanced Security (GHAS) — enable secret scanning and CodeQL on all 8 product repositories | GitHub Enterprise — all 8 product repositories | Advait Deshmukh (VP Engineering) | MEDIUM | No | VP Engineering | Apr 2026 | Apr 2026 | Yes — enabled on one test repo first | Yes — alerts confirmed firing; no false-positive PR blocking | Yes — disable GHAS per repository if needed | No | Completed | G-16; R-011
CHG-003 | NORMAL | Entra ID PIM — enable Privileged Identity Management for all Azure Owner and AWS Admin roles | Microsoft Entra ID PIM; AWS IAM (Entra federation) | Vikram Sundaram (CISO) | HIGH | Yes | CISO; COO informed | Apr 2026 | May 2026 | Yes — PIM activation flow tested per role type | Yes — all activations in Entra audit log; standing assignments removed | Yes — revert to standing assignments if PIM causes operational disruption | No | Completed | G-04; R-001
CHG-004 | NORMAL | Tenable Nessus — configure monthly authenticated scan schedule (production cloud infrastructure) | Tenable Nessus; AWS ap-south-1; Azure UAE North | Neha Choudhury (SOC Manager) | MEDIUM | No | SOC Manager; CISO informed | May 2026 | Jun 2026 | Yes — test scan on non-production environment | Yes — first production scan Jun 2026; findings reviewed | Yes — revert to ad-hoc scanning | No | Completed | G-15; R-010
CHG-005 | NORMAL | Microsoft Sentinel — deploy cloud configuration drift alert rules (5 alert categories) | Microsoft Sentinel; AWS CloudTrail; Azure Monitor | Neha Choudhury (SOC Manager) | HIGH | Yes | CISO; SOC Manager | Jun 2026 | Jul 2026 | Yes — alert rules tested with simulated events in dev environment | Yes — all 5 categories confirmed firing in production | Yes — disable alert rules | No | Completed | G-09; G-11; R-003
PHASE 5 — OPERATIONAL CHANGES (Aug–Oct 2026)
CHG-006 | STANDARD | AWS S3 Object Lock (Compliance mode) — enable on all India production backup buckets | AWS S3 — India backup buckets BK-001 to BK-004 | Sana Al Farsi (Head of Cloud Infra) | HIGH | Yes | CISO; VaultArchive confirmed | Jul 2026 | Aug 2026 | Yes — tested on non-production bucket first | Yes — Object Lock status confirmed via AWS console; VaultArchive walkthrough Oct 2026 confirmed | No — Object Lock Compliance mode is irreversible; pre-implementation review is the compensating control | No | Completed | G-14; R-015
CHG-007 | STANDARD | Azure Immutable Blob Storage — enable time-based retention policy on all UAE backup containers | Azure Blob Storage — UAE North BK-008 to BK-010 | Sana Al Farsi (Head of Cloud Infra) | HIGH | Yes | CISO; VaultArchive confirmed | Jul 2026 | Aug 2026 | Yes — tested on non-production container | Yes — Immutable Blob Storage confirmed; VaultArchive walkthrough Oct 2026 confirmed | No — Immutable Blob Storage with locked retention is irreversible | No | Completed | G-14; R-015
CHG-008 | NORMAL | Kubernetes Pod Security Standards — enforce Restricted profile on all production namespaces | Amazon EKS (India); Azure AKS (UAE) — all production namespaces | Advait Deshmukh (VP Engineering) | HIGH | Yes | CISO; VP Engineering | Aug 2026 | Sep 2026 | Yes — enforced in staging for 2 weeks before production | Yes — all production pods Running under Restricted PSS; no privileged containers | Yes — revert to Baseline PSS profile | No | Completed | G-16; R-011
CHG-009 | NORMAL | Dependabot — enable automated dependency scanning on all 8 product repositories + IaC repos | GitHub Enterprise — all repositories | Advait Deshmukh (VP Engineering) | MEDIUM | No | VP Engineering | Aug 2026 | Sep 2026 | Yes — enabled on 2 repos first; alert volume assessed; 3 High CVEs resolved pre-rollout | Yes — Dependabot active; ongoing alert review | Yes — disable Dependabot per repository | No | Completed | G-16; R-011
CHG-010 | NORMAL | cert-manager — automate TLS certificate renewal for all enterprise customer VPC/VNet namespaces (DR test corrective action) | Amazon EKS / Azure AKS — 6 enterprise customer namespaces | Sana Al Farsi (Head of Cloud Infra) | MEDIUM | No | Head of Cloud Infra; CISO informed | Oct 2026 | Oct 2026 | Yes — tested on one enterprise namespace first | Yes — automated renewal confirmed for all 6 namespaces | Yes — revert to manual cert-manager process | No | Completed | DR test finding — OPS-008
CHG-011 | NORMAL | SentinelWatch MSSP — implement per-analyst Sentinel workspace access grants (replacing group-level) | Microsoft Sentinel workspace; Microsoft Entra ID | Vikram Sundaram (CISO) | HIGH | Yes | CISO; SentinelWatch agreed (security schedule condition) | Oct 2026 | Dec 2026 (SentinelWatch committed) | Pending — SentinelWatch to implement | Pending — to be verified after implementation | Yes — revert to group-level grants if per-analyst approach causes operational issues | No | In Progress — due Dec 2026 | OPS-003 SentinelWatch condition
CHG-012 | NORMAL | Security awareness platform — procure, configure and launch for TNA-001, TNA-002, TNA-003, TNA-016 | Awareness platform (SaaS) — all ~430 staff | Priya Subramaniam (Head of HR) | MEDIUM | No | Head of HR; ISMS Manager | Jun 2026 | Jul 2026 | Yes — UAT with pilot group (20 staff) | Yes — 95%+ completion across departments (Procurement pending vacancy) | Yes — revert to manual awareness delivery | No | Completed | G-10; R-013
PLANNED CHANGES (Nov 2026 onward)
CHG-013 | NORMAL | Annual penetration test — production platform (API-GW, auth layer, EHR-CORE, HIS-CORE) | Production platform — pre-Stage 2 audit | Vikram Sundaram (CISO) | HIGH | Yes | CISO — to be approved | Feb 2027 | Feb 2027 | Yes — scope confirmed with pentesting firm | Pending | N/A — read-only test | No | Planned — Feb 2027 | G-16; Stage 2 requirement
CHG-014 | NORMAL | Tier 2 vendor security assessments — PulseMail, PayBridge, TrustID (30-question questionnaire) | Vendor assessment process | Meera Iyer (ISMS Manager) | MEDIUM | No | ISMS Manager | Nov 2026 | Dec 2026 | N/A — process, not technical | Pending — Dec 2026 | N/A | No | In Progress | OPS-003 Tier 2 backlog
← ADD FUTURE CHANGES BELOW
CHG-XXX | STANDARD / NORMAL / EMERGENCY | [Change description] | [System] | [Requestor] | HIGH / MEDIUM / LOW | Yes / No | [Approver] | [DD Mon YYYY] | [DD Mon YYYY] | Yes / No / N/A | [Verification result] | Yes / No | Yes / No | Pending / Approved / In Progress / Completed / Rolled Back / Cancelled | [Risk or gap ref]
Types: STANDARD=pre-approved pattern, no individual review ¦ NORMAL=risk-assessed, CISO approval for HIGH ¦ EMERGENCY=expedited, see Tab 2 ¦ Security Impact HIGH requires CISO approval; MEDIUM requires CISO notification ¦ Rollback: all changes must have a documented rollback plan unless technically irreversible (e.g., S3 Object Lock Compliance mode), in which case pre-implementation review is the compensating control.

## Emergency Change Log
ISMS-OPS-010 ¦ Emergency Change Log ¦ Expedited changes — separate approval track
Emergency changes bypass the standard review window due to operational urgency (active incident containment, critical vulnerability). ¦ Verbal CISO approval logged immediately. Full retrospective review within 48 hours. ¦ An emergency change without retrospective formal approval within 48 hours is an unauthorised change and a Clause 6.3 nonconformity.
Emrg ID | Change Description | System | Raised By | Emergency Justification | Verbal CISO Approval Time | Implemented Time | Retrospective Review Date | Formally Approved? | Rollback Possible? | Status
No emergency changes have been raised since Phase 4 launch. This register will be populated if and when an emergency change is required. Emergency changes arising from security incidents are coordinated through ISMS-OPS-005 (Incident Management Procedure).
EMRG-XXX | [Description] | [System] | [Name + role] | [Why cannot wait for standard review] | [Date/time CISO verbal approval] | [Date/time implemented] | [Retrospective review date — within 48h] | Yes / No | Yes / No | Implemented — awaiting retrospective review / Retrospectively approved / Rolled back
CRITICAL: Emergency change without retrospective formal approval within 48 hours is an unauthorised change — nonconformity under Clause 6.3. ¦ If CISO unavailable: COO provides verbal approval. Both sign the retrospective review. ¦ Emergency changes involving security controls must also be reviewed in ISMS-OPS-001 D-02 to confirm no permanent baseline deviation.

## Change Statistics
ISMS-OPS-010 ¦ Change Statistics ¦ Monthly summary for management reporting
Used in the monthly GRC status report (ISMS-SUP-007 I-04) and at each quarterly Steering Committee. ¦ Updated by ISMS Manager within 5 business days of month-end.
Period | Total Changes | Standard | Normal | Emergency | Completed | Rolled Back / Failed | Notes
Apr–Jun 2026 (Phase 4 baseline) | 5 | 0 | 5 | 0 | 5 | 0 | MFA enforcement, GHAS, PIM, Nessus scan schedule, Sentinel alert rules. All HIGH-impact, all CISO-approved. All completed.
Jul–Sep 2026 (Phase 5 — Q3) | 5 | 2 | 3 | 0 | 5 | 0 | S3 Object Lock and Azure Immutable Blob (standard). Kubernetes PSS enforcement, Dependabot, cert-manager (normal). 0 emergency, 0 rollbacks.
Oct 2026 (Phase 5 — partial month) | 2 | 0 | 2 | 0 | 1 | 0 | cert-manager automation completed. SentinelWatch per-analyst access in progress (Dec 2026 deadline). 0 emergency changes.
Nov–Dec 2026 (planned) | TBC | TBC | TBC | 0 | TBC | 0 | Tier 2 vendor assessments. MedLink Gulf assessment completion. SentinelWatch access implementation due Dec 2026.
CUMULATIVE (Apr–Oct 2026) | 12 | 2 | 10 | 0 | 11 | 0 | 12 changes logged since Phase 4. 0 emergency changes. 0 rollbacks. 11 completed, 1 in progress (CHG-011).
Phase 5 change health (Oct 2026): 0 emergency changes (target: <5%) ¦ 0 rollbacks (target: <10%) ¦ 0 changes without approval (target: 0) ¦ 0 HIGH-impact changes without CISO approval (target: 0) ¦ 100% of HIGH-impact changes have post-implementation verification.