## Audit Checklist
ISMS-PEV-004 ¦ Internal Audit Checklist ¦ ISO/IEC 27001:2022 Clause 9.2 ¦ Project HealthSec ¦ MediSync Technologies Pvt. Ltd.
Audit Lead: [External consultant — to be appointed] ¦ Audit Period: 9–11 December 2026 ¦ v1.0 ¦ November 2026 ¦ Finding codes: CONF=Conforming OBS=Observation MINOR=Minor NCR MAJOR=Major NCR P=Positive finding ¦ Status: Pending / In progress / Complete ¦ Classification: Confidential — Internal Use Only
Test ID | Clause / Control | Audit Question | Evidence Required | Evidence Received? | Auditee / Interviewee | Audit Finding (notes) | Finding Classification | Finding Ref (if NCR) | Tested By | Test Date | Status
CLAUSE 4 — CONTEXT OF THE ORGANISATION (AT-001 to AT-003)
AT-001 | 4.1 | Is the context analysis (ISMS-INI-006) current and does it reflect MediSync's current operating environment, including the DPDP Act 2023 and UAE PDPL obligations? | ISMS-INI-006 Context Analysis Report (current version). ISMS-INI-010 Legal Register (confirm DPDP Act and UAE PDPL entries are current). Ask: when was this last formally reviewed? |  | Meera Iyer (ISMS Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-002 | 4.2 | Are interested parties identified and their requirements documented? Does the register reflect the current enterprise customer base (~180+ hospitals)? | ISMS-INI-009 Interested Parties Register. ISMS-INI-010 Legal Register. Confirm entry count and last review date. |  | Meera Iyer (ISMS Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-003 | 4.3 | Is the ISMS scope (ISMS-INI-011) documented, appropriate, and does it accurately reflect all four locations, all 8 products, and both cloud regions? | ISMS-INI-011 Scope Document. Ask: are there any systems or processes within MediSync that handle patient data but are excluded from scope? If so, why? |  | Vikram Sundaram (CISO) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
CLAUSE 5 — LEADERSHIP (AT-004 to AT-006)
AT-004 | 5.1 / 5.2 | Is the IS Policy (ISMS-LDR-001) approved by top management, communicated to all staff, and acknowledged? Has it been reviewed within the last 12 months? | ISMS-LDR-001 IS Policy (version and approval date). ISMS-LDR-008 Policy Approval Record. ISMS-SUP-004 Training Records — policy acknowledgement records for sample of 5 named staff. Ask: when was the policy last reviewed? |  | Vikram Sundaram (CISO) + Priya Subramaniam (HR) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-005 | 5.3 | Are ISMS roles, responsibilities, and authorities defined and communicated? Is the CISO formally appointed? Is the Deputy ISMS Manager confirmed? | ISMS-LDR-007 CISO Appointment Record. ISMS-LDR-005 Roles Register. ISMS-LDR-003 Governance Chart. Confirm Rohan Sharma is named as Deputy ISMS Manager. |  | Meera Iyer (ISMS Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-006 | 5.1 (Steering Committee) | Is the Steering Committee constituted and meeting per its charter? Sample the last 2 sets of minutes for evidence of active management engagement with ISMS agenda items. | ISMS-LDR-006 Management Review Charter. Last 2 Steering Committee meeting minutes. Confirm: were all mandatory agenda items (A-01 to A-14) addressed? Were decisions recorded? |  | Meera Iyer (ISMS Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
CLAUSE 6 — PLANNING (AT-007 to AT-010)
AT-007 | 6.1.2 | Is the risk assessment methodology (ISMS-PLN-001) being followed? Is the Risk Register (ISMS-PLN-004) current with all 21 risks scored and Phase 5 reassessment (ISMS-OPS-011) incorporated? | ISMS-PLN-001 Risk Assessment Methodology. ISMS-PLN-004 Risk Register (confirm 21 risks, Phase 5 scores). ISMS-OPS-011 Risk Reassessment Report. Confirm R-006, R-007, R-015 show as CLOSED. |  | Vikram Sundaram (CISO) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-008 | 6.1.3 / SoA | Is the Statement of Applicability (ISMS-PLN-006) complete? Are all 93 Annex A controls addressed with inclusion/exclusion justification? Do all "FI" entries have retrievable evidence in ISMS-OPS-002? | ISMS-PLN-006 SoA. ISMS-OPS-002 Control Evidence Log. Sample test: select 5 controls marked FI — confirm the cited evidence location in GRC Repository is accessible and the evidence is current. |  | Vikram Sundaram (CISO) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-009 | 6.1.3 / Risk treatment | Is the Risk Treatment Plan (ISMS-PLN-005) current? Are closed risks (R-006, R-007, R-015) correctly marked Complete? Are the three remaining MED-HIGH risks (R-002, R-004, R-009) each linked to active treatment actions? | ISMS-PLN-005 Risk Treatment Plan. Confirm treatment action status matches ISMS-OPS-011 conclusions. Ask: what is the target date for R-002 residual score reduction? |  | Vikram Sundaram (CISO) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-010 | 6.2 | Are IS objectives (ISMS-LDR-002) documented, measurable, and being monitored? Are OO-08 questionnaire response times being tracked as committed at LDR-009? | ISMS-LDR-002 IS Objectives Document (11 strategic + 10 operational). ISMS-PEV-001 Monitoring Plan — confirm KPI-017 (questionnaire SLA) is being measured. Ask: what is the current questionnaire response time? |  | Meera Iyer (ISMS Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
CLAUSE 7 — SUPPORT (AT-011 to AT-014)
AT-011 | 7.2(d) | Are training records being maintained as evidence of competence? Sample 5 named individuals — do their training records exist, are they current, and do they include the policy acknowledgement? | ISMS-SUP-004 Training Records (Tab 1 — Training Log). Select 5 staff from different departments. Confirm each has: (1) policy acknowledgement record, (2) core awareness completion record. Check certificate register — confirm Sana Al Farsi AZ-500 and Neha Choudhury CEH are flagged and renewal is tracked. |  | Priya Subramaniam (Head of HR) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-012 | 7.3 | Is the security awareness programme operating? Have all departments reached ≥95% completion? Is the phishing simulation baseline established? | ISMS-SUP-004 Tab 2 (Dept Completion Summary) — confirm ≥95% per department (except Procurement — vacancy noted). ISMS-SUP-006 Attendance Log — confirm Champion onboarding session record. Phishing simulation baseline result (Aug 2026). Ask: when is the second simulation scheduled? |  | Priya Subramaniam (Head of HR) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-013 | 7.4 | Is the communication plan (ISMS-SUP-007) being followed? Are the three regulatory notification paths (CERT-In, DPDP Act, UAE PDPL) known and accessible to the relevant owners? | ISMS-SUP-007 Communication Plan. Ask Head of Legal: if an incident occurred tonight, what would you do and in what order regarding CERT-In notification? Answer should reference OPS-005 Track 1 and the 6-hour clock starting from awareness. |  | Omar Al Mansoori (Head of Legal) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-014 | 7.5 | Does the Document Register (ISMS-SUP-009) match what is actually in the GRC Repository? Spot-check 5 documents listed as Approved. | ISMS-SUP-009 Document Register (Master List). Navigate to the GRC Repository — retrieve 5 documents listed as Approved and confirm they exist at the stated location, are the stated version, and have the stated status. Any document listed but not findable = nonconformity. |  | Meera Iyer (ISMS Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
CLAUSE 8 — OPERATION + PRIORITY GAP CLOSURE TESTS (AT-015 to AT-024)
AT-015 | 8.1 / A5.37 | Are the operational security procedures (ISMS-OPS-001) being followed in practice — not just documented? Test D-01 (access control) and D-02 (cloud config) against live systems. | ISMS-OPS-001 Operational Security Procedures. For D-01: ask IT Operations Lead to show the Entra ID PIM activation log for the last month — confirm activations are within normal hours and have approval records. For D-02: ask Cloud Infrastructure to show the current security group rules for one production VPC — confirm no 0.0.0.0/0 inbound except port 443 on API-GW. |  | IT Operations Lead + Sana Al Farsi |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-016 | A5.15 / A5.18 — G-04 | [PRIORITY] Access review — hospital-facing admin accounts. Is G-04 (stale admin accounts) genuinely closed? Pull the Q3 2026 review and confirm the 2 stale accounts were disabled, with Entra audit log evidence. | ISMS-OPS-009 Access Review Log (REV-001). Entra ID audit log — confirm disablement of the 2 stale accounts on the dates stated in REV-001. Confirm Q4 2026 review is scheduled. Ask CISO: what happens if a hospital IT contact leaves without notifying MediSync? |  | Vikram Sundaram (CISO) + IT Operations Lead |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-017 | A5.24–A5.26 — R-006 | [PRIORITY] Incident management — R-006 closure. Is the IR procedure genuinely operational? Can the SOC Manager explain the CERT-In 6-hour clock without prompting from the document? | ISMS-OPS-005 Incident Management Procedure. ISMS-OPS-006 Incident Register (confirm 3 entries). Ask SOC Manager: walk me through what happens from the moment a suspicious alert fires at 3am on a Saturday. Listen for: SentinelWatch escalation, CISO notification timeline, CERT-In clock trigger point. The answer should not require consulting the document. |  | Neha Choudhury (SOC Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-018 | A5.23 / A8.9 — G-11 | [PRIORITY] Cloud configuration baseline — is the Sentinel monitoring actually catching drift? Request a live demonstration. | ISMS-OPS-001 D-02.3. Pull the Sentinel alert rule list — confirm the 5 mandatory alert categories have active rules. Ask Cloud Infrastructure: demonstrate what happens when I temporarily make a bucket public. Watch for: Sentinel alert firing, severity classification, SOC notification. (If a live test is not acceptable, review the most recent test result and alert log.) |  | Sana Al Farsi (Head of Cloud Infra) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-019 | A8.13 — R-015 | [PRIORITY] Backup immutability — is S3 Object Lock and Azure Immutable Blob Storage active right now on production backup buckets? | ISMS-OPS-003 Section 2.2 Domain C (VaultArchive assessment). ISMS-OPS-008 DR test record (Appendix A). Ask Cloud Infrastructure to show the S3 Object Lock settings on the EHR-CORE backup bucket in the AWS console — confirm Compliance mode is active. Also show the Azure Immutable Blob Storage policy on the UAE backup container. |  | Sana Al Farsi (Head of Cloud Infra) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-020 | A5.19 / A5.20 — G-07 | [PRIORITY] Vendor assessments — are VaultArchive and SentinelWatch assessments complete? Is MedLink Gulf complete (expected Nov 2026)? | ISMS-OPS-003 Vendor Assessment Reports. ISMS-OPS-004 Supplier Register. Confirm: VaultArchive score (88/100), security schedule signed date. SentinelWatch score (82/100), security schedule signed, 4 conditions tracked. MedLink Gulf: confirm assessment complete, score, and security schedule status. Ask: what would happen if a new Tier 1 vendor was needed urgently? |  | Meera Iyer (ISMS Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-021 | A6.3 — awareness | [PRIORITY] Awareness training — is the evidence retrievable? Select 3 staff names from ISMS-SUP-004 and confirm their completion records exist in the awareness platform. | ISMS-SUP-004 Training Log. ISMS-SUP-005 Awareness Plan. Select 3 staff from different departments (ask HR to pull them up in the platform during the audit). Confirm: completion status, score, date. Ask: what happens to someone who refuses to complete the training? |  | Priya Subramaniam (Head of HR) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-022 | A8.24 — G-14 | [PRIORITY] Key management — are API secrets being rotated within 90 days? Is AWS KMS auto-rotation confirmed active? | ISMS-OPS-001 D-06.2. AWS Secrets Manager rotation report (confirm 0 secrets >90 days). AWS KMS console — confirm CMK automatic rotation enabled for India region. Azure Key Vault — confirm rotation policy active. Ask: what is the process if a secret is found to be compromised at 2am? |  | Sana Al Farsi (Head of Cloud Infra) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-023 | A8.32 — change management | Are production changes being logged in ISMS-OPS-010? Do all logged changes have approval records? Are there any Sentinel drift alerts without a corresponding change record? | ISMS-OPS-010 Change Management Log (14 changes logged). Select 3 changes — confirm each has a documented approval (CISO sign-off for HIGH-impact). Pull Sentinel configuration drift alerts for Oct–Nov 2026 — do any drift events lack a corresponding change record in OPS-010? |  | Vikram Sundaram (CISO) + IT Operations Lead |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-024 | A8.8 — vulnerability management | Is the monthly vulnerability scan completing and are findings being tracked to remediation within SLA? | Tenable Nessus scan completion report (most recent — confirm ≥95% of hosts scanned). ISMS-OPS-002 Control Evidence Log (vulnerability findings section). Ask SOC Manager: what was the most recent Critical finding? When was it remediated? Show the remediation evidence. |  | Neha Choudhury (SOC Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
CLAUSE 9 — PERFORMANCE EVALUATION (AT-025)
AT-025 | 9.1 | Are KPIs being measured per ISMS-PEV-001? Is the monthly GRC status report being produced? Are escalation thresholds being triggered when breached? | ISMS-PEV-001 Monitoring Plan. ISMS-PEV-002 KPI Log (last 3 months). Last 3 monthly GRC status reports. Ask: show me the last time an escalation threshold was breached — what happened? |  | Meera Iyer (ISMS Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
CLAUSE 10 — IMPROVEMENT (AT-026 to AT-027)
AT-026 | 10.1 / 10.2 | Is the nonconformity process operational? Are the 8 lessons learned from the 2024 near-misses and the October 2026 tabletop all closed? Is the corrective action register being maintained? | ISMS-IMP-001 Nonconformity Procedure. ISMS-IMP-002 Nonconformity Register. ISMS-OPS-006 Lessons Learned (Tab 3 — confirm LL-001 to LL-008 all status Complete). ISMS-IMP-004 Continual Improvement Log. Ask: if a control was found to be ineffective today, walk me through what would happen. |  | Meera Iyer (ISMS Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
AT-027 | 10.2 | Is the continual improvement log (ISMS-IMP-004) being used? Have any improvements been identified and tracked since Phase 5 launched? | ISMS-IMP-004 Continual Improvement Log. ISMS-OPS-010 Change Log (CHG-010 cert-manager automation is an example of improvement driven by a DR test finding). Ask: name one improvement you have made to the ISMS since Phase 5 launched that was not driven by a nonconformity. |  | Meera Iyer (ISMS Manager) |  |  |  | [Audit lead] | [Dec 2026] | Pending — fieldwork 9–11 Dec 2026
TOTAL AUDIT TESTS: 27 ¦ Priority gap closure tests (marked [PRIORITY]): 7 ¦ All tests status: Pending — fieldwork 9–11 December 2026 ¦ Finding codes: CONF=Conforming ¦ OBS=Observation ¦ MINOR=Minor nonconformity ¦ MAJOR=Major nonconformity ¦ P=Positive finding ¦ Complete this checklist during fieldwork — do not pre-fill findings before evidence has been reviewed.

## Evidence Tracker
ISMS-PEV-004 ¦ Evidence Tracker ¦ Documents requested, received, and reviewed during fieldwork
One row per evidence item requested. Updated by audit lead during fieldwork. ¦ Evidence not received by the end of fieldwork is flagged as a potential finding. ¦ All evidence reviewed is retained in the audit working papers file.
Evid. ID | Audit Test Ref | Document / Evidence Requested | GRC Repo Path / Source | Requested From | Date Requested | Date Received | Status
EV-001 | AT-001 | ISMS-INI-006 Context Analysis Report v1.0 | /Phase 1 — Initiation/ | Meera Iyer | [Dec 2026] |  | Pending
EV-002 | AT-002 | ISMS-INI-009 Interested Parties Register v1.0 | /Phase 1 — Initiation/ | Meera Iyer | [Dec 2026] |  | Pending
EV-003 | AT-003 | ISMS-INI-011 ISMS Scope Document v1.0 | /Phase 1 — Initiation/ | Meera Iyer | [Dec 2026] |  | Pending
EV-004 | AT-004 | ISMS-LDR-001 IS Policy v1.0 + ISMS-LDR-008 Policy Approval Record | /Phase 2 — Leadership/ | Meera Iyer | [Dec 2026] |  | Pending
EV-005 | AT-004 | Training Records — policy acknowledgements (5 named staff) | /Phase 4 — Support/ISMS-SUP-004 | Priya Subramaniam | [Dec 2026] |  | Pending
EV-006 | AT-005 | ISMS-LDR-007 CISO Appointment + ISMS-LDR-005 Roles Register | /Phase 2 — Leadership/ | Meera Iyer | [Dec 2026] |  | Pending
EV-007 | AT-006 | Last 2 Steering Committee meeting minutes | /Phase 2 — Leadership/ (latest) | Meera Iyer | [Dec 2026] |  | Pending
EV-008 | AT-007 | ISMS-PLN-004 Risk Register v1.0 (current) | /Phase 3 — Planning/ | Meera Iyer | [Dec 2026] |  | Pending
EV-009 | AT-007 | ISMS-OPS-011 Risk Reassessment Report v1.0 | /Phase 5 — Operation/ | Meera Iyer | [Dec 2026] |  | Pending
EV-010 | AT-008 | ISMS-PLN-006 SoA v1.0 + ISMS-OPS-002 Control Evidence Log | /Phase 3 — Planning/ + /Phase 5 — Operation/ | Meera Iyer | [Dec 2026] |  | Pending
EV-011 | AT-011 | ISMS-SUP-004 Training Records — sample 5 named individuals | /Phase 4 — Support/ | Priya Subramaniam | [Dec 2026] |  | Pending
EV-012 | AT-012 | ISMS-SUP-004 Tab 2 Dept Completion Summary (current) | /Phase 4 — Support/ | Priya Subramaniam | [Dec 2026] |  | Pending
EV-013 | AT-012 | Phishing simulation baseline results (Aug 2026) | /Training Records/Phishing Simulations/ | Neha Choudhury | [Dec 2026] |  | Pending
EV-014 | AT-014 | ISMS-SUP-009 Document Register + 5 documents cross-checked | /Phase 4 — Support/ | Meera Iyer | [Dec 2026] |  | Pending
EV-015 | AT-015 | Entra ID PIM activation log (last 30 days) | Microsoft Entra ID admin portal | IT Operations Lead | [Dec 2026] |  | Pending
EV-016 | AT-015 | Production VPC security group rules (one VPC) | AWS Console / Azure Portal | Sana Al Farsi | [Dec 2026] |  | Pending
EV-017 | AT-016 [PRIORITY] | ISMS-OPS-009 Access Review Log REV-001 (Q3 2026) | /Phase 5 — Operation/ | Meera Iyer | [Dec 2026] |  | Pending
EV-018 | AT-016 [PRIORITY] | Entra ID audit log — disablement of 2 stale accounts (Sep 2026) | Microsoft Entra ID audit log | IT Operations Lead | [Dec 2026] |  | Pending
EV-019 | AT-017 [PRIORITY] | ISMS-OPS-005 IR Procedure + ISMS-OPS-006 Incident Register | /Phase 5 — Operation/ | Neha Choudhury | [Dec 2026] |  | Pending
EV-020 | AT-018 [PRIORITY] | Sentinel alert rules list (5 mandatory categories) | Microsoft Sentinel workspace | Neha Choudhury | [Dec 2026] |  | Pending
EV-021 | AT-019 [PRIORITY] | AWS S3 Object Lock console screenshot — EHR-CORE bucket | AWS S3 console (live demonstration) | Sana Al Farsi | [Dec 2026] |  | Pending
EV-022 | AT-019 [PRIORITY] | Azure Immutable Blob Storage policy — UAE backup container | Azure Portal (live demonstration) | Sana Al Farsi | [Dec 2026] |  | Pending
EV-023 | AT-019 [PRIORITY] | ISMS-OPS-003 VaultArchive assessment + ISMS-OPS-008 DR test record | /Phase 5 — Operation/ | Meera Iyer | [Dec 2026] |  | Pending
EV-024 | AT-020 [PRIORITY] | ISMS-OPS-003 Vendor Assessment Reports (all 3 Tier 1) | /Phase 5 — Operation/ | Meera Iyer | [Dec 2026] |  | Pending
EV-025 | AT-020 [PRIORITY] | ISMS-OPS-004 Supplier Register (current) | /Phase 5 — Operation/ | Meera Iyer | [Dec 2026] |  | Pending
EV-026 | AT-021 [PRIORITY] | Awareness platform — completion records for 3 named staff | Awareness platform admin portal | Priya Subramaniam | [Dec 2026] |  | Pending
EV-027 | AT-022 [PRIORITY] | AWS Secrets Manager rotation report | AWS Secrets Manager console | Sana Al Farsi | [Dec 2026] |  | Pending
EV-028 | AT-022 [PRIORITY] | AWS KMS CMK rotation status — India region | AWS KMS console (live demonstration) | Sana Al Farsi | [Dec 2026] |  | Pending
EV-029 | AT-023 | ISMS-OPS-010 Change Management Log (all 14 changes) | /Phase 5 — Operation/ | Meera Iyer | [Dec 2026] |  | Pending
EV-030 | AT-023 | Sentinel configuration drift alerts Oct–Nov 2026 | Microsoft Sentinel alert log | Neha Choudhury | [Dec 2026] |  | Pending
EV-031 | AT-024 | Tenable Nessus last scan report (most recent monthly) | Tenable Nessus scan management | Neha Choudhury | [Dec 2026] |  | Pending
EV-032 | AT-025 | ISMS-PEV-002 KPI Log (last 3 months) + last 3 monthly GRC reports | /Phase 6 — Performance/ | Meera Iyer | [Dec 2026] |  | Pending
EV-033 | AT-026 | ISMS-OPS-006 Lessons Learned Tab 3 (LL-001 to LL-008) | /Phase 5 — Operation/ | Meera Iyer | [Dec 2026] |  | Pending

## Interview Log
ISMS-PEV-004 ¦ Interview Log ¦ Auditee sessions scheduled and completed
All interviews are conducted by the audit lead. The ISMS Manager facilitates scheduling but does not attend interviews unless the auditee requests it. ¦ Interviews are approximately 45 minutes. Notes from each interview are retained in the audit working papers.
Session ID | Auditee Name | Role | Date / Time | Audit Tests Covered | Duration (planned) | Topics / Key Questions | Status
INT-001 | Meera Iyer | ISMS Manager / Head of GRC | 9 Dec 2026, 09:00–09:45 IST | AT-001, AT-002, AT-003, AT-007, AT-014, AT-025, AT-026 | 45 min | Context, scope, risk register currency, document control, KPI measurement, corrective actions. Opening session — ISMS overview. | Scheduled
INT-002 | Vikram Sundaram | CISO | 9 Dec 2026, 10:00–10:45 IST | AT-007, AT-008, AT-009, AT-010, AT-015, AT-016, AT-023 | 45 min | Risk assessment, SoA, risk treatment, access review, change management, PIM activation review. Focus: R-006 closure rationale. | Scheduled
INT-003 | Neha Choudhury | SOC Manager | 9 Dec 2026, 11:00–11:45 IST | AT-017, AT-018, AT-024, AT-025 | 45 min | Incident management procedure (CERT-In clock walk-through), Sentinel alert rules, vulnerability scan process and SLA compliance. KEY: ask her to walk through IR without consulting the document. | Scheduled
INT-004 | Sana Al Farsi | Head of Cloud Infrastructure | 9 Dec 2026, 14:00–14:45 IST | AT-015, AT-019, AT-022 | 45 min | Live demonstration: S3 Object Lock, Azure Immutable Blob, AWS KMS rotation, PIM activation log, production security group rules. | Scheduled
INT-005 | Advait Deshmukh | VP Engineering | 10 Dec 2026, 09:00–09:45 IST (video — Pune) | AT-015 (D-05) | 45 min | SDLC controls: GitHub branch protection, GHAS secret scanning, Kubernetes PSS, Dependabot. Ask to demonstrate a branch protection rule. | Scheduled
INT-006 | Priya Subramaniam | Head of HR | 10 Dec 2026, 10:00–10:45 IST | AT-011, AT-012, AT-021 | 45 min | Training records completeness, awareness platform completion rates, phishing simulation results, new joiner induction process. | Scheduled
INT-007 | Omar Al Mansoori | Head of Legal (UAE) | 10 Dec 2026, 15:00–15:45 UAE time (video — Dubai) | AT-013 | 45 min | CERT-In and DPDP Act notification paths knowledge check. Ask: if an incident occurred tonight involving UAE patient data, walk me through your notification obligations. | Scheduled
INT-008 | IT Operations Lead | IT Operations | 11 Dec 2026, 09:00–09:45 IST | AT-015 (D-01), AT-016 | 45 min | Access provisioning process (JML SLA), Entra ID access review execution, stale account remediation evidence from Q3 2026 review. | Scheduled
INT-009 | Meera Iyer | ISMS Manager (closing) | 11 Dec 2026, 16:00–16:30 IST | All — closing meeting | 30 min | Closing meeting: verbal summary of preliminary findings. ISMS Manager to confirm factual accuracy of any findings before the draft report is issued. | Scheduled