## Findings Register
ISMS-PEV-006 ¦ Internal Audit Findings Register ¦ ISO/IEC 27001:2022 Clause 9.2 / 10.1 ¦ Project HealthSec ¦ MediSync Technologies Pvt. Ltd.
Owner: Meera Iyer, ISMS Manager ¦ v1.0 ¦ December 2026 ¦ One row per finding from all audit engagements. ¦ Types: MAJOR NCR ¦ MINOR NCR ¦ OBS (Observation) ¦ POS (Positive) ¦ Status: Open ¦ In Progress ¦ Closed ¦ Noted (observations) ¦ Classification: Confidential — Internal Use Only
Finding Ref | Audit Ref | Type | Finding Summary | ISO 27001:2022 Clause / Control | Audit Test Ref | Auditee / Area | Report Date | CAR Ref (NCRs only) | Corrective Action Owner | CA Target Date | CA Verified By | CA Closed Date | Status
AUDIT 1 — FULL SCOPE (December 2026) ¦ Fieldwork: 9–11 Dec 2026 ¦ Report issued: 22 Dec 2026
POS-001 | Audit 1 (Dec 2026) | POS | Backup immutability confirmed live — S3 Object Lock (Compliance mode) and Azure Immutable Blob Storage active on all production backup resources. Confirmed via live console demonstration, not documentary review alone. | A5.29; A8.13 | AT-019 | Sana Al Farsi (Head of Cloud Infra) | 22 Dec 2026 | N/A — positive finding | N/A | N/A | N/A | N/A | Noted
POS-002 | Audit 1 (Dec 2026) | POS | IR procedure embedded in SOC practice — SOC Manager described the full CERT-In notification sequence accurately from memory, including the correct clock trigger point (MEDIUM or above classification). Tabletop findings clearly absorbed. | A5.24; A5.25 | AT-017 | Neha Choudhury (SOC Manager) | 22 Dec 2026 | N/A — positive finding | N/A | N/A | N/A | N/A | Noted
NCR-001 | Audit 1 (Dec 2026) | MINOR NCR | SoA evidence gap — control A5.8 (Information security in project management) marked FI in ISMS-PLN-006 but evidence cited in ISMS-OPS-002 (/Phase 5 — Operation/ISMS-OPS-001) not retrievable at that GRC Repository path. Evidence of implementation cannot be independently confirmed. | Clause 6.1.3(d); Clause 7.5 | AT-008 | Vikram Sundaram (CISO) | 22 Dec 2026 | CAR-001 | Vikram Sundaram (CISO) | 31 Jan 2027 | [Audit lead — Audit 2] | [Feb 2027] | Open
NCR-002 | Audit 1 (Dec 2026) | MINOR NCR | AZ-500 certification (Sana Al Farsi — Head of Cloud Infrastructure) expired August 2025. No renewal booking confirmed and no documented risk acceptance or compensating control assessment recorded in 16 months since expiry. | Clause 7.2 — Competence | AT-011 | Priya Subramaniam (Head of HR) | 22 Dec 2026 | CAR-002 | Priya Subramaniam (HR) + Sana Al Farsi | 31 Jan 2027 | [Audit lead — Audit 2] | [Feb 2027] | Open
NCR-003 | Audit 1 (Dec 2026) | MINOR NCR | One production security group inbound rule modification (14 November 2026, AWS ap-south-1, EHR-CORE) found in Sentinel drift alert log with no corresponding approved change record in ISMS-OPS-010. IT Operations Lead confirmed the change was made without prior approval during a connectivity troubleshooting session. | A8.32; ISMS-PLN-009; ISMS-OPS-001 D-02.2 | AT-023 | IT Operations Lead | 22 Dec 2026 | CAR-003 | IT Operations Lead + CISO | 31 Jan 2027 | [Audit lead — Audit 2] | [Feb 2027] | Open
OBS-001 | Audit 1 (Dec 2026) | OBS | Head of Procurement vacancy — position unfilled since Phase 4 (Month 4, now Month 11). ISMS Manager holds interim ownership of procurement-related activities. Effective but creates single-person-dependency risk and may affect perceived independence of supplier decisions. | Clause 7.1 — Resources | AT-020 | Meera Iyer (ISMS Manager) | 22 Dec 2026 | N/A — observation | Steering Committee for consideration | N/A | N/A | N/A | Noted — management response at Dec 2026 MR
OBS-002 | Audit 1 (Dec 2026) | OBS | Procurement department awareness completion at 0% — directly caused by Head of Procurement vacancy. M-04 gate condition not met for this department. Situation unchanged since Phase 4 gate. Resolution requires filling the vacancy. | Clause 7.3 — Awareness | AT-012 | Priya Subramaniam (Head of HR) | 22 Dec 2026 | N/A — observation | Steering Committee for consideration | N/A | N/A | N/A | Noted — management response at Dec 2026 MR
OBS-003 | Audit 1 (Dec 2026) | OBS | MedLink Gulf Tier 1 assessment — fieldwork confirmed complete (preliminary score: Low risk band) but formal assessment report not yet issued and ISMS-OPS-004 not updated. Administrative gap only — assessment was conducted within the required period. | A5.22 — Monitoring of supplier services | AT-020 | Meera Iyer (ISMS Manager) | 22 Dec 2026 | N/A — observation | Meera Iyer (ISMS Manager) | Jan 2027 | N/A | N/A | Noted — target: report issued Jan 2027
AUDIT 2 — PRE-STAGE 2 TARGETED (February 2027) ¦ Fieldwork planned: 10–12 Feb 2027 ¦ Pending
TBD | Audit 2 (Feb 2027) | [Finding type] | [To be populated after Audit 2 fieldwork — 10–12 February 2027. Audit 2 will confirm NCR-001, NCR-002, NCR-003 corrective action closure and conduct pre-Stage 2 evidence completeness review.] | [TBC] | [TBC] | [TBC] | [Feb 2027] | [TBC] | [TBC] | [TBC] | [TBC] | [TBC] | Pending
AUDIT 1 SUMMARY: Major NCRs: 0 ¦ Minor NCRs: 3 ¦ Observations: 3 ¦ Positive findings: 2 ¦ Overall conclusion: ISMS substantially conforms to ISO 27001:2022. Recommended to proceed to Stage 1 subject to closure of 3 minor NCRs. ¦ All NCR corrective action plans due 31 January 2027. Closure confirmed at Audit 2 (Feb 2027).

## Corrective Action Tracker
ISMS-PEV-006 ¦ Corrective Action Tracker ¦ NCR corrective actions only ¦ Clause 10.1 — Nonconformity and Corrective Action
One row per NCR corrective action plan. ¦ Corrective action plans must be submitted to the ISMS Manager by 31 January 2027. ¦ Closure is confirmed by the audit lead at Audit 2 (10–12 February 2027) via evidence review. ¦ Logged in ISMS-IMP-002 (Nonconformity Register) — this tab is the Phase 6 tracking view.
CAR Ref | NCR Ref | NCR Description (brief) | Root Cause Analysis | Corrective Action Planned | Action Owner | CA Plan Submitted? | CA Target Date | Evidence of Completion | Status
CAR-001 | NCR-001 | A5.8 SoA evidence gap — FI control with non-retrievable evidence | Root cause: when ISMS-OPS-002 was populated during Phase 5, the evidence location for A5.8 was entered as a generic OPS-001 path rather than a specific document or sub-path. The architecture review records either exist in a sub-folder not cited in OPS-002, or they were never formally documented as a discrete evidence artefact. | Option A: Locate existing architecture review records (e.g., sprint planning documents or design review notes containing security requirements for in-scope features) and store at a specific, retrievable GRC Repository path. Update OPS-002 evidence location to that specific path. Option B: If no such records exist as discrete documents, create a representative architecture review record covering the top 3 security-relevant feature developments from Phase 5 and store at the cited path. Update OPS-002. Option C: If neither option A nor B is feasible by 31 Jan 2027, update the SoA status for A5.8 from FI to IP (In Progress) and OPS-002 accordingly. This reduces the claim but removes the nonconformity. | Vikram Sundaram (CISO) | [Pending — due 31 Jan 2027] | 31 Jan 2027 | Architecture review evidence stored at specific GRC Repository path, retrievable by audit lead without assistance. OR SoA updated to IP with OPS-002 reflecting accurate status. | Open — CA plan not yet submitted
CAR-002 | NCR-002 | AZ-500 certification lapsed 16 months — no documented renewal action | Root cause: The AZ-500 expiry was flagged in ISMS-SUP-004 (Certificate Register) when the register was created in Phase 4, but no formal ownership of the renewal action was assigned. The ISMS Manager's attention was focused on Phase 5 deliverables; HR treated the certificate register as an informational document rather than an action-generating document. The result was a documented gap with no one explicitly responsible for closing it. | Option A: Book and confirm an AZ-500 renewal course (or AZ-500 equivalent, e.g., AZ-305 Azure Solutions Architect Expert, which subsumes AZ-500 scope). Provide booking confirmation as evidence. Target: examination date confirmed by 31 Jan 2027. Option B: If scheduling an examination by 31 Jan 2027 is not feasible, document a CISO-approved risk acceptance noting: (1) the compensating controls active during the gap (the OPS-001 D-02 baseline does not require real-time Azure expertise to enforce), (2) the planned resolution timeline. Risk acceptance must be signed by CISO and filed in the GRC Repository. | Priya Subramaniam (Head of HR) in coordination with Sana Al Farsi | [Pending — due 31 Jan 2027] | 31 Jan 2027 | Evidence of AZ-500 or equivalent renewal booking confirmation with confirmed exam date. OR CISO-signed risk acceptance with compensating controls documented and planned resolution timeline. | Open — CA plan not yet submitted
CAR-003 | NCR-003 | Production security group modified 14 Nov 2026 without prior approval record | Root cause: The IT Operations Lead understood that urgent connectivity troubleshooting justified immediate action, and was not aware that even emergency changes require verbal CISO approval before implementation (not after). The emergency change process in ISMS-OPS-010 Tab 2 had not been sufficiently briefed to IT Operations. The change management process was understood at the standard-change level but the emergency change track was not. | Step 1: Post-incident review — Confirm the 14 November security group modification is consistent with the ISMS-OPS-001 D-02.1 cloud configuration baseline. Document the review outcome in ISMS-OPS-010 as a retrospective change record (CHG-015), clearly marked as a retrospective approval. Step 2: Brief IT Operations team on the emergency change process — specifically ISMS-OPS-010 Tab 2: even for urgent changes, verbal CISO approval must be obtained immediately before implementation, with formal approval within 48 hours. Brief to include the specific scenario of connectivity troubleshooting (the trigger for this NCR). Step 3: Close the Sentinel alert correctly in the SOC alert log, noting the retrospective change review as the closure reason. | IT Operations Lead (Steps 1 and 3) + CISO (Step 2 sign-off and brief) | [Pending — due 31 Jan 2027] | 31 Jan 2027 | CHG-015 retrospective change record in OPS-010 (confirming configuration is baseline-compliant). Evidence of IT Operations team briefing (attendance record or email confirmation). Sentinel alert closed with closure note. | Open — CA plan not yet submitted
AUDIT 2 CLOSURE CONFIRMATION (February 2027) — To be completed by audit lead after fieldwork
At Audit 2 (10–12 Feb 2027), the audit lead reviews evidence submitted for CAR-001, CAR-002, and CAR-003. ¦ For each CAR: the audit lead updates Column J (Status) from "Open" to "Closed" or "Closed with observation" based on evidence reviewed. ¦ A corrective action that addresses the symptom but not the root cause is "Closed with observation" — not "Closed". ¦ Any CAR not closed at Audit 2 becomes an input to the Stage 2 certification audit and is noted in the Audit 2 report (ISMS-PEV-005b).