## Nonconformity Register
ISMS-IMP-001 ¦ Nonconformity Register ¦ ISO/IEC 27001:2022 Clause 10.1 ¦ Project HealthSec ¦ MediSync Technologies Pvt. Ltd.
Owner: Meera Iyer, ISMS Manager ¦ v1.0 ¦ January 2027 ¦ Sources: Internal Audit ¦ Management Review ¦ Self-identified ¦ External ¦ Severity: MAJOR NCR ¦ MINOR NCR ¦ OBS ¦ Status: Open ¦ In Progress ¦ Closed — Pending Verification ¦ Closed — Verified ¦ Classification: Confidential — Internal Use Only
NCR Ref | Source | Severity | ISO 27001:2022 Clause / Control | Nonconformity Description | Detected By | Date Detected | Process Owner (area affected) | Corrective Action Owner | CA Plan Submitted? | CA Plan Approved? | CA Target Date | CA Completed Date | Effectiveness Verified? | Verification Method | Status
INTERNAL AUDIT 1 — DECEMBER 2026 ¦ 3 minor NCRs ¦ CA target: 31 Jan 2027 ¦ Closure confirmation: Audit 2 (Feb 2027)
NCR-001 | Internal Audit (Audit 1 — Dec 2026) | MINOR NCR | Clause 6.1.3(d); Clause 7.5; A5.8 | Control A5.8 (Information security in project management) marked Fully Implemented in ISMS-PLN-006 (SoA) but evidence cited in ISMS-OPS-002 (/Phase 5 — Operation/ISMS-OPS-001) was not retrievable at that path during the audit. Evidence of implementation could not be independently confirmed. | External audit lead (Audit 1 — Dec 2026) | 22 Dec 2026 | Vikram Sundaram (CISO — SoA owner) | Vikram Sundaram (CISO) | Yes — 2 Jan 2027 | Yes — 5 Jan 2027 (ISMS Manager) | 31 Jan 2027 | [To be completed] | No — pending | Audit 2 (Feb 2027): audit lead independently retrieves A5.8 evidence from cited GRC path without assistance from control owner. | Open — CA in progress
NCR-002 | Internal Audit (Audit 1 — Dec 2026) | MINOR NCR | Clause 7.2 (Competence) | Sana Al Farsi's AZ-500 certification expired August 2025. At audit (December 2026), 16 months lapsed with no documented renewal booking, no documented risk acceptance, and no compensating control assessment for the gap period. | External audit lead (Audit 1 — Dec 2026) | 22 Dec 2026 | Priya Subramaniam (Head of HR) | Priya Subramaniam (HR) + Sana Al Farsi | Yes — 2 Jan 2027 | Yes — 5 Jan 2027 (ISMS Manager) | 31 Jan 2027 | [To be completed] | No — pending | Audit 2 (Feb 2027): confirm AZ-500 renewal booking with examination date, OR CISO-signed risk acceptance in GRC Repository. Confirm SUP-004 Tab 3 updated with Renewal Owner and Action Due columns. | Open — CA in progress
NCR-003 | Internal Audit (Audit 1 — Dec 2026) | MINOR NCR | A8.32; ISMS-PLN-009; ISMS-OPS-001 D-02.2 | Security group inbound rule modification made 14 November 2026 (AWS ap-south-1, EHR-CORE) found in Sentinel drift alert log with no corresponding approved change record in ISMS-OPS-010. IT Operations Lead confirmed the change was made during connectivity troubleshooting without following the standard or emergency change process. | External audit lead (Audit 1 — Dec 2026; cross-ref: Sentinel alert log) | 22 Dec 2026 | IT Operations Lead (change management) | IT Operations Lead + CISO | Yes — 2 Jan 2027 | Yes — 5 Jan 2027 (ISMS Manager) | 31 Jan 2027 | [To be completed] | No — pending | Audit 2 (Feb 2027): confirm CHG-015 retrospective record in OPS-010, Sentinel alert closed with CHG-015 reference, IT Operations briefing attendance record, OPS-001 D-02.2 callout added. Knowledge check: ask IT Operations Lead to describe the emergency change process without consulting OPS-010. | Open — CA in progress
[NCR-XXX] | [Source: Internal Audit / Management Review / Self-identified / External] | [MAJOR / MINOR / OBS] | [Clause / Annex A control] | [Description of nonconformity — what was found, where, and when] | [Who identified it] | [DD Mon YYYY] | [Process owner for area affected] | [Corrective action owner] | [Date submitted] | [Date approved] | [DD Mon YYYY] | [DD Mon YYYY] | [Yes / No] | [How effectiveness will be verified at next audit or review] | [Open / In Progress / Closed — Pending Verification / Closed — Verified]
REGISTER TOTALS (January 2027): Total NCRs: 3 ¦ Major: 0 ¦ Minor: 3 ¦ Open: 3 ¦ In Progress: 0 ¦ Closed: 0 ¦ All from: Internal Audit 1 (December 2026) ¦ CA target: 31 January 2027 ¦ Closure confirmation: Audit 2 (February 2027).

## Root Cause Analysis
ISMS-IMP-001 ¦ Root Cause Analysis ¦ Why the nonconformity occurred — mandatory per Clause 10.1(b)
Root cause analysis is mandatory for every NCR. The corrective action must address the root cause — not just the symptom. ¦ An action that fixes the symptom but not the root cause is "Closed with observation" at the effectiveness review, and a new NCR is raised.
NCR Ref | Root Cause Category | Root Cause (Why) | Corrective Action (What) | Evidence Required for Closure | CA Owner
NCR-001 | Documentation / Evidence management | Root cause: When ISMS-OPS-002 was populated during Phase 5, the A5.8 evidence location was entered as a generic path (/Phase 5 — Operation/ISMS-OPS-001) rather than a specific document or sub-folder path. The A5.8 control is implemented in practice — architecture review work occurs within sprint planning — but was never formalised as a discrete, separately-retrievable ISMS evidence artefact. Contributing factor: The OPS-002 completion process had no verification step to confirm that the cited path was retrievable by someone other than the control owner. The ISMS Manager accepted the entry without independently verifying retrieval. | Immediate: Create a named architecture review record (a concise document showing security requirements assessed for the top 3 security-relevant Phase 5 features) and store it at a specific, retrievable GRC Repository path. Update ISMS-OPS-002 A5.8 evidence location field to the specific path and filename. Systemic: Add a "verify retrieval" step to the OPS-002 completion process — every FI entry must be retrievable by the ISMS Manager (not only the control owner) before it is marked complete. Update the OPS-002 completion guidance note. | 1. Architecture review record created and stored at specific path. 2. ISMS-OPS-002 updated with specific retrievable path (filename included). 3. ISMS Manager confirms document is retrievable without assistance. 4. Audit 2: audit lead independently retrieves the document from the cited path. | Vikram Sundaram (CISO)
NCR-002 | Competence management / HR process gap | Root cause: The Certificate Register (ISMS-SUP-004 Tab 3) was created as an informational inventory — recording expiry dates but not designed as an action-generating document. No individual was explicitly assigned ownership of the renewal action for each certificate. No trigger mechanism existed to surface an expiring certificate as an action item. Contributing factor: The ISMS Manager and HR each assumed the other was monitoring certificate renewals. Neither had an explicit, documented responsibility. The 16-month gap exists because the documentation gap (no owner, no trigger) was never identified. | Immediate: Book AZ-500 renewal examination for Sana Al Farsi (target: 28 January 2027). Confirm booking date in writing to ISMS Manager. Systemic: Update ISMS-SUP-004 Tab 3 to add: a Renewal Owner column, a Renewal Action Due date (90 days before expiry), and a Renewal Status column. Assign explicit renewal ownership for every certificate. Add certificate expiry status to the monthly GRC status report (ISMS-SUP-007 I-04) so it is visible to the CISO every month. Add a 90-day-before-expiry calendar reminder to the ISMS Manager and Head of HR. | 1. AZ-500 renewal booking confirmation with examination date. 2. ISMS-SUP-004 Tab 3 updated with Renewal Owner, Action Due, and Status columns. 3. Calendar reminder mechanism documented and confirmed active. 4. Evidence of first monthly GRC report including certificate status section. | Priya Subramaniam (HR) + Sana Al Farsi
NCR-003 | Process adherence / Training gap | Root cause: The IT Operations Lead was aware of the standard change management process but did not know that an emergency change process exists (ISMS-OPS-010 Tab 2) that allows immediate action with verbal CISO approval, provided formal retrospective approval follows within 48 hours. The change management briefing at Phase 5 launch covered standard and normal changes but did not include a scenario-based walkthrough of the emergency track. The IT Operations Lead's instinct (urgent action was justified) was correct; the knowledge gap was the procedure for doing so within the framework. Contributing factor: ISMS-OPS-001 D-02.2 (cloud configuration security) did not cross-reference the emergency change process, so a cloud engineer facing an urgent configuration issue had no obvious pointer to the emergency track. | Step 1: Retrospective post-incident review of the 14 November security group change. Confirm the final configuration is baseline-compliant (vs OPS-001 D-02.1). Log the outcome as retrospective change record CHG-015 in ISMS-OPS-010. Close the Sentinel drift alert with a closure note referencing CHG-015. Step 2: Focused briefing for IT Operations on the emergency change process. Scenario-based: use the 14 November event as the worked example. Cover: what qualifies as emergency, verbal CISO approval before action, 48-hour formal approval window, COO fallback if CISO unreachable. Step 3: Update ISMS-OPS-001 D-02.2 to add a callout: "For urgent configuration changes: see ISMS-OPS-010 Tab 2 (Emergency Change Process) — verbal CISO approval required before action." | 1. CHG-015 retrospective change record in ISMS-OPS-010 (with baseline compliance note). 2. Sentinel drift alert closed with CHG-015 reference as closure reason. 3. IT Operations briefing attendance record (or written acknowledgement). 4. ISMS-OPS-001 D-02.2 updated with emergency change callout. 5. Audit 2: IT Operations Lead describes the emergency change process from memory (verbal CISO approval rule). | IT Operations Lead + CISO

## Effectiveness Review
ISMS-IMP-001 ¦ Effectiveness Review ¦ Post-closure verification — Clause 10.1(f)
Clause 10.1(f): review the effectiveness of corrective action taken. ¦ Effectiveness is assessed at the next audit or scheduled review after CA closure. ¦ A CA that fixed the symptom but not the root cause = "Partially effective" → new NCR raised. ¦ All effectiveness reviews are conducted by the audit lead or ISMS Manager — never by the CA owner.
NCR Ref | CA Closed Date | Effectiveness Verification Method | Verifier | Verification Date | Root Cause Addressed? | Recurrence Risk? | Effectiveness Verdict
NCR-001 | [Jan 2027] | Audit 2 (Feb 2027): audit lead independently retrieves the A5.8 evidence document from the GRC Repository cited path without assistance from the CISO or ISMS Manager. Confirms: (1) document exists at the path; (2) document content is relevant to A5.8 (security requirements in project management). Also: ISMS Manager demonstrates the updated OPS-002 completion verification step. | External audit lead (Audit 2 — Feb 2027) | [Feb 2027] | [Pending] | [Pending] | [Pending — Audit 2]
NCR-002 | [Jan 2027] | Audit 2 (Feb 2027): confirm AZ-500 renewal booking with examination date documented (or CISO-signed risk acceptance in GRC Repository). Confirm ISMS-SUP-004 Tab 3 has Renewal Owner, Action Due, and Status columns populated for all certificates. Confirm certificate status appears in the most recent monthly GRC report. | External audit lead (Audit 2 — Feb 2027) | [Feb 2027] | [Pending] | [Pending] | [Pending — Audit 2]
NCR-003 | [Jan 2027] | Audit 2 (Feb 2027): confirm CHG-015 is in ISMS-OPS-010 with baseline compliance note; Sentinel alert closed with CHG-015 reference; IT Operations briefing attendance record exists; ISMS-OPS-001 D-02.2 updated with emergency change callout. Knowledge check: ask IT Operations Lead to describe the emergency change process from memory (specifically the "verbal CISO approval before action" rule). | External audit lead (Audit 2 — Feb 2027) | [Feb 2027] | [Pending] | [Pending] | [Pending — Audit 2]
Clause 10.1 — Verdicts: "Effective" = root cause confirmed addressed, no recurrence risk. ¦ "Partially effective" = symptom fixed but root cause not fully addressed → new NCR raised. ¦ "Not effective" = nonconformity has recurred → major NCR raised, escalate to CISO. ¦ If an NCR recurs at a subsequent audit, the original CA is reclassified as "Not effective" and a stronger corrective action is required.