## Corrective Action Tracker
ISMS-IMP-004 ¦ Corrective Action Tracker ¦ ISO/IEC 27001:2022 Clause 10.1 ¦ Project HealthSec ¦ MediSync Technologies Pvt. Ltd.
Owner: Meera Iyer, ISMS Manager ¦ v1.0 ¦ January 2027 ¦ Consolidates all corrective actions from all NCRs across all sources. ¦ Updated weekly during active CA periods. ¦ Priority: HIGH = blocks Stage 1 / Stage 2 ¦ MEDIUM = must close before management review ¦ LOW = improvement, no deadline pressure ¦ Classification: Confidential — Internal Use Only
CA Ref | NCR Ref | CAR Ref | Source | Action Description | Owner | Priority | Date Opened | Target Date | Days Remaining | Completion Date | Verified By | Verification Date | Evidence In GRC? | Effectiveness Verdict | Status
NCR CORRECTIVE ACTIONS — CAR-001 (NCR-001: SoA evidence gap)
CA-001-1 | NCR-001 | CAR-001 | Internal Audit Dec 2026 | Step 1: Identify specific Phase 5 sprint planning or design review documents that constitute A5.8 evidence. Confirm these exist in GRC Repository or on record. | Vikram Sundaram (CISO) | HIGH | 5 Jan 2027 | 15 Jan 2027 | 10 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | In Progress
CA-001-2 | NCR-001 | CAR-001 | Internal Audit Dec 2026 | Step 2: Create named A5.8 Architecture Review Record covering security requirement decisions for top 3 security-relevant Phase 5 features. Store at specific, retrievable GRC Repository path. | Vikram Sundaram (CISO) | HIGH | 5 Jan 2027 | 15 Jan 2027 | 10 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | In Progress
CA-001-3 | NCR-001 | CAR-001 | Internal Audit Dec 2026 | Step 3: Update ISMS-OPS-002 A5.8 evidence location field to specific path and filename of the new Architecture Review Record. | Meera Iyer (ISMS Manager) | HIGH | 5 Jan 2027 | 20 Jan 2027 | 15 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | Not started
CA-001-4 | NCR-001 | CAR-001 | Internal Audit Dec 2026 | Step 4: ISMS Manager independently retrieves the A5.8 document from the cited GRC path without assistance from the CISO. Confirms accessibility to a third party. | Meera Iyer (ISMS Manager) | HIGH | 5 Jan 2027 | 20 Jan 2027 | 15 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | Not started
CA-001-SYS | NCR-001 | CAR-001 | Internal Audit Dec 2026 | Systemic improvement: Add "verify retrieval" step to ISMS-OPS-002 completion process. Document as guidance note in OPS-002 Tab 1 header so all future FI entries are independently verified before acceptance. | Meera Iyer (ISMS Manager) | HIGH | 5 Jan 2027 | 31 Jan 2027 | 26 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | Not started
NCR CORRECTIVE ACTIONS — CAR-002 (NCR-002: AZ-500 lapse)
CA-002-1 | NCR-002 | CAR-002 | Internal Audit Dec 2026 | Step 1: Book AZ-500 renewal examination for Sana Al Farsi. Target examination date on or before 28 January 2027. Provide written booking confirmation to ISMS Manager. | Priya Subramaniam (HR) + Sana Al Farsi | HIGH | 5 Jan 2027 | 20 Jan 2027 | 15 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | In Progress
CA-002-2 | NCR-002 | CAR-002 | Internal Audit Dec 2026 | Step 2: Update ISMS-SUP-004 Tab 3 Certificate Register — add Renewal Owner, Renewal Action Due (90 days before expiry), and Renewal Status columns. Backfill all existing entries. | Priya Subramaniam (HR) | HIGH | 5 Jan 2027 | 20 Jan 2027 | 15 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | In Progress
CA-002-3 | NCR-002 | CAR-002 | Internal Audit Dec 2026 | Step 3: Set up 90-day-before-expiry calendar reminders for ISMS Manager and Head of HR for every certificate in the register. Document the reminder mechanism. | Meera Iyer (ISMS Manager) | MEDIUM | 5 Jan 2027 | 25 Jan 2027 | 20 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | Not started
CA-002-4 | NCR-002 | CAR-002 | Internal Audit Dec 2026 | Step 4: Add "Certificate Renewal Status" as standing section to monthly GRC status report template (ISMS-SUP-007 I-04). Include: certificate name, holder, expiry date, renewal status, renewal owner. | Meera Iyer (ISMS Manager) | MEDIUM | 5 Jan 2027 | 31 Jan 2027 | 26 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | Not started
NCR CORRECTIVE ACTIONS — CAR-003 (NCR-003: unapproved change)
CA-003-1 | NCR-003 | CAR-003 | Internal Audit Dec 2026 | Step 1: Post-incident review of 14 November 2026 security group change. Confirm final configuration is baseline-compliant (vs OPS-001 D-02.1). Create retrospective change record CHG-015 in ISMS-OPS-010 Tab 1 — marked "Retrospective — post-incident review" with CISO approval note. | IT Operations Lead + CISO | HIGH | 5 Jan 2027 | 15 Jan 2027 | 10 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | In Progress
CA-003-2 | NCR-003 | CAR-003 | Internal Audit Dec 2026 | Step 2: Close Sentinel configuration drift alert in SOC alert log. Closure note must reference CHG-015 as the retrospective change record and confirm the configuration is baseline-compliant. | Neha Choudhury (SOC Manager) | HIGH | 5 Jan 2027 | 15 Jan 2027 | 10 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | Not started
CA-003-3 | NCR-003 | CAR-003 | Internal Audit Dec 2026 | Step 3: Conduct focused briefing for IT Operations team on the emergency change process (ISMS-OPS-010 Tab 2). Use the 14 November event as the worked example. Cover: what qualifies as emergency, verbal CISO approval before action, 48-hour formal approval window, COO fallback. Record attendance. | Vikram Sundaram (CISO) | HIGH | 5 Jan 2027 | 15 Jan 2027 | 10 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | Not started
CA-003-4 | NCR-003 | CAR-003 | Internal Audit Dec 2026 | Step 4: Update ISMS-OPS-001 D-02.2 to add callout: "Urgent configuration change needed? See ISMS-OPS-010 Tab 2 (Emergency Change Process). Verbal CISO approval required before action. Do not make the change first and seek approval after." | Meera Iyer (ISMS Manager) | MEDIUM | 5 Jan 2027 | 20 Jan 2027 | 15 | [Pending] | [Audit lead] | [Feb 2027] | No — pending | [Pending Audit 2] | Not started
MANAGEMENT REVIEW ACTIONS (PEV-008 — December 2026 management review)
CA-MR-01 | OBS-003 | — (Mgmt Review) | Management Review Dec 2026 | Issue MedLink Gulf Tier 1 assessment report formally. Update ISMS-OPS-004 Supplier Register with completed assessment status, score, and security schedule status. | Meera Iyer (ISMS Manager) | HIGH | 22 Dec 2026 | 10 Jan 2027 | 5 | [Pending] | Meera Iyer (self-verify) | [Jan 2027] | No — pending | N/A — not an NCR | In Progress
CA-MR-02 | — | — (Mgmt Review) | Management Review Dec 2026 | Complete Tier 2 vendor assessments (PulseMail, PayBridge, TrustID). Update ISMS-OPS-004 Supplier Register. | Meera Iyer (ISMS Manager) | HIGH | 22 Dec 2026 | 31 Jan 2027 | 26 | [Pending] | Meera Iyer (self-verify) | [Jan 2027] | No — pending | N/A — not an NCR | In Progress
CA-MR-03 | — | — (Mgmt Review) | Management Review Dec 2026 | Submit Stage 1 certification body application. | Meera Iyer (ISMS Manager) | HIGH | 22 Dec 2026 | 15 Jan 2027 | 10 | [Pending] | Meera Iyer (self-verify) | [Jan 2027] | N/A | N/A — programme action | In Progress
CA-MR-04 | — | — (Mgmt Review) | Management Review Dec 2026 | Confirm certification body fees budget approval. | Rajesh Menon (CFO) | HIGH | 22 Dec 2026 | 15 Jan 2027 | 10 | [Pending] | ISMS Manager (confirmation) | [Jan 2027] | N/A | N/A — programme action | Not started
CA-MR-05 | — | — (Mgmt Review) | Management Review Dec 2026 | Appoint Head of Procurement and nominate 8th Security Champion. | Farhan Ahmed (COO) | HIGH | 22 Dec 2026 | 28 Feb 2027 | 54 | [Pending] | ISMS Manager (confirmation) | [Feb 2027] | N/A | N/A — programme action | In Progress
TOTALS (January 2027): Total actions: 18 ¦ NCR corrective actions: 13 (CAR-001: 5, CAR-002: 4, CAR-003: 4) ¦ Management review actions: 5 ¦ In Progress: 6 ¦ Not started: 8 ¦ Complete: 0 ¦ All NCR actions target: 31 January 2027 ¦ Verification: Audit 2 (February 2027)

## Status Dashboard
ISMS-IMP-004 ¦ Action Status Dashboard ¦ Management summary view — updated weekly
This tab is the summary view for the monthly GRC status report (ISMS-SUP-007 I-04) and Steering Committee pack. ¦ RAG: GREEN = on track ¦ AMBER = at risk (fewer than 7 days to target) ¦ RED = overdue
Action Group / Owner | Total Actions | Not Started | In Progress | Complete | Overdue | RAG Status
CAR-001 (NCR-001 SoA evidence) | 5 | 3 | 2 | 0 | 0 | GREEN — on track
CAR-002 (NCR-002 AZ-500 lapse) | 4 | 2 | 2 | 0 | 0 | GREEN — on track
CAR-003 (NCR-003 unapproved change) | 4 | 3 | 1 | 0 | 0 | AMBER — 3 steps not yet started; 10-day window
Management Review actions (Dec 2026) | 5 | 1 | 4 | 0 | 0 | AMBER — CA-MR-01 due 10 Jan; 5 days
TOTAL | 18 | 9 | 9 | 0 | 0 | AMBER — 9 actions not yet started; all by 31 Jan 2027
KEY DATES: CA-MR-01 (MedLink Gulf report): 10 Jan 2027 ¦ CA-MR-03 (Stage 1 application): 15 Jan 2027 ¦ CA-MR-04 (CB fees budget): 15 Jan 2027 ¦ All NCR CAs: 31 Jan 2027 ¦ Audit 2 (CA closure verification): 10–12 Feb 2027 ¦ Stage 1 target: February 2027
OWNER ACCOUNTABILITY — who owns what
Owner | Actions Owned | Count | Priority | Earliest Target | Description | Status
Vikram Sundaram (CISO) | CA-001-1, CA-001-2, CA-003-3 | 3 actions | HIGH all | 15 Jan 2027 | A5.8 architecture evidence (2 steps) + IT Operations emergency change briefing | AMBER
Meera Iyer (ISMS Manager) | CA-001-3, CA-001-4, CA-001-SYS, CA-002-3, CA-002-4, CA-003-4, CA-MR-01, CA-MR-02, CA-MR-03 | 9 actions | Mix HIGH/MED | 10 Jan – 31 Jan 2027 | Highest action load — ISMS Manager is the critical path | AMBER
Priya Subramaniam (HR) + Sana Al Farsi | CA-002-1, CA-002-2 | 2 actions | HIGH | 20 Jan 2027 | AZ-500 booking + Certificate Register restructure | GREEN
IT Operations Lead + CISO | CA-003-1 | 1 action | HIGH | 15 Jan 2027 | Retrospective CHG-015 change record + baseline review | In Progress
Neha Choudhury (SOC Manager) | CA-003-2 | 1 action | HIGH | 15 Jan 2027 | Close Sentinel alert with CHG-015 reference | Not started
Rajesh Menon (CFO) | CA-MR-04 | 1 action | HIGH | 15 Jan 2027 | Certification body fees budget approval | Not started
Farhan Ahmed (COO) | CA-MR-05 | 1 action | HIGH | 28 Feb 2027 | Head of Procurement appointment + 8th Security Champion nomination | In Progress

## Continual Improvement Log
ISMS-IMP-004 ¦ Continual Improvement Log ¦ ISO/IEC 27001:2022 Clause 10.2 — Continual Improvement
Improvements beyond NCR correction — these are proactive enhancements to the ISMS that are not driven by a nonconformity. ¦ Sources: Internal audit observations ¦ Management review decisions ¦ Self-identified ¦ RCA pattern observations ¦ This log feeds the annual management review (ISMS-PEV-008) as evidence of continual improvement.
Improvement Ref | Source | Improvement Description | Action / Change Required | Owner | Target Date | Completed Date | Status
CI-001 | RCA pattern observation (ISMS-IMP-003 Pattern 1) | Process design assumed human action without verification mechanisms — all three Dec 2026 NCRs share this root cause pattern. | Apply "verification checkpoint" design principle to all future ISMS process design: any process that relies on a person taking undirected action must also have a trigger mechanism or verification step. Document as a design principle in the ISMS management framework (Phase 9 Stage 2 prep). | Meera Iyer (ISMS Manager) | Mar 2027 | [Pending] | Planned
CI-002 | RCA pattern observation (ISMS-IMP-003 Pattern 2) | Phase 5 delivery pace created latent documentation completeness gaps — two NCRs trace to documentation completed without a closing verification pass. | Add a "last mile verification pass" step to the Phase 9 (Stage 2 preparation) workplan — targeted check of documentation assumptions: every FI entry retrievable, every cross-reference tested, every procedure briefed to the right audience. | Meera Iyer (ISMS Manager) | Jan 2027 | [Pending] | In Progress
CI-003 | Management Review (ISMS-PEV-008 D-11) | Cross-region failover capability for India not built — FS-3 (complete regional cloud outage) has no automated recovery path. | Architecture assessment for India cross-region failover (e.g., warm standby in ap-south-2 Hyderabad). Cost estimate to Steering Committee for approval. Not required for certification — post-certification improvement. | Ridhima Kapoor (CTO) | Q2 2027 | [Pending] | Planned — post-cert
CI-004 | Management Review (ISMS-PEV-008 D-11) | Security questionnaire response time currently 7–10 business days against a post-certification target of ≤5 days. | Build pre-approved questionnaire response library — templated answers to the 20 most common security questionnaire questions, ISMS Manager-approved, ready for rapid customisation and dispatch by Head of Sales. | Meera Iyer (ISMS Manager) | Apr 2027 | [Pending] | In Progress
CI-005 | Management Review (ISMS-PEV-008 D-11) | Year 1 awareness programme module to be refreshed before the July 2027 annual cycle, incorporating incident history and phishing simulation results. | Review Year 1 awareness module content. Incorporate: lessons learned from 2024 near-misses, Oct 2026 tabletop findings, and Feb 2027 phishing simulation results. Update platform content and re-issue to all ~430 staff. | Priya Subramaniam (Head of HR) | Jun 2027 | [Pending] | Planned
CI-006 | Internal Audit Observation (ISMS-PEV-005 OBS-001) | ISMS Manager holds interim Procurement ownership since Month 4 (11 months) — creates single-person-dependency and may affect perceived independence of supplier decisions. | Fill Head of Procurement position. On appointment, transfer procurement-related ISMS ownership formally. Nominate 8th Security Champion from Procurement department. | Farhan Ahmed (COO) | Feb 2027 | [Pending] | In Progress
CI-007 | Internal Audit Observation (ISMS-PEV-005 OBS-003) | MedLink Gulf Tier 1 assessment fieldwork complete but formal report not issued — administrative gap identified at audit. | Issue formal MedLink Gulf assessment report. Update ISMS-OPS-004 Supplier Register. Implement a formal "assessment closure checklist" for all future Tier 1 assessments to prevent the same gap — report issuance should be a mandatory step before any assessment is marked complete. | Meera Iyer (ISMS Manager) | 10 Jan 2027 | [Pending] | In Progress
CI-008 | DR Test finding (ISMS-OPS-008 Appendix A) | Enterprise customer VPC certificate renewal was manual — caused 2-minute RTO overrun at DR test. | Automate certificate renewal using cert-manager for all enterprise customer VPC/VNet namespaces. Remove manual step from DR runbook (RB-006). | Sana Al Farsi (Head of Cloud Infra) | Oct 2026 | Oct 2026 | Complete