## Effectiveness Register
ISMS-IMP-005 ¦ Effectiveness Verification Records ¦ ISO/IEC 27001:2022 Clause 10.1(f) ¦ Project HealthSec ¦ MediSync Technologies Pvt. Ltd.
Owner: Meera Iyer, ISMS Manager ¦ v1.0 ¦ February 2027 (updated post-Audit 2) ¦ Clause 10.1(f): review the effectiveness of corrective action taken. ¦ Verdicts: Effective ¦ Partially effective (new NCR raised) ¦ Not effective (major NCR raised) ¦ Pending ¦ All verifications conducted by external audit lead at Audit 2 — never by the CA owner. ¦ Classification: Confidential — Internal Use Only
CA Ref | NCR Ref | CAR Ref | Corrective Action (brief) | CA Completed Date | Verified By | Verification Date | Verification Method | Evidence Reviewed | Root Cause Addressed? | Recurrence Risk? | NCR Status Post-Verification | NCR Updated in IMP-001? | Effectiveness Verdict
NCR CORRECTIVE ACTION EFFECTIVENESS — ALL PENDING AUDIT 2 (10–12 February 2027) ¦ Verifier: External audit lead
CA-001 (all steps) | NCR-001 | CAR-001 | Create A5.8 Architecture Review Record at specific GRC path; update OPS-002 evidence location; add retrieval verification step to OPS-002 completion process. | [Jan 2027] | External audit lead (Audit 2 — Feb 2027) | [Feb 2027] | Document retrieval test + OPS-002 inspection + knowledge check | 1. Navigate to GRC Repository path cited in OPS-002 for A5.8 — retrieve document without assistance. 2. Confirm document content is relevant to A5.8 (security requirements in project management). 3. Confirm OPS-002 A5.8 entry shows specific path and filename. 4. Confirm OPS-002 Tab 1 header includes retrieval verification guidance note. 5. Ask ISMS Manager: demonstrate the OPS-002 completion verification step. | [Audit 2] | [Audit 2] | [Pending — Audit 2] | [Pending] | Pending — Audit 2 (Feb 2027)
CA-002 (all steps) | NCR-002 | CAR-002 | AZ-500 renewal booking confirmed; SUP-004 Tab 3 restructured with Renewal Owner / Action Due / Status columns; 90-day calendar reminders active; certificate status in monthly GRC report. | [Jan 2027] | External audit lead (Audit 2 — Feb 2027) | [Feb 2027] | Certificate Register review + GRC report review + process knowledge check | 1. Review ISMS-SUP-004 Tab 3 — confirm Renewal Owner, Action Due, and Renewal Status columns are populated for all entries. 2. Confirm AZ-500 renewal booking documentation exists in GRC Repository (booking confirmation with examination date). 3. Review most recent monthly GRC status report — confirm "Certificate Renewal Status" section is present. 4. Ask Head of HR: describe the process if a certificate expires within 90 days — confirm awareness of the calendar trigger and the GRC report escalation mechanism. 5. Confirm the calendar reminder mechanism is documented. | [Audit 2] | [Audit 2] | [Pending — Audit 2] | [Pending] | Pending — Audit 2 (Feb 2027)
CA-003 (all steps) | NCR-003 | CAR-003 | CHG-015 retrospective change record created; Sentinel alert closed; IT Operations emergency change briefing conducted; OPS-001 D-02.2 callout added. | [Jan 2027] | External audit lead (Audit 2 — Feb 2027) | [Feb 2027] | Document review + Sentinel log check + knowledge check (IT Ops Lead) | 1. Open ISMS-OPS-010 Tab 1 — confirm CHG-015 retrospective change record exists with: configuration details, baseline compliance note, CISO retrospective approval. 2. Check Sentinel alert log — confirm the 14 November 2026 drift alert is closed with CHG-015 referenced as the closure reason. 3. Review IT Operations emergency change briefing attendance record (or written acknowledgements). 4. Open ISMS-OPS-001 D-02.2 — confirm the emergency change callout box is present and legible. 5. Knowledge check: ask IT Operations Lead to describe when and how verbal CISO approval is obtained for an emergency change — specifically confirm they understand "before action, not after." | [Audit 2] | [Audit 2] | [Pending — Audit 2] | [Pending] | Pending — Audit 2 (Feb 2027)
EFFECTIVENESS VERDICT DEFINITIONS: "Effective" = root cause confirmed addressed; nonconformity cannot recur under the same conditions; NCR status updated to Closed — Verified in ISMS-IMP-001. ¦ "Partially effective" = symptom fixed but root cause not fully addressed; new minor NCR raised; additional corrective action required. ¦ "Not effective" = same nonconformity recurred; major NCR raised; escalate to CISO and Steering Committee. ¦ RULE: A corrective action verified as effective by the CA owner is not independently verified. Only the audit lead or ISMS Manager may issue a verdict.

## Audit 2 Verification
ISMS-IMP-005 ¦ Audit 2 Verification Record ¦ 10–12 February 2027 ¦ Pre-Stage 2 targeted audit — CA closure confirmation
This tab is completed by the audit lead during Audit 2 fieldwork (10–12 February 2027). ¦ Audit 2 purpose: (1) confirm all NCR-001, NCR-002, NCR-003 corrective actions are complete; (2) verify evidence is in place; (3) issue effectiveness verdicts; (4) conduct pre-Stage 2 evidence completeness review. ¦ Pre-populated with the verification criteria from ISMS-IMP-002 (CAR forms). Audit lead completes the "Audit Lead Finding" and "Verdict" columns during fieldwork.
NCR Ref | Verification Criterion (from CAR form) | Specific Evidence Check | Audit Lead Finding (completed at Audit 2) | Criterion Met? | Verdict
NCR-001 — SoA evidence gap (CAR-001) ¦ 4 verification criteria
NCR-001 | Evidence retrieval — A5.8 document accessible | Navigate to the exact GRC Repository path cited in ISMS-OPS-002 for A5.8. Retrieve the document without assistance from the CISO or ISMS Manager. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-001 | Evidence content — A5.8 document relevant | Review the retrieved document. Confirm it addresses security requirements in project management context — specifically, that it documents security considerations assessed for Phase 5 feature developments. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-001 | OPS-002 updated — specific path and filename | Open ISMS-OPS-002. Navigate to A5.8 entry. Confirm evidence location field shows the full specific path including filename (not a generic folder path). | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-001 | OPS-002 completion process — retrieval verification step added | Review ISMS-OPS-002 Tab 1 header guidance. Confirm a "verify retrieval" instruction is present stating that FI entries must be independently retrievable before acceptance. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-002 — AZ-500 lapse (CAR-002) ¦ 5 verification criteria (1 knowledge check)
NCR-002 | AZ-500 renewal — booking confirmed with examination date | Review AZ-500 renewal booking confirmation document in GRC Repository. Confirm it names an examination date on or before 28 January 2027 (or confirm CISO-signed risk acceptance if booking was not possible). | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-002 | SUP-004 Tab 3 restructured — Renewal Owner column | Open ISMS-SUP-004 Tab 3. Confirm "Renewal Owner" column exists and is populated with a named individual for every certificate entry. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-002 | SUP-004 Tab 3 restructured — Renewal Action Due column | Confirm "Renewal Action Due" column exists and is populated with a date 90 days before expiry for every certificate. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-002 | Certificate status in monthly GRC report | Review the most recent monthly GRC status report (ISMS-SUP-007 I-04). Confirm a "Certificate Renewal Status" section is present with certificate details, holder, expiry, status, and owner. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-002 | Knowledge check — Head of HR describes renewal trigger process | Ask Head of HR (without reference to documents): if a certificate expires in 90 days, what happens? Expected answer: 90-day calendar reminder triggers action; renewal owner initiates renewal; status appears in monthly GRC report for CISO visibility. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No [ ] Partial | [Pending]
NCR-003 — Unapproved change (CAR-003) ¦ 5 verification criteria (1 knowledge check)
NCR-003 | CHG-015 retrospective change record in OPS-010 | Open ISMS-OPS-010 Tab 1. Confirm CHG-015 entry exists and includes: (1) description of the 14 November security group change, (2) baseline compliance confirmation note, (3) CISO retrospective approval reference, (4) "Retrospective" label. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-003 | Sentinel alert closed with CHG-015 reference | Check SOC Sentinel alert log for the 14 November 2026 drift alert. Confirm status is Closed and closure note references CHG-015. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-003 | IT Operations emergency change briefing — attendance recorded | Review briefing attendance record (or written acknowledgements from IT Operations team members). Confirm record exists and covers the emergency change topic. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-003 | OPS-001 D-02.2 callout added — emergency change cross-reference | Open ISMS-OPS-001. Navigate to D-02.2 (cloud configuration security). Confirm a callout or highlighted note is present directing engineers to ISMS-OPS-010 Tab 2 for urgent changes, with the "verbal CISO approval before action" rule stated. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No | [Pending]
NCR-003 | Knowledge check — IT Operations Lead describes emergency change process | Ask IT Operations Lead (without reference to documents): if you urgently need to modify a production security group during a connectivity incident, what do you do? Expected answer: contact CISO for verbal approval before making the change, then log in OPS-010 Tab 2 emergency track, formal approval within 48 hours. | [Audit lead finding — Feb 2027] | [ ] Yes [ ] No [ ] Partial | [Pending]
AUDIT 2 OVERALL NCR CLOSURE CONCLUSION — To be completed by audit lead at close of Audit 2 fieldwork
NCR Ref | All criteria met? | Effectiveness verdict | NCR status post-Audit 2 | Audit lead signature | Date
NCR-001 | [ ] Yes [ ] No [ ] Partial | [ ] Effective [ ] Partially effective [ ] Not effective | [Closed — Verified / Partially closed / Remains open] | ______________________________ | [Feb 2027]
NCR-002 | [ ] Yes [ ] No [ ] Partial | [ ] Effective [ ] Partially effective [ ] Not effective | [Closed — Verified / Partially closed / Remains open] | ______________________________ | [Feb 2027]
NCR-003 | [ ] Yes [ ] No [ ] Partial | [ ] Effective [ ] Partially effective [ ] Not effective | [Closed — Verified / Partially closed / Remains open] | ______________________________ | [Feb 2027]

## Verification Criteria
ISMS-IMP-005 ¦ Verification Criteria Reference ¦ What "effective" means for each corrective action
This tab defines the effectiveness criteria for each NCR — what the audit lead must confirm to issue an "Effective" verdict. ¦ Criteria are derived from ISMS-IMP-002 (CAR forms) Section 6 (Evidence Required for Closure) and Section 7 (Effectiveness Review). ¦ A corrective action that meets all evidence criteria but fails a knowledge check may still receive a "Partially effective" verdict.
NCR Ref | CAR Ref | Root Cause (brief) | Evidence Criterion | Effectiveness Test | Minimum Standard for "Effective" Verdict
NCR-001 | CAR-001 | OPS-002 completion process had no retrieval verification step — allowed FI entries with non-retrievable evidence. | A5.8 Architecture Review Record: named document at specific GRC path, content relevant to A5.8 scope. | Audit lead retrieves document without assistance, from the exact path cited in OPS-002. | Document retrieved independently AND content addresses security requirements in project management. If either fails: Partially effective.
NCR-001 | CAR-001 | (systemic improvement) | OPS-002 completion guidance: retrieval verification step documented in Tab 1 header. | Audit lead reads OPS-002 Tab 1 header and finds the verification instruction. | Instruction is present and unambiguous. If missing: CA for systemic improvement is not complete — Partially effective.
NCR-002 | CAR-002 | Certificate Register had no renewal ownership, trigger mechanism, or governance visibility — no one owned the AZ-500 renewal action. | AZ-500 renewal: booking confirmation with examination date on or before 28 January 2027 (or CISO risk acceptance). | Document exists in GRC Repository with examination date confirmed. | Booking confirmation (or risk acceptance) present in GRC Repository with a specific date. If examination date is after 28 January 2027 without CISO risk acceptance: Partially effective.
NCR-002 | CAR-002 | (systemic — governance) | SUP-004 Tab 3 restructured: Renewal Owner, Action Due, Status columns populated for all entries. | Audit lead opens SUP-004 Tab 3 and inspects all columns for all rows. | All three new columns present and populated for every certificate entry. If any entry is blank: Partially effective.
NCR-002 | CAR-002 | (systemic — monitoring) | Certificate status section in monthly GRC report. | Audit lead reviews most recent GRC report for certificate status section. | Section present with all required fields. If absent: root cause (no governance visibility) not addressed — Partially effective.
NCR-002 | CAR-002 | (systemic — knowledge) | Head of HR can describe the renewal trigger process without reference to documents. | Knowledge check: audit lead asks HR to describe the process if a certificate nears expiry. | HR describes 90-day trigger, renewal owner action, and GRC report escalation correctly. If HR cannot describe without document reference: knowledge gap persists — Partially effective.
NCR-003 | CAR-003 | Emergency change process not known to IT Operations — not covered in change management briefing and not cross-referenced at point of need. | CHG-015 retrospective change record in OPS-010 with baseline compliance note and CISO approval. | Audit lead opens OPS-010 Tab 1, finds CHG-015, reads notes. | CHG-015 present with all required fields (configuration details, baseline compliance note, CISO approval, "Retrospective" label). If any field missing: Partially effective.
NCR-003 | CAR-003 | (documentation — cross-reference) | OPS-001 D-02.2 callout directing engineers to emergency change process with "before action, not after" rule. | Audit lead navigates to OPS-001 D-02.2 and reads the callout. | Callout is present, references OPS-010 Tab 2 by name, and states the "verbal CISO approval before action" rule explicitly. If callout is absent or does not mention timing: root cause (discoverability) not addressed — Partially effective.
NCR-003 | CAR-003 | (knowledge — critical test) | IT Operations Lead can describe the emergency change process — specifically "verbal CISO approval before action" — without reference to OPS-010. | Knowledge check: audit lead asks IT Operations Lead to describe the process for urgent configuration changes. | IT Operations Lead correctly states: (1) contact CISO for verbal approval, (2) approval before action, (3) log in OPS-010 Tab 2 emergency track, (4) formal approval within 48 hours. If they cannot state "before action, not after": root cause (knowledge gap) not addressed — Partially effective.