## Improvement Log
ISMS-IMP-006 ¦ Continual Improvement Log ¦ ISO/IEC 27001:2022 Clause 10.2 ¦ Project HealthSec ¦ MediSync Technologies Pvt. Ltd.
Owner: Meera Iyer, ISMS Manager ¦ v1.0 ¦ January 2027 ¦ Records all proactive ISMS improvements — not driven by a nonconformity (those are in ISMS-IMP-001). ¦ Sources: Internal Audit observations ¦ Management Review decisions ¦ RCA pattern observations ¦ Operational experience ¦ External intelligence ¦ Updated at each monthly GRC report and at each management review. ¦ Classification: Confidential — Internal Use Only
CI Ref | Source Category | Source Document | Improvement Description | Action / Change Required | Owner | Priority | Date Identified | Target Date | Completed Date | ISMS Documents Affected | Management Review Note | Presented at MR? | Status
PHASE 5 — OPERATIONAL IMPROVEMENTS (October 2026) ¦ Source: DR test, tabletop, vendor assessments
CI-001 | Operational experience | ISMS-OPS-008 Appendix A (DR test) | Enterprise customer VPC certificate renewal was a manual step — caused a 2-minute RTO overrun at the October 2026 DR test. | Automate TLS certificate renewal using cert-manager for all 6 enterprise customer VPC/VNet namespaces. Remove manual renewal step from DR runbook (ISMS-OPS-008 RB-006). | Sana Al Farsi (Head of Cloud Infra) | LOW | Oct 2026 | Oct 2026 | Oct 2026 | ISMS-OPS-007 Section 9; ISMS-OPS-008 RB-006 | Completed pre-MR; reported at Dec 2026 management review as evidence of operational improvement. | Yes — Dec 2026 MR | Complete
CI-002 | Operational experience | ISMS-OPS-005 Tabletop exercise (INC-003) | October 2026 tabletop exercise revealed 5 procedure gaps in the IR procedure — including the CERT-In clock trigger delay and DPDP Act ownership confusion. | Incorporate all 5 tabletop findings into ISMS-OPS-005 v1.0. Issue updated procedure before it is needed in a real incident. | Neha Choudhury (SOC Manager) | HIGH | Oct 2026 | Oct 2026 | Oct 2026 | ISMS-OPS-005 (Sections 5, 7, 11) | Completed pre-MR; tabletop findings documented in ISMS-OPS-005 Section 12; procedure updated before Stage 1. | Yes — Dec 2026 MR | Complete
CI-003 | Operational experience | ISMS-OPS-003 VaultArchive assessment | VaultArchive assessment identified that their internal DR test was 14 months overdue and their monitoring tool sub-processor assessment was 18 months old. | Track VaultArchive remediation commitments in security schedule. Confirm VaultArchive DR test by December 2026. Confirm sub-processor reassessment by March 2027. | Meera Iyer (ISMS Manager) | MEDIUM | Oct 2026 | Mar 2027 | [Pending] | ISMS-OPS-003; ISMS-OPS-004 | VaultArchive DR test commitment due Dec 2026. Sub-processor reassessment due Mar 2027. Both tracked as security schedule conditions. | Yes — Dec 2026 MR | In Progress
CI-004 | Operational experience | ISMS-OPS-003 SentinelWatch assessment | SentinelWatch assessment identified that their BCDR has not been tested for 18 months — security schedule condition requires test by March 2027. | Track SentinelWatch BCDR test completion as a security schedule condition. Report at next Steering Committee if condition not met by March 2027. Log as KPI-028. | Meera Iyer (ISMS Manager) | MEDIUM | Oct 2026 | Mar 2027 | [Pending] | ISMS-OPS-003; ISMS-OPS-004; ISMS-PEV-001 (KPI-028) | R-021 (SentinelWatch BCDR) added to risk register. KPI-028 monitors this condition. Due March 2027. | Yes — Dec 2026 MR | In Progress
PHASE 6 — AUDIT AND MANAGEMENT REVIEW IMPROVEMENTS (December 2026) ¦ Source: Internal audit observations + management review decisions
CI-005 | Internal Audit obs. | ISMS-PEV-005 (OBS-001) | Head of Procurement vacancy 11 months — ISMS Manager holds interim ownership, creating single-person-dependency risk and affecting perceived independence of supplier decisions. | Fill Head of Procurement position. Transfer procurement-related ISMS ownership formally on appointment. Nominate 8th Security Champion from Procurement. | Farhan Ahmed (COO) | HIGH | Dec 2026 | Feb 2027 | [Pending] | ISMS-SUP-001; ISMS-OPS-004; ISMS-LDR-005 | Noted as OBS-001 at audit. COO confirmed appointment in progress at Dec 2026 management review. Target: February 2027. | Yes — Dec 2026 MR | In Progress
CI-006 | Internal Audit obs. | ISMS-PEV-005 (OBS-003) | MedLink Gulf Tier 1 assessment fieldwork complete but formal report not issued — administrative gap found at audit. | Issue MedLink Gulf assessment report. Update ISMS-OPS-004. Implement an "assessment closure checklist" for all future Tier 1 assessments so report issuance is a mandatory step. | Meera Iyer (ISMS Manager) | HIGH | Dec 2026 | 10 Jan 2027 | [Pending] | ISMS-OPS-003; ISMS-OPS-004 | OBS-003 at audit. Management response committed at Dec 2026 MR: report issued by 10 January 2027. | Yes — Dec 2026 MR | In Progress
CI-007 | Management Review | ISMS-PEV-008 (D-11) | Security questionnaire response time currently 7–10 business days — against a post-certification target of ≤5 business days (OO-08). | Build a pre-approved questionnaire response library: templated answers to the 20 most common security questionnaire questions, ISMS Manager-approved, ready for customisation and rapid dispatch by Head of Sales. | Meera Iyer (ISMS Manager) | MEDIUM | Dec 2026 | Apr 2027 | [Pending] | ISMS-LDR-002 (OO-08); ISMS-SUP-007 | Approved at Dec 2026 management review (D-11). Pre-certification: best-effort. Post-certification target: ≤5 days using the response library. | Yes — Dec 2026 MR | In Progress
CI-008 | Management Review | ISMS-PEV-008 (D-11) | Year 1 security awareness programme module should be refreshed before the July 2027 annual cycle — incorporating 2024 incident lessons, October 2026 tabletop findings, and February 2027 phishing simulation results. | Review Year 1 module content. Update to incorporate: lessons learned from near-misses, tabletop findings, and phishing simulation results. Reissue via awareness platform to all ~430 staff before July 2027. | Priya Subramaniam (Head of HR) | MEDIUM | Dec 2026 | Jun 2027 | [Pending] | ISMS-SUP-005; ISMS-SUP-004 | Approved at Dec 2026 management review (D-11). Refresh to incorporate lessons from the first full programme year and phishing simulation results (available after Feb 2027). | Yes — Dec 2026 MR | Planned
CI-009 | Management Review | ISMS-PEV-008 (D-11) | Cross-region failover capability for India not built — a complete AWS ap-south-1 regional outage cannot be mitigated within the 4-hour Tier 1 RTO. | Architecture assessment for India cross-region warm standby (e.g., ap-south-2 Hyderabad). Produce cost estimate and business case for Steering Committee approval. Not required for certification — post-certification roadmap item. | Ridhima Kapoor (CTO) | LOW | Dec 2026 | Q2 2027 | [Pending] | ISMS-OPS-007 (Section 9) | Noted as post-certification improvement at Dec 2026 MR (D-11). Architecture assessment by Q2 2027; budget approval required before build. | Yes — Dec 2026 MR | Planned — post-cert
PHASE 7 — RCA PATTERN IMPROVEMENTS (January 2027) ¦ Source: ISMS-IMP-003 programme pattern observations
CI-010 | RCA pattern observation | ISMS-IMP-003 (Pattern 1) | All three Dec 2026 NCRs share the root cause pattern: process design assumed human action without a verification or trigger mechanism — no checkpoint to confirm the action was taken. | Apply "verification checkpoint" design principle to all future ISMS process development: any process relying on undirected human action must include a trigger mechanism or verification step. Document as a design principle in the ISMS management framework during Phase 9 Stage 2 preparation. | Meera Iyer (ISMS Manager) | MEDIUM | Jan 2027 | Mar 2027 | [Pending] | ISMS programme framework (Phase 9 prep) | Derived from RCA of all three Dec 2026 NCRs. Design principle to be embedded in Stage 2 preparation methodology — prevents recurrence of the same governance pattern. | No — identified post-MR; for next Steering Committee | Planned
CI-011 | RCA pattern observation | ISMS-IMP-003 (Pattern 2) | Phase 5 delivery pace created latent documentation completeness gaps — two NCRs trace to documentation completed without a closing verification pass. | Add a targeted "last mile verification pass" to the Phase 9 (Stage 2 preparation) workplan. Scope: all FI entries retrievable, all cross-references tested, all procedures briefed to the correct audience. | Meera Iyer (ISMS Manager) | HIGH | Jan 2027 | Jan 2027 | [Pending] | Phase 9 workplan; ISMS-OPS-002 | Direct response to NCR-001 and NCR-003 pattern. Phase 9 workplan updated to include this pass before Stage 2 fieldwork begins. | No — identified post-MR; for next Steering Committee | In Progress
CI-012 | RCA pattern observation | ISMS-IMP-003 (Pattern 3) | Detection system worked for NCR-003 (Sentinel caught the unapproved change via KPI-023). The corrective action should focus on improving prevention, not augmenting already-effective monitoring. | Confirm corrective action for NCR-003 (CAR-003) correctly targets prevention: the OPS-001 D-02.2 callout and the IT Operations briefing. Review KPI-023 threshold settings to confirm the monitoring remains fit for purpose as the change rate scales post-certification. | Neha Choudhury (SOC Manager) | LOW | Jan 2027 | Mar 2027 | [Pending] | ISMS-OPS-001 (D-02.2); ISMS-PEV-001 (KPI-023) | Confirms the monitoring system is working. Prevention-layer improvements (CAR-003 steps 3–4) are the corrective actions. KPI-023 review in Q1 2027. | No — identified post-MR; for next Steering Committee | Planned
FUTURE / ONGOING IMPROVEMENTS ¦ Source: Operational experience + external intelligence
CI-013 | Operational experience | ISMS-OPS-007 (Section 5.3) | UAE region DR test has not yet been conducted — only India region was tested in October 2026. Azure UAE North recovery capability is unverified. | Schedule UAE region DR test as the primary scenario for the 2027 annual DR test. Test: Azure Immutable Blob restore from VaultArchive UAE archives. Confirm Azure PITR recovery time against the Tier 1 RTO (4 hours). | Sana Al Farsi (Head of Cloud Infra) | MEDIUM | Jan 2027 | Oct 2027 | [Pending] | ISMS-OPS-007; ISMS-OPS-008 | Noted in ISMS-OPS-007 Section 9. India DR test confirmed all RTOs. UAE test to follow in 2027 annual cycle. | No — planned for 2027 annual management review | Planned — 2027
CI-014 | External intelligence | ISMS-INI-010 (Legal Register) | DPDP Act 2023 implementation rules not yet finalised by the Government of India — the regulatory landscape remains uncertain, with implications for MediSync's Data Processor obligations. | Monitor MeitY DPDP Act rule notifications. Review Legal Register (ISMS-INI-010) whenever new rules are notified. Brief CISO and Head of Legal within 5 business days of any new rule. Update OPS-005 Track 2 if notification obligations change. | Omar Al Mansoori (Head of Legal) | HIGH | Jan 2027 | Ongoing | [Ongoing] | ISMS-INI-010; ISMS-OPS-005 (Track 2) | Ongoing monitoring item. No specific improvement action triggered yet — rules not finalised. Will become a documented improvement when rules are notified and MediSync's obligations are confirmed. | Yes — Dec 2026 MR (D-09) | In Progress — ongoing
CI-015 | External intelligence | ISMS-INI-010 (Legal Register) | UAE PDPL regulatory infrastructure continues to mature — the Data Protection Office notification portal and guidance may be updated, affecting MediSync's Track 3 notification procedure. | Monitor UAE DPO publications and update ISMS-OPS-005 Track 3 if the notification channel or process changes. Review at each quarterly legal update. | Omar Al Mansoori (Head of Legal) | MEDIUM | Jan 2027 | Ongoing | [Ongoing] | ISMS-INI-010; ISMS-OPS-005 (Track 3) | Ongoing monitoring item. No immediate action required — Track 3 procedure is current. | Yes — Dec 2026 MR (D-09) | In Progress — ongoing
IMPROVEMENT LOG SUMMARY (January 2027): Total items: 15 ¦ Complete: 2 ¦ In Progress: 8 ¦ Planned: 5 ¦ High priority: 5 ¦ Medium: 7 ¦ Low: 3 ¦ This log is reviewed at every management review and every quarterly Steering Committee. Complete items are retained as evidence of continual improvement under Clause 10.2.

## Improvement by Source
ISMS-IMP-006 ¦ Improvement by Source ¦ Grouped by trigger — shows which ISMS inputs are driving improvements
This view helps demonstrate to a certification body that improvements are systematically driven by the monitoring and measurement programme, internal audits, management reviews, risk assessments, and operational experience — not random or reactive.
CI Ref | Source | Improvement (brief) | Owner | Target | Status
OPERATIONAL EXPERIENCE ¦ Source: DR test, tabletop exercise, vendor assessments
CI-001 | Operational experience | Enterprise customer VPC certificate renewal was a manual ste | Sana Al Farsi (Head of Cloud Infra) | Oct 2026 | Complete
CI-002 | Operational experience | October 2026 tabletop exercise revealed 5 procedure gaps in | Neha Choudhury (SOC Manager) | Oct 2026 | Complete
CI-003 | Operational experience | VaultArchive assessment identified that their internal DR te | Meera Iyer (ISMS Manager) | Mar 2027 | In Progress
CI-004 | Operational experience | SentinelWatch assessment identified that their BCDR has not | Meera Iyer (ISMS Manager) | Mar 2027 | In Progress
CI-013 | Operational experience | UAE region DR test has not yet been conducted — only India r | Sana Al Farsi (Head of Cloud Infra) | Oct 2027 | Planned — 2027
INTERNAL AUDIT ¦ Source: Audit 1 observations (ISMS-PEV-005)
CI-005 | Internal Audit obs. | Head of Procurement vacancy 11 months — ISMS Manager holds i | Farhan Ahmed (COO) | Feb 2027 | In Progress
CI-006 | Internal Audit obs. | MedLink Gulf Tier 1 assessment fieldwork complete but formal | Meera Iyer (ISMS Manager) | 10 Jan 2027 | In Progress
MANAGEMENT REVIEW ¦ Source: December 2026 management review decisions (ISMS-PEV-008)
CI-007 | Management Review | Security questionnaire response time currently 7–10 business | Meera Iyer (ISMS Manager) | Apr 2027 | In Progress
CI-008 | Management Review | Year 1 security awareness programme module should be refresh | Priya Subramaniam (Head of HR) | Jun 2027 | Planned
CI-009 | Management Review | Cross-region failover capability for India not built — a com | Ridhima Kapoor (CTO) | Q2 2027 | Planned — post-cert
ROOT CAUSE ANALYSIS ¦ Source: ISMS-IMP-003 programme pattern observations
CI-010 | RCA pattern observation | All three Dec 2026 NCRs share the root cause pattern: proces | Meera Iyer (ISMS Manager) | Mar 2027 | Planned
CI-011 | RCA pattern observation | Phase 5 delivery pace created latent documentation completen | Meera Iyer (ISMS Manager) | Jan 2027 | In Progress
CI-012 | RCA pattern observation | Detection system worked for NCR-003 (Sentinel caught the una | Neha Choudhury (SOC Manager) | Mar 2027 | Planned
EXTERNAL INTELLIGENCE ¦ Source: Regulatory monitoring (ISMS-INI-010 Legal Register)
CI-014 | External intelligence | DPDP Act 2023 implementation rules not yet finalised by the | Omar Al Mansoori (Head of Legal) | Ongoing | In Progress — ongoing
CI-015 | External intelligence | UAE PDPL regulatory infrastructure continues to mature — the | Omar Al Mansoori (Head of Legal) | Ongoing | In Progress — ongoing
Clause 10.2 requires the organisation to continually improve the suitability, adequacy, and effectiveness of the ISMS. ¦ This view demonstrates that improvements are systematically driven by the monitoring and measurement programme (PEV-001), internal audits (PEV-003), management reviews (PEV-007), risk assessment (PLN-004), and operational experience — not reactive to failures alone. The diversity of sources confirms the ISMS is self-improving across multiple feedback loops.

## Management Review Feed
ISMS-IMP-006 ¦ Management Review Feed ¦ Pre-formatted input for Clause 9.3 management review ¦ Agenda item A-10
This tab produces the Clause 10.2 input for each management review. ¦ The ISMS Manager updates this tab before each management review to reflect current status. ¦ Content maps to ISMS-PEV-007 agenda item A-10 (Opportunities for Improvement) and ISMS-PEV-009 Part 1 Input K.
CI Ref | Improvement Summary | Action / Change Taken or Planned | Owner | Status at This Review | Management Decision Required?
DECEMBER 2026 MANAGEMENT REVIEW — Agenda item A-10 input ¦ 13 improvement items
CI-001 | cert-manager automation — enterprise VPC certificate renewal automated post-DR test | Automation implemented October 2026. DR runbook updated. Verified at Audit 1 — no findings. | Sana Al Farsi | Complete — closed | No — complete
CI-002 | IR procedure updated — 5 tabletop findings incorporated into OPS-005 v1.0 | All 5 tabletop findings incorporated into ISMS-OPS-005 Section 12. Procedure in force from October 2026. Confirmed effective at Audit 1 (POS-002 positive finding). | Neha Choudhury | Complete — closed | No — complete
CI-003 | VaultArchive remediation commitments tracked — DR test and sub-processor reassessment | VaultArchive DR test due December 2026. Sub-processor reassessment due March 2027. Both tracked as security schedule conditions. | Meera Iyer | In Progress — March 2027 | No — monitoring
CI-004 | SentinelWatch BCDR test condition tracked — security schedule condition | R-021 added to risk register. KPI-028 monitors completion. Due March 2027. | Meera Iyer | In Progress — March 2027 | No — monitoring
CI-005 | Head of Procurement appointment — reduces ISMS Manager single-point-dependency | Recruitment in progress. COO confirmed target: February 2027. | Farhan Ahmed (COO) | In Progress — February 2027 | Yes — confirm timeline or escalate
CI-006 | MedLink Gulf assessment report — administrative gap closed | Report to be issued 10 January 2027. OPS-004 to be updated simultaneously. | Meera Iyer | In Progress — 10 Jan 2027 | No — ISMS Manager action
CI-007 | Security questionnaire response library — OO-08 post-certification target | Library to be built by April 2027 for post-certification deployment. | Meera Iyer | In Progress — April 2027 | No — ISMS Manager action
CI-008 | Year 2 awareness programme refresh — incorporating lessons and simulation results | Refresh to begin June 2027, incorporating February 2027 phishing simulation results. | Priya Subramaniam | Planned — June 2027 | No — note for Year 2 planning
CI-009 | Cross-region failover — post-certification architecture assessment | Architecture assessment by Q2 2027. Cost estimate to Steering Committee for budget approval. | Ridhima Kapoor (CTO) | Planned post-cert — Q2 2027 | Yes — Steering Committee budget decision required Q2 2027
CI-010 | Verification checkpoint design principle — embedded in Phase 9 workplan | RCA pattern observation: all three NCRs share root cause of process design without verification mechanism. Design principle to be documented in Phase 9 Stage 2 prep. | Meera Iyer | In Progress — March 2027 | No — ISMS Manager action
CI-011 | Last mile verification pass — added to Phase 9 Stage 2 preparation workplan | Targeted documentation verification pass before Stage 2: all FI entries retrievable, cross-references tested, procedures briefed. | Meera Iyer | In Progress — January 2027 | No — ISMS Manager action
CI-014 | DPDP Act rule monitoring — ongoing regulatory watch | MeitY DPDP Act implementation rules not yet finalised. Legal Register monitored quarterly. OPS-005 Track 2 will be updated when rules are notified. | Omar Al Mansoori (Head of Legal) | Ongoing — no action yet | No — monitoring; action if rules notified
CI-015 | UAE PDPL monitoring — Track 3 notification procedure currency | UAE DPO publications monitored. OPS-005 Track 3 is current. No immediate changes required. | Omar Al Mansoori (Head of Legal) | Ongoing — no action yet | No — monitoring