## Readiness Checklist
ISMS-ST1-003 ¦ Stage 1 Readiness Checklist ¦ Internal self-assessment ¦ Project HealthSec ¦ MediSync Technologies Pvt. Ltd.
Owner: Meera Iyer, ISMS Manager ¦ v1.0 ¦ February 2027 ¦ Completed before Stage 1 audit (10–11 February 2027). ¦ RAG: GREEN = ready ¦ AMBER = ready with note / minor gap ¦ RED = gap — action required ¦ CB Focus Area: items flagged in ISMS-ST1-002 (Stage 1 Audit Plan) Section 5 ¦ Classification: Confidential — Internal Use Only
Check Ref | Clause / Control | Readiness Question | Evidence / Document | GRC Path | Document Status | Readiness Notes | Self- Assessment | CB Focus Area? | Checked By | Check Date | RAG
CLAUSE 4 — CONTEXT (RC-001 to RC-003)
RC-001 | 4.1 | Is the context analysis current and does it reflect MediSync's operating environment including DPDP Act 2023 and UAE PDPL? | ISMS-INI-006 Context Analysis Report | Phase 1 — Initiation | Approved v1.0 | Reviewed at Dec 2026 management review — confirmed current. DPDP Act 2023 and UAE PDPL both reflected in legal register INI-010. | READY | No | Meera Iyer | Feb 2027 | GREEN
RC-002 | 4.2 | Are interested parties and their requirements documented? Does the register reflect 180+ hospital customers? | ISMS-INI-009 Interested Parties Register; ISMS-INI-010 Legal Register | Phase 1 — Initiation | Approved v1.0 | Interested parties register current. Legal register updated Dec 2026 — CERT-In, DPDP Act, UAE PDPL all present. | READY | No | Meera Iyer | Feb 2027 | GREEN
RC-003 | 4.3 | Is the ISMS scope documented, appropriate, and covering all four locations, all 8 products, both cloud regions? | ISMS-INI-011 ISMS Scope Document | Phase 1 — Initiation | Approved v1.0 | Scope confirmed at Dec 2026 management review. No scope changes since approval. Exclusions documented and justified. | READY | No | Vikram Sundaram | Feb 2027 | GREEN
CLAUSE 5 — LEADERSHIP (RC-004 to RC-006)
RC-004 | 5.1 / 5.2 | Is the IS Policy approved by top management, communicated to all staff, and reviewed within 12 months? | ISMS-LDR-001 IS Policy; ISMS-LDR-008 Policy Approval Record | Phase 2 — Leadership | Approved v1.0 | Policy approved by CEO Feb 2026. Communicated and acknowledged by ~430 staff. Reviewed at Dec 2026 management review — no amendments required. | READY | No | Meera Iyer | Feb 2027 | GREEN
RC-005 | 5.3 | Is the CISO formally appointed? Are roles, responsibilities, and authorities documented and communicated? | ISMS-LDR-007 CISO Appointment; ISMS-LDR-005 Roles Register | Phase 2 — Leadership | Approved v1.0 | CISO appointment documented Feb 2026. Roles register covers all ISMS function owners. Deputy ISMS Manager (Rohan Sharma) named. | READY | No | Meera Iyer | Feb 2027 | GREEN
RC-006 | 5.1 (Steering) | Is the Steering Committee constituted and meeting per the charter? Are minutes from the last 2 meetings available? | ISMS-LDR-006 SC Charter; last 2 SC meeting minutes | Phase 2 — Leadership | Approved v1.0 | Steering Committee met Q3 2026 and December 2026 (management review). Both minutes available. All mandatory agenda items addressed. | READY | No | Meera Iyer | Feb 2027 | GREEN
CLAUSE 6 — PLANNING (RC-007 to RC-010)
RC-007 | 6.1.2 | Is the risk assessment methodology documented and being followed? Is the risk register current with Phase 5 reassessment incorporated? | ISMS-PLN-001 Risk Methodology; ISMS-PLN-004 Risk Register; ISMS-OPS-011 Reassessment | Phase 3 — Planning | Approved v1.0 | 21 risks assessed. Phase 5 reassessment completed Oct 2026 (OPS-011). R-006, R-007, R-015 closures accepted at Dec 2026 management review. 0 HIGH risks. | READY | FA-2 | Vikram Sundaram | Feb 2027 | GREEN
RC-008 | 6.1.3 / SoA | Is the SoA complete — all 93 Annex A controls addressed with inclusion/exclusion justification? Are all FI entries evidenced? | ISMS-PLN-006 SoA; ISMS-OPS-002 Control Evidence Log | Phase 3 — Planning | Approved v1.0 | 88 FI, 2 PI, 3 IP, 0 NI. NCR-001 corrective action completed Jan 2027 — A5.8 evidence retrievable. Retrieval verification step added to OPS-002. 10-control spot-check by ISMS Manager confirmed. | READY | FA-1 | Vikram Sundaram | Feb 2027 | GREEN
RC-009 | 6.1.3 / Treatment | Is the risk treatment plan current? Are closed risks (R-006, R-007, R-015) marked as closed? Are MED-HIGH risks (R-002, R-004, R-009) linked to active treatment actions? | ISMS-PLN-005 Risk Treatment Plan; ISMS-OPS-011 | Phase 3 — Planning | Approved v1.0 | Treatment plan updated post-Audit 1. Closures confirmed at Dec 2026 MR. R-002 treatment: phishing simulation (Feb 2027 — in progress). R-004: tabletop annual cycle. R-009: regulatory monitoring (ongoing). | READY | FA-2 | Vikram Sundaram | Feb 2027 | GREEN
RC-010 | 6.2 | Are IS objectives (21 total) documented, measurable, and being monitored? Are OO-08 questionnaire response times being tracked? | ISMS-LDR-002 IS Objectives; ISMS-PEV-001 Monitoring Plan | Phase 2 + Phase 6 | Approved v1.0 | O-01 (certification Apr 2027): on track. O-04 (awareness ≥95%): 94% — Procurement vacancy gap accepted at MR. OO-08 (≤5 day response): 7–10 days currently — post-certification improvement item (CI-007). | READY — note OO-08 not yet at target; accepted as post-certification | No | Meera Iyer | Feb 2027 | AMBER
CLAUSE 7 — SUPPORT (RC-011 to RC-014)
RC-011 | 7.2(d) | Are training records maintained as evidence of competence? Are certificate register gaps corrected? | ISMS-SUP-004 Training Records; Certificate Register Tab 3 | Phase 4 — Support | Approved v1.0 | NCR-002 corrective action completed Jan 2027: AZ-500 renewal booked (examination 28 Jan 2027); Certificate Register restructured with Renewal Owner, Action Due, Status columns; 90-day reminders active. Neha Choudhury CEH: flagged as watch item — not yet an NCR but noted. | READY — AZ-500 renewed; certificate register restructured | FA-1 (indirect) | Meera Iyer | Feb 2027 | GREEN
RC-012 | 7.3 | Is the awareness programme operating? Has ≥95% completion been achieved? Is phishing simulation baseline established? | ISMS-SUP-005 Awareness Programme; ISMS-SUP-004 Tab 2; Phishing results | Phase 4 — Support | Approved v1.0 | 94% all-staff completion. Procurement 0% (vacancy — accepted at Dec 2026 MR). Second phishing simulation Feb 2027 — results to Steering Committee Mar 2027. Awareness gap is structural (vacancy), not programme failure. | READY — 94% accepted for certification; Procurement gap documented | No | Meera Iyer | Feb 2027 | AMBER
RC-013 | 7.4 | Are the three regulatory notification paths (CERT-In, DPDP Act, UAE PDPL) known and accessible? Is communication plan in force? | ISMS-SUP-007 Communication Plan; ISMS-OPS-005 (all three tracks) | Phase 4 + Phase 5 | Approved v1.0 | All three tracks in OPS-005. SOC Manager confirmed CERT-In clock trigger at Audit 1 (POS-002). Head of Legal confirmed DPDP Act and UAE PDPL tracks at Dec 2026 MR. | READY | FA-3 | Meera Iyer | Feb 2027 | GREEN
RC-014 | 7.5 | Does the Document Register match the GRC Repository? Are 5 randomly selected documents accessible at their stated paths? | ISMS-SUP-009 Document Register / Master List | Phase 4 — Support | Approved v1.0 | Document Register contains 92 primary ISMS documents. 5-document spot-check completed by ISMS Manager Feb 2027 — all 5 found at stated paths in stated versions. OPS-002 retrieval verification step now in force for all future FI entries. | READY | No | Meera Iyer | Feb 2027 | GREEN
CLAUSE 8 — OPERATION (RC-015 to RC-020)
RC-015 | 8.1 / A5.37 | Are operational security procedures in force? Are D-01 (access control) and D-02 (cloud config) being followed in live systems? | ISMS-OPS-001 Operational Procedures (all domains) | Phase 5 — Operation | Approved v1.0 | OPS-001 confirmed operational at Audit 1 — all 7 gap closures verified by external audit lead. NCR-003 corrective action completed Jan 2027: CHG-015 retrospective record created, IT Operations briefed on emergency change process, OPS-001 D-02.2 callout added. | READY | No | Vikram Sundaram | Feb 2027 | GREEN
RC-016 | 8.1 / A5.15–A5.18 — G-04 | Is G-04 (stale admin accounts) closed? Q3 2026 access review confirmed and Q4 review completed? | ISMS-OPS-009 Access Review Log (REV-001, REV-002) | Phase 5 — Operation | Approved v1.0 | REV-001 (Q3 2026): 847 accounts reviewed, 2 stale accounts disabled (confirmed Entra audit log). REV-002 (Q4 2026 / Jan 2027): completed — 0 stale accounts found. G-04 closed. | READY — Q4 review complete, 0 stale accounts found | FA-1 (SoA evidence) | Vikram Sundaram | Feb 2027 | GREEN
RC-017 | 8.1 / A5.24–A5.26 — R-006 | Is R-006 (IR plan failure) closed? Is ISMS-OPS-005 v1.0 in force, tabletop-tested, and embedded in SOC practice? | ISMS-OPS-005 IR Procedure; ISMS-OPS-006 Incident Register; tabletop record | Phase 5 — Operation | Approved v1.0 | R-006 closed at Dec 2026 MR. OPS-005 v1.0 in force. Tabletop Oct 2026 — 5 findings all incorporated. Incident register: 3 entries. Audit 1 POS-002 confirms procedure embedded in SOC practice. | READY — strongest positive finding at Audit 1 | FA-2 | Vikram Sundaram | Feb 2027 | GREEN
RC-018 | 8.1 / A8.13 — R-015 | Is R-015 (ransomware — backup loss) closed? Is S3 Object Lock and Azure Immutable Blob confirmed active? | ISMS-OPS-003 VaultArchive assessment; ISMS-OPS-008 DR test record | Phase 5 — Operation | Approved v1.0 | R-015 closed at Dec 2026 MR. Object Lock (Compliance mode) and Immutable Blob confirmed live at Audit 1 (POS-001). DR test Oct 2026 confirmed backup recovery. Stage 1 CB can request live demo — Sana Al Farsi available. | READY — confirmed live at internal audit | FA-2 | Vikram Sundaram | Feb 2027 | GREEN
RC-019 | 8.1 / A5.19–A5.20 — G-07 | Are all Tier 1 vendor assessments complete? VaultArchive (88/100), SentinelWatch (82/100), MedLink Gulf? | ISMS-OPS-003 Vendor Assessment Reports; ISMS-OPS-004 Supplier Register | Phase 5 — Operation | Approved v1.0 | VaultArchive (88/100) and SentinelWatch (82/100) complete — security schedules signed. MedLink Gulf: assessment fieldwork complete, formal report issued Jan 2027 (OBS-003 resolved). All Tier 1 assessments complete. Tier 2 assessments (PulseMail, PayBridge, TrustID) complete Jan 2027. | READY — all Tier 1 complete; Tier 2 complete Jan 2027 | No | Meera Iyer | Feb 2027 | GREEN
RC-020 | 8.1 / A8.32 — change mgmt | Is the change management process in force? NCR-003 corrective action complete? | ISMS-OPS-010 Change Log; ISMS-OPS-001 D-02.2 | Phase 5 — Operation | Approved v1.0 | NCR-003 CA completed Jan 2027: CHG-015 retrospective record created and baseline-compliant; Sentinel alert closed with CHG-015 reference; IT Operations emergency change briefing completed with attendance record; OPS-001 D-02.2 callout added. | READY — NCR-003 corrective action fully complete | No | Vikram Sundaram | Feb 2027 | GREEN
CLAUSE 9 — PERFORMANCE EVALUATION (RC-021 to RC-024)
RC-021 | 9.1 | Is the KPI measurement plan (PEV-001) operational? Are monthly GRC reports being produced? | ISMS-PEV-001 Monitoring Plan; ISMS-PEV-002 KPI Log (full year) | Phase 6 — Performance | Approved v1.0 | 28 KPIs measured per PEV-001. Monthly GRC reports operational since Phase 5. Certificate renewal status added to monthly GRC report (NCR-002 systemic improvement). | READY | No | Meera Iyer | Feb 2027 | GREEN
RC-022 | 9.2 | Was the internal audit conducted by an independent, qualified auditor? Was it full-scope? | ISMS-PEV-005 Audit Report; ISMS-PEV-003 Audit Programme | Phase 6 — Performance | Approved v1.0 | External audit lead — IRCA-registered ISO 27001 Lead Auditor. No prior involvement with MediSync ISMS implementation. Full scope (all clauses + sampled Annex A controls). Audit 1 Dec 2026. Audit 2 confirmed 10–12 Feb 2027 — CA closure verification. | READY — independent, qualified, full-scope | FA-4 | Meera Iyer | Feb 2027 | GREEN
RC-023 | 9.2 / NCRs | Are all 3 minor NCR corrective action plans complete? Is Audit 2 confirming closure? | ISMS-IMP-001 NCR Register; ISMS-IMP-002 CAR Forms; ISMS-IMP-005 Effectiveness Records | Phase 7 — Improvement | v1.0 | All 3 NCR CAs completed Jan 2027 (before the 31 Jan target): NCR-001 (A5.8 evidence created and retrievable), NCR-002 (AZ-500 booked 28 Jan 2027; certificate register restructured), NCR-003 (CHG-015 created; IT Ops briefed; OPS-001 D-02.2 updated). Audit 2 (10–12 Feb 2027) to confirm effectiveness. | READY — all 3 CAs complete before Stage 1 date. Audit 2 confirms. | FA-4 | Meera Iyer | Feb 2027 | GREEN
RC-024 | 9.3 | Did the management review address all 11 Clause 9.3.2 mandatory inputs? Are outputs documented? | ISMS-PEV-008 MR Minutes; ISMS-PEV-009 MR Input/Output Record | Phase 6 — Performance | Approved v1.0 | Dec 2026 management review: 12 agenda items, 13 decisions, 12 actions. All 11 mandatory inputs confirmed in PEV-009. Stage 1 proceed decision recorded (D-12). Signed by CEO and ISMS Manager 5 Jan 2027. Retained permanently. | READY — all mandatory inputs addressed; Stage 1 proceed formally authorised | FA-5 | Meera Iyer | Feb 2027 | GREEN
CLAUSE 10 — IMPROVEMENT (RC-025 to RC-026)
RC-025 | 10.1 | Is the nonconformity and corrective action process operational? Is the NCR register being maintained? | ISMS-IMP-001 NCR Register; ISMS-IMP-004 CA Tracker | Phase 7 — Improvement | v1.0 | NCR register active since Dec 2026 audit. 3 NCRs registered, all CAs completed Jan 2027. CA tracker monitors 18 actions (13 NCR + 5 MR actions). Process confirmed operational. | READY | No | Meera Iyer | Feb 2027 | GREEN
RC-026 | 10.2 | Is the continual improvement log being maintained? Are improvements drawn from multiple sources? | ISMS-IMP-006 CI Log; ISMS-IMP-007 Lessons Learned Register | Phase 7 — Improvement | v1.0 | CI Log: 15 items from 5 sources (operational experience, audit observations, management review decisions, RCA patterns, external intelligence). Lessons Learned: 18 lessons from 6 source types. 10 complete, 7 in progress, 1 planned. | READY — improvements from multiple sources; Clause 10.2 satisfied | No | Meera Iyer | Feb 2027 | GREEN
DUAL JURISDICTION AND HEALTHCARE CONTEXT (RC-027 to RC-028)
RC-027 | Scope coherence — dual jurisdiction | Are both AWS India and Azure UAE regions consistently covered by the ISMS — risk register, SoA controls, incident notification, DR planning? | ISMS-PLN-004 (risks covering UAE); ISMS-OPS-005 (Tracks 1–3); ISMS-OPS-007 (UAE region DR plan) | Phase 3 + Phase 5 | Approved v1.0 | Risk register covers UAE region risks (R-008, R-009, R-011). SoA controls applied to both regions. OPS-005 Track 3 covers UAE PDPL. UAE region DR test planned Oct 2027 (CI-013). India DR test confirmed Oct 2026. | READY — note: UAE DR test planned 2027 (India only tested Oct 2026) | FA-6 | Vikram Sundaram | Feb 2027 | AMBER
RC-028 | Healthcare context — EHR standards | Is MoHFW EHR Standards 2016 compliance documented for EHR-CORE and HIS-CORE? Is the healthcare technical expert likely to find this evidenced? | ISMS-INI-010 Legal Register; product compliance documentation | Phase 1 + Phase 5 | Approved v1.0 | MoHFW EHR Standards compliance confirmed for EHR-CORE and HIS-CORE — documented in Legal Register INI-010. No material changes notified in current period (confirmed Head of Clinical Integration written brief, Dec 2026 MR). CB healthcare technical expert will review. | READY — legal register current; clinical integration head brief available | FA-3 | Vikram Sundaram | Feb 2027 | GREEN
READINESS SUMMARY (February 2027): Total checks: 28 ¦ GREEN (ready): 25 ¦ AMBER (ready with note): 3 ¦ RED (gap): 0 ¦ Overall assessment: READY TO PROCEED TO STAGE 1 ¦ AMBER items are documented known gaps — all accepted at Dec 2026 management review or flagged as post-certification improvement items. No RED items. No undisclosed gaps.

## Document Availability
ISMS-ST1-003 ¦ Document Availability ¦ Confirms every Stage 1 requested document is in the GRC Repository
One row per document requested in ISMS-ST1-002 Section 6. ¦ ISMS Manager to confirm each document is accessible at its stated GRC path before the Stage 1 opening meeting. ¦ GREEN = accessible ¦ AMBER = accessible but check needed ¦ RED = not accessible — action required
Document Ref | Document Title | GRC Repository Path | Version | Last Updated | CB Priority | Available?
ISMS-INI-006 | Context Analysis Report | /Phase 1 — Initiation/ | v1.0 | Feb 2026 | Required Day 1 | GREEN
ISMS-INI-009 | Interested Parties Register | /Phase 1 — Initiation/ | v1.0 | Feb 2026 | Required Day 1 | GREEN
ISMS-INI-010 | Legal and Regulatory Register | /Phase 1 — Initiation/ | v1.0 | Dec 2026 review | Required Day 1 | GREEN
ISMS-INI-011 | ISMS Scope Document | /Phase 1 — Initiation/ | v1.0 | Feb 2026 | Required Day 1 | GREEN
ISMS-LDR-001 | Information Security Policy | /Phase 2 — Leadership/ | v1.0 | Feb 2026 | Required Day 1 | GREEN
ISMS-LDR-002 | Information Security Objectives | /Phase 2 — Leadership/ | v1.0 | Feb 2026 | Required Day 1 | GREEN
ISMS-LDR-006 | Steering Committee Charter | /Phase 2 — Leadership/ | v1.0 | Feb 2026 | Required Day 1 | GREEN
ISMS-LDR-007 | CISO Appointment Record | /Phase 2 — Leadership/ | v1.0 | Feb 2026 | Required Day 1 | GREEN
ISMS-PLN-001 | Risk Assessment Methodology | /Phase 3 — Planning/ | v1.0 | May 2026 | Required Day 1 | GREEN
ISMS-PLN-004 | Risk Register (Phase 5 baseline) | /Phase 3 — Planning/ | v1.0 | Oct 2026 | Required Day 1 | GREEN
ISMS-PLN-005 | Risk Treatment Plan | /Phase 3 — Planning/ | v1.0 | Jan 2027 | Required Day 1 | GREEN
ISMS-PLN-006 | Statement of Applicability (all 93 controls) | /Phase 3 — Planning/ | v1.0 | May 2026 | Required Day 1 | GREEN
ISMS-SUP-001 | Resource Allocation Plan | /Phase 4 — Support/ | v1.0 | Feb 2026 | Required Day 1 | GREEN
ISMS-SUP-004 | Training Records (incl. Certificate Register Tab 3) | /Phase 4 — Support/ | v1.0 (Tab 3 updated Jan 2027) | Jan 2027 | Required Day 1 | GREEN
ISMS-SUP-005 | Security Awareness Programme | /Phase 4 — Support/ | v1.0 | May 2026 | Required Day 1 | GREEN
ISMS-SUP-009 | Document Register / Master List | /Phase 4 — Support/ | v1.0 | Jan 2027 | Required Day 1 | GREEN
ISMS-SUP-010 | Records Retention Schedule | /Phase 4 — Support/ | v1.0 | May 2026 | Required Day 1 | GREEN
ISMS-OPS-001 | Operational Security Procedures (all domains) | /Phase 5 — Operation/ | v1.0 (D-02.2 updated Jan 2027) | Jan 2027 | Required Day 2 | GREEN
ISMS-OPS-002 | Control Evidence Log | /Phase 5 — Operation/ | v1.0 (A5.8 updated Jan 2027) | Jan 2027 | Required Day 2 | GREEN
ISMS-OPS-003 | Vendor Assessment Reports (all Tier 1) | /Phase 5 — Operation/ | v1.0 | Jan 2027 | Required Day 2 | GREEN
ISMS-OPS-004 | Supplier Register | /Phase 5 — Operation/ | v1.0 (Tier 2 updated Jan 2027) | Jan 2027 | Required Day 2 | GREEN
ISMS-OPS-005 | Incident Management Procedure | /Phase 5 — Operation/ | v1.0 | Oct 2026 | Required Day 2 | GREEN
ISMS-OPS-007 | BCDR Plan | /Phase 5 — Operation/ | v1.0 | Oct 2026 | Required Day 2 | GREEN
ISMS-OPS-008 | DR Test Record and Runbooks | /Phase 5 — Operation/ | v1.0 | Oct 2026 | Required Day 2 | GREEN
ISMS-OPS-009 | Access Review Log (REV-001 + REV-002) | /Phase 5 — Operation/ | v1.0 | Jan 2027 | Required Day 2 | GREEN
ISMS-OPS-010 | Change Management Log | /Phase 5 — Operation/ | v1.0 (CHG-015 added Jan 2027) | Jan 2027 | Required Day 2 | GREEN
ISMS-OPS-011 | Risk Reassessment Report (Phase 5) | /Phase 5 — Operation/ | v1.0 | Oct 2026 | Required Day 2 | GREEN
ISMS-PEV-001 | Monitoring and Measurement Plan | /Phase 6 — Performance/ | v1.0 | Dec 2026 | Supporting | GREEN
ISMS-PEV-003 | Internal Audit Programme | /Phase 6 — Performance/ | v1.0 | Nov 2026 | Required Day 2 | GREEN
ISMS-PEV-005 | Internal Audit Report (Audit 1, Dec 2026) | /Phase 6 — Performance/ | v1.0 | Dec 2026 | Required Day 2 | GREEN
ISMS-PEV-006 | Internal Audit Findings Register | /Phase 6 — Performance/ | v1.0 | Dec 2026 | Required Day 2 | GREEN
ISMS-PEV-008 | Management Review Minutes (Dec 2026) | /Phase 6 — Performance/ | v1.0 | Jan 2027 | Required Day 2 | GREEN
ISMS-PEV-009 | Management Review Input/Output Record | /Phase 6 — Performance/ | v1.0 | Jan 2027 | Required Day 2 | GREEN
ISMS-IMP-001 | Nonconformity Register | /Phase 7 — Improvement/ | v1.0 | Jan 2027 | Required Day 2 | GREEN
ISMS-IMP-002 | Corrective Action Request Forms (all 3) | /Phase 7 — Improvement/ | v1.0 | Jan 2027 | Required Day 2 | GREEN
ISMS-IMP-003 | Root Cause Analysis Reports | /Phase 7 — Improvement/ | v1.0 | Jan 2027 | Required Day 2 | GREEN
ISMS-IMP-006 | Continual Improvement Log | /Phase 7 — Improvement/ | v1.0 | Jan 2027 | Required Day 2 | GREEN
ISMS-IMP-007 | Lessons Learned Register | /Phase 7 — Improvement/ | v1.0 | Jan 2027 | Supporting | GREEN
DOCUMENT AVAILABILITY SUMMARY: Total documents: 38 ¦ Available (GREEN): 38 ¦ Not available (RED): 0 ¦ GRC Repository access confirmed accessible for certification body lead auditor. ¦ All document updates (Jan 2027 NCR corrective actions) have been reflected in the GRC Repository.

## Open Items
ISMS-ST1-003 ¦ Open Items ¦ Known gaps and risks going into Stage 1 — with mitigations
These are the known open items as at the Stage 1 audit date (10–11 February 2027). ¦ Each item has a documented management decision accepting it for the certification period, or a mitigation in place. ¦ No undisclosed gaps. The certification body has access to all of these items in the ISMS documentation.
Item Ref | Category | Open Item Description | Management Decision / Mitigation | Source Document | Impact on Stage 1 | RAG
OI-001 | Awareness completion | Procurement department: 0% awareness completion. All-staff completion: 94% — below the 95% target. | Dec 2026 management review (D-02): gap attributed to Head of Procurement vacancy. Accepted for the certification period. Head of Procurement appointment in progress — target February 2027. On appointment, new hire completes awareness module within 4 weeks. | ISMS-PEV-008 (D-02); ISMS-IMP-006 (CI-005) | AMBER — CB will see this in the audit report. The gap is documented, explained, and managed. | AMBER
OI-002 | SoA — In Progress controls (3) | 3 controls remain in Progress (IP) status in ISMS-PLN-006: A5.29 (IS during disruption — UAE DR test pending), A5.31 (legal requirements — DPDP Act rules not finalised), A5.36 (policies compliance review — annual cycle due Apr 2027). | All three IP controls have documented treatment timelines: A5.29 — UAE DR test Oct 2027 (CI-013); A5.31 — DPDP Act rules monitoring (CI-014, no action possible until rules published); A5.36 — annual review scheduled Apr 2027. None are required to be FI before Stage 1 — only before Stage 2 certification decision. | ISMS-PLN-006 (SoA); ISMS-IMP-006 (CI-013, CI-014) | AMBER — CB will review these. Each has a documented rationale and planned completion. Not blocking Stage 1. | AMBER
OI-003 | Penetration test (pre-Stage 2) | Annual penetration test not yet completed. Scheduled February 2027 — before Stage 2. | Dec 2026 management review confirmed penetration test is a pre-Stage 2 condition (approved at M-05 tranche). Test is scheduled Feb 2027 by external firm. Results will be available before Stage 2 audit commences. Critical and High findings will be remediated before Stage 2. | ISMS-PEV-008 (D-12); ISMS-ST1-002 (Section 7 — Conditional criterion) | AMBER — CB Stage 1 audit plan acknowledges this as a Conditional criterion. Not blocking Stage 1. | AMBER
OI-004 | UAE region DR test (2027) | DR test conducted October 2026 covered India region only (AWS ap-south-1). Azure UAE North recovery has not been tested — planned October 2027 annual cycle. | India DR test confirmed all RTOs within target. UAE region DR test planned Oct 2027 (CI-013 in CI log). UAE primary region hosts only UAE patient data — a separate failure scenario. ISMS-OPS-007 Section 9 documents the limitation and the planned test. | ISMS-OPS-007 (Section 9); ISMS-IMP-006 (CI-013) | AMBER — CB will note this. Not blocking Stage 1 or Stage 2. Planned 2027 annual cycle. | AMBER
OI-005 | DPDP Act implementation rules | DPDP Act 2023 implementation rules not yet finalised by the Government of India. MediSync's obligations as Data Processor are clear — but the Data Fiduciary obligations of hospital customers remain partly unresolved. | Legal Register (INI-010) reflects the current uncertainty. OPS-005 Track 2 is drafted to meet the anticipated obligations. Head of Legal monitors MeitY publications quarterly. When rules are finalised, Track 2 will be reviewed and updated within 30 days. | ISMS-INI-010; ISMS-OPS-005 (Track 2); ISMS-IMP-006 (CI-014) | AMBER — external regulatory uncertainty; MediSync cannot resolve this. CB will understand the context. | AMBER
OI-006 | Neha Choudhury CEH (expired 2023) | Neha Choudhury's Certified Ethical Hacker (CEH) certification expired 2023 — approximately 3–4 years lapsed. This was noted in ISMS-SUP-004 Tab 3 at the internal audit but was not raised as an NCR (auditor noted the SOC Manager has demonstrated deep operational competence through incident management; CEH is not a role-critical qualification in the same way as AZ-500 for a cloud infrastructure role). | Noted as a watch item. The CEH lapse is less operationally significant than the AZ-500 lapse (NCR-002) because Neha Choudhury's role is primarily SOC management and procedure — not active penetration testing. The audit lead did not raise this as an NCR. The certificate register (Tab 3 Jan 2027 update) now tracks it with a Renewal Owner and Action Due date. HR to assess renewal priority alongside AZ-500 follow-up. | ISMS-SUP-004 (Tab 3); ISMS-PEV-005 (Section 7) | AMBER — CB may or may not note this. Certificate register now tracking it with ownership. | AMBER
OPEN ITEMS POLICY: MediSync does not conceal known gaps from the certification body. All items above are documented in the ISMS and visible to the CB in the GRC Repository. Every AMBER item has a management decision accepting it for the certification period or a mitigation actively in place. No RED items — no undisclosed gaps that could constitute a major nonconformity at Stage 1 or Stage 2.

## Readiness Sign-Off
ISMS-ST1-003 ¦ Readiness Sign-Off ¦ CISO and ISMS Manager declaration that MediSync is ready for Stage 1
This sign-off confirms that the readiness checklist has been completed, all known open items are documented, and MediSync is ready to proceed to Stage 1 audit on 10–11 February 2027.
The following individuals confirm that: (1) The Stage 1 readiness checklist (Tab 1) has been completed and reviewed. (2) All ISMS documents requested in ISMS-ST1-002 are available in the GRC Repository (Tab 2). (3) All known open items are documented in Tab 3 — no undisclosed gaps. (4) MediSync is ready to proceed to Stage 1 audit on 10–11 February 2027. (5) The GRC Repository read-only access has been tested and is accessible to the certification body.
Declaration | Name | Signature | Date
CISO — MediSync Technologies Pvt. Ltd. I confirm the ISMS is operationally ready for Stage 1 certification audit. | Vikram Sundaram | ______________________________ | _______ February 2027
ISMS Manager — MediSync Technologies Pvt. Ltd. I confirm all documentation is complete, accessible, and up to date in the GRC Repository. | Meera Iyer | ______________________________ | _______ February 2027
READINESS SUMMARY: 28 readiness checks completed ¦ 25 GREEN (ready) ¦ 3 AMBER (ready with note — all accepted/mitigated) ¦ 0 RED ¦ 38 documents confirmed in GRC Repository ¦ 6 open items documented and disclosed ¦ OVERALL READINESS VERDICT: READY TO PROCEED TO STAGE 1