## Condition Register
ISMS-ST1-006 ¦ Stage 1 Condition Register ¦ Tracks Stage 2 conditions from ISMS-ST1-005 to closure ¦ Project HealthSec ¦ MediSync Technologies Pvt. Ltd.
Owner: Meera Iyer, ISMS Manager ¦ v1.0 ¦ February 2027 ¦ Source: ISMS-ST1-005 (Stage 1 Audit Findings Report, issued 18 February 2027). ¦ S2-C001 and S2-C002 are Stage 2 conditions — both must be resolved before Stage 2 is scheduled. ¦ Stage 1 observations (OBS-S1-001, OBS-S1-002, OBS-S1-003) are tracked in Tab 1 for completeness but require no mandatory action. ¦ Classification: Confidential — Internal Use Only
Condition Ref | Type | ISO 27001:2022 Clause / Control | Condition Description (from ISMS-ST1-005) | Resolution Required | Condition Owner | Resolution Target | Response Submitted? | CB Acceptance Date | Evidence Package Ref | Condition Closed? | Closed Date | S2 Proceed Unblocked? | Status
STAGE 2 CONDITIONS (S2-C001, S2-C002) — Both must be resolved before Stage 2 is scheduled
S2-C001 | STAGE 2 CONDITION | A8.8 — Vulnerability management; A5.36 — Compliance with IS policies | Annual penetration test not yet complete at Stage 1 date (10–11 Feb 2027). Test scheduled 17–21 February 2027. CB requires penetration test results to be shared before Stage 2 is scheduled. Any Critical or High findings must have documented remediation or CISO-signed risk acceptance before Stage 2 commences. | Share penetration test results with CB lead auditor. Confirm all Critical and High findings are remediated (or risk-accepted). CB to confirm S2-C001 is resolved before scheduling Stage 2. | Vikram Sundaram (CISO) | By 28 Feb 2027 (results available; shared with CB) | [To be completed] | [To be confirmed by CB] | EP-001 | [Yes / No] | [Date] | [Yes / No] | In Progress — test completed 21 Feb 2027; results under review
S2-C002 | STAGE 2 CONDITION | A6.3 — IS awareness; Clause 7.5 — Documented information availability | During the 10-control SoA evidence spot-check, the CB found that ISMS-OPS-002 cites the awareness platform admin URL as evidence for A6.3 (Awareness) rather than a GRC-resident evidence document. The awareness programme is clearly implemented (94% completion). The OPS-002 entry needs to cite a GRC-resident document (e.g., monthly awareness completion summary exported from the platform and filed in GRC Repository). | Create a GRC-resident evidence document for A6.3: export the most recent monthly awareness completion summary from the awareness platform and file it in the GRC Repository. Update ISMS-OPS-002 A6.3 evidence location field to the specific GRC path. Notify CB lead auditor when complete. | Meera Iyer (ISMS Manager) | By 28 Feb 2027 (before Stage 2 commences) | [To be completed] | [To be confirmed by CB] | EP-002 | [Yes / No] | [Date] | [Yes / No] | In Progress — action initiated; completion target 25 Feb 2027
STAGE 1 OBSERVATIONS (OBS-S1-001 to OBS-S1-003) — No mandatory action; tracked for Stage 2 awareness
OBS-S1-001 | OBSERVATION (no mandatory action) | Clause 7.3 — Awareness | Awareness completion at 94% all-staff. Procurement department at 0% due to Head of Procurement vacancy (Month 11). CB accepted the management decision. Head of Procurement appointment in progress (target February 2027). | No mandatory corrective action. Head of Procurement to be appointed February 2027. On appointment, new hire completes awareness module within 4 weeks. Lead auditor to confirm awareness ≥95% at Stage 2. | Farhan Ahmed (COO) / Priya Subramaniam (HR) | Feb 2027 (appointment) | N/A | N/A — observation; no CB acceptance required | N/A | N/A — observation | N/A | N/A | Tracked — appointment in progress; no action required before Stage 2
OBS-S1-002 | OBSERVATION (no mandatory action) | Clause 6.1.3 / SoA (A5.29, A5.31, A5.36) | 3 SoA controls remain In Progress: A5.29 (UAE DR test — Oct 2027), A5.31 (DPDP Act rules not finalised), A5.36 (annual compliance review — April 2027). Each has a documented completion timeline. CB noted A5.36 should be FI by Stage 2 (April 2027 review due before Stage 2 target date). | No mandatory action before Stage 2. A5.36 annual compliance review to be completed April 2027 — before or concurrent with Stage 2. A5.29 and A5.31 documented timelines to be updated at April 2027 post-certification management review. | Meera Iyer (ISMS Manager) | A5.36: Apr 2027; A5.29: Oct 2027; A5.31: ongoing | N/A | N/A — observation | N/A | N/A — observation | N/A | N/A | Tracked — A5.36 on track for April 2027
OBS-S1-003 | OBSERVATION (no mandatory action) | A8.13; A5.29 (DR completeness) | UAE region DR test not yet conducted — India region tested October 2026 (all RTOs met). Azure UAE North recovery not independently tested. UAE test planned October 2027 annual cycle. CB noted this as a Year 1 surveillance item — to be reviewed at first surveillance audit (December 2027). | No mandatory action before Stage 2 or certification. UAE DR test planned October 2027. ISMS-OPS-007 Section 9 documents the limitation. CI-013 in the CI log tracks this as a planned improvement. | Sana Al Farsi (Head of Cloud Infra) | Oct 2027 (planned annual cycle) | N/A | N/A — observation | N/A | N/A — observation | N/A | N/A | Tracked — planned for 2027 annual DR test
STAGE 1 POSITIVE FINDINGS (PF-001 to PF-003) — Noted for record; no action required
PF-001 | POSITIVE FINDING | A5.24–A5.26; R-006 closure | Risk closure evidence at an exceptional standard: R-006 closed with three independent evidence sources (OPS-005 procedure, INC-003 tabletop record, OPS-006 incident register). SOC Manager confirmed CERT-In clock trigger from memory at internal audit. | No action required. Positive finding noted for record. Stage 2 will conduct an independent live IR procedure walkthrough. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Positive finding — noted
PF-002 | POSITIVE FINDING | Clause 10.1 — NCR corrective actions | All three NCRs from December 2026 internal audit resolved ahead of target (28 Jan 2027 vs 31 Jan 2027 target). AZ-500 examination passed 28 January 2027. RCA quality praised — root cause vs symptom distinction clear. | No action required. Effectiveness of corrective actions to be verified at Stage 2 via document review and knowledge checks. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Positive finding — noted
PF-003 | POSITIVE FINDING | Regulatory compliance (CERT-In, DPDP Act, UAE PDPL) | Dual-jurisdiction regulatory coherence rated above average for an organisation of MediSync's size. Three notification tracks documented. All 22 enterprise customer DPAs current. DPDP Act uncertainty handled pragmatically. | No action required. Stage 2 to review a sample DPA to confirm currency. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Positive finding — noted
STAGE 1 FINDINGS SUMMARY (February 2027): Stage 2 conditions (mandatory): 2 — both In Progress, target 28 Feb 2027 ¦ Observations (no mandatory action): 3 ¦ Positive findings: 3 ¦ Stage 2 cannot be scheduled until S2-C001 and S2-C002 are both confirmed resolved by the CB lead auditor.

## Response Actions
ISMS-ST1-006 ¦ Response Actions ¦ Specific steps to resolve S2-C001 and S2-C002
One row per action step. Both conditions must be resolved and accepted by the CB before Stage 2 can be scheduled. ¦ ISMS Manager to update "Completed?" column as each step is done and notify CB upon full resolution.
Step Ref | Condition | Action Description | How to Verify (what CB will check) | Owner | Target Date | Completed?
S2-C001 — Penetration Test Results (target: 28 February 2027)
C001-S1 | S2-C001 | Confirm penetration test has been completed by the named external firm (scheduled 17–21 February 2027). Obtain the formal penetration test report from the firm. | CB will request to see the penetration test report on the firm's letterhead, scoped to API-GW, HIS-CORE, and EHR-CORE external interfaces. Report must be dated within the scheduled window. | Vikram Sundaram (CISO) | 21 Feb 2027 | [Done — 21 Feb 2027]
C001-S2 | S2-C001 | Review the penetration test report for Critical and High findings. For each Critical or High finding: either document the remediation action taken (with evidence) or document a CISO-signed risk acceptance explaining why the finding cannot be remediated within the Stage 2 timeline and what compensating control applies. | CB will review: (a) the finding list; (b) for each Critical/High finding — either an evidence-backed remediation record or a CISO-signed risk acceptance. Medium and Low findings do not require pre-Stage 2 remediation but must be tracked. | Vikram Sundaram (CISO) | 25 Feb 2027 | [Pending — in progress]
C001-S3 | S2-C001 | Store the penetration test report (classified Restricted) in the GRC Repository at: /Phase 5 — Operation/Penetration Tests/PenTest_Feb2027_[Firm]_Restricted.pdf. Store any remediation records or risk acceptances at the same path. Update ISMS-OPS-002 with the pen test evidence location. | CB will navigate to the GRC path and retrieve the report. The report must be accessible to the lead auditor via the existing read-only SharePoint link. | Meera Iyer (ISMS Manager) | 25 Feb 2027 | [Pending]
C001-S4 | S2-C001 | Notify CB lead auditor that S2-C001 is resolved: send email to [lead auditor email] with a brief summary of: (a) test completion date, (b) number of findings by severity, (c) Critical/High remediation status, (d) GRC Repository path for the report. | CB lead auditor confirms S2-C001 resolved by email. Written confirmation required before Stage 2 can be scheduled. | Vikram Sundaram (CISO) | 28 Feb 2027 | [Pending]
S2-C002 — A6.3 Awareness Evidence Document (target: 28 February 2027)
C002-S1 | S2-C002 | Export the most recent monthly awareness completion summary from the awareness platform. The export must show: staff name (or employee ID), department, module completion status, completion date, and score. Export format: PDF or Excel. Export period: January 2027 (the month immediately before Stage 1). | CB will review the exported document to confirm it shows per-department completion rates consistent with the 94% figure cited in ISMS-SUP-004 Tab 2. | Priya Subramaniam (Head of HR) | 24 Feb 2027 | [Pending]
C002-S2 | S2-C002 | File the exported awareness completion summary in the GRC Repository at: /Phase 5 — Operation/ISMS-OPS-002/A6.3_Awareness_Completion_Evidence_Jan2027.xlsx (or .pdf). This creates a GRC-resident evidence document that can be independently retrieved without accessing the live awareness platform. | CB lead auditor will navigate to this path and retrieve the document. The file must be accessible via the existing read-only SharePoint link. | Meera Iyer (ISMS Manager) | 25 Feb 2027 | [Pending]
C002-S3 | S2-C002 | Update ISMS-OPS-002 A6.3 evidence location field: replace the current awareness platform admin URL with the specific GRC Repository path: /Phase 5 — Operation/ISMS-OPS-002/A6.3_Awareness_Completion_Evidence_Jan2027.xlsx | CB will open ISMS-OPS-002, navigate to A6.3, and confirm the evidence location field now shows a GRC Repository path (not a URL). CB will then navigate to the stated path and retrieve the document. | Meera Iyer (ISMS Manager) | 25 Feb 2027 | [Pending]
C002-S4 | S2-C002 | Notify CB lead auditor that S2-C002 is resolved: send email to [lead auditor email] confirming: (a) awareness completion summary exported and filed at stated GRC path, (b) OPS-002 A6.3 evidence location updated. Include the GRC Repository path in the email. | CB lead auditor confirms S2-C002 resolved by email. Written confirmation required before Stage 2 commences. | Meera Iyer (ISMS Manager) | 28 Feb 2027 | [Pending]

## Evidence Package
ISMS-ST1-006 ¦ Evidence Package ¦ What MediSync sends to the CB to confirm S2-C001 and S2-C002 resolution
This tab defines the evidence package that will be sent to the CB lead auditor to confirm that both Stage 2 conditions are resolved. ¦ The CB lead auditor must confirm both conditions resolved before Stage 2 can be scheduled. ¦ Evidence should be sent as a single email to the lead auditor with a brief cover note summarising the resolution of each condition.
Evidence Ref | Condition | Evidence Description | Where Filed (GRC Repository Path) | Prepared By | Date Ready | In GRC Repo? | Sent to CB?
S2-C001 — Penetration Test Evidence Package (to be sent to CB by 28 February 2027)
EP-001-A | S2-C001 | Penetration test report — formal report from external firm covering API-GW, HIS-CORE, and EHR-CORE external interfaces. Classified Restricted. | /Phase 5 — Operation/Penetration Tests/PenTest_Feb2027_[Firm]_Restricted.pdf | Vikram Sundaram (CISO) | 25 Feb 2027 | [Pending] | [Pending]
EP-001-B | S2-C001 | Critical and High finding remediation records — for each Critical/High finding: a brief description of the finding, the remediation action taken, and the evidence of remediation (e.g., screenshot, configuration record, code change). | /Phase 5 — Operation/Penetration Tests/PenTest_Feb2027_Remediation_Log.xlsx | Vikram Sundaram (CISO) | 25 Feb 2027 | [Pending] | [Pending]
EP-001-C | S2-C001 | CISO risk acceptance (if any Critical/High findings cannot be remediated before Stage 2) — CISO-signed document noting the finding, the compensating control, and the planned remediation timeline. | /Phase 5 — Operation/Penetration Tests/PenTest_Feb2027_Risk_Acceptance_[if needed].pdf | Vikram Sundaram (CISO) | 25 Feb 2027 (if needed) | [If needed] | [If needed]
EP-001-D | S2-C001 | ISMS-OPS-002 updated — A8.8 and A5.36 evidence location fields updated to reference the GRC path for the pen test report. | /Phase 5 — Operation/ISMS-OPS-002 (updated) | Meera Iyer (ISMS Manager) | 25 Feb 2027 | [Pending] | [Pending]
S2-C002 — A6.3 Awareness Evidence Package (to be sent to CB by 28 February 2027)
EP-002-A | S2-C002 | Awareness completion summary export — January 2027 monthly export from the awareness platform showing per-staff completion status, department, date, and score. | /Phase 5 — Operation/ISMS-OPS-002/A6.3_Awareness_Completion_Evidence_Jan2027.xlsx | Priya Subramaniam (Head of HR) | 24 Feb 2027 | [Pending] | [Pending]
EP-002-B | S2-C002 | ISMS-OPS-002 updated — A6.3 evidence location field updated from the awareness platform URL to the GRC Repository path: /Phase 5 — Operation/ISMS-OPS-002/A6.3_Awareness_Completion_Evidence_Jan2027.xlsx | /Phase 5 — Operation/ISMS-OPS-002 (updated) | Meera Iyer (ISMS Manager) | 25 Feb 2027 | [Pending] | [Pending]
CB NOTIFICATION COVER NOTE TEMPLATE — Adapt and send to lead auditor when both conditions are resolved
COVER NOTE TEMPLATE (adapt and send by email): Subject: MediSync — Stage 1 Condition Resolution — S2-C001 and S2-C002 Dear [Lead Auditor Name], I am writing to confirm that both Stage 2 conditions from the Stage 1 Findings Report (ISMS-ST1-005) have been resolved. S2-C001 — Penetration Test: The annual penetration test was completed on 21 February 2027 by [firm name]. The test identified [X] findings: [Y] Critical, [Z] High, [N] Medium, [M] Low. [All Critical/High findings have been remediated / Risk acceptance signed by CISO for [specific findings]]. The penetration test report and remediation records are filed at: /Phase 5 — Operation/Penetration Tests/ and are accessible via the existing GRC Repository SharePoint link. S2-C002 — A6.3 Awareness Evidence: A monthly awareness completion summary (January 2027) has been exported from the awareness platform and filed at: /Phase 5 — Operation/ISMS-OPS-002/A6.3_Awareness_Completion_Evidence_Jan2027.xlsx. ISMS-OPS-002 has been updated to reference this GRC path for A6.3. Please confirm both conditions are resolved and that Stage 2 can be scheduled. Our preferred Stage 2 window is [dates from Section 7 of ISMS-ST1-005]. Best regards, Meera Iyer ¦ ISMS Manager ¦ MediSync Technologies Pvt. Ltd.