## Governance Structure Chart
ISMS-LDR-003 ¦ ISMS Governance Structure Chart ¦ Project HealthSec — ISO/IEC 27001:2022 ¦ MediSync Technologies Pvt. Ltd. ¦ v1.0 ¦ April 2026 ¦ Owner: Vikram Sundaram, CISO
Classification: Confidential — Internal Use Only ¦ For instructions on how to read this chart, see Tab 2 (Roles & Responsibilities) ¦ Arrows flow from authority to accountability. Dotted lines indicate coordination, not reporting.
BOARD OF DIRECTORS 5 members (incl. 2 independent directors) Ultimate accountability for information security risk
ISMS STEERING COMMITTEE Chair: Ananya Rao (CEO) ¦ Members: CTO · CFO · COO · CISO · Head of Legal · ISMS Manager ¦ Meets quarterly + at each phase gate
| CISO Vikram Sundaram Day-to-day ISMS authority Technical & risk decisions |  |  |  | CTO Ridhima Kapoor Engineering resources Architecture decisions |  | COO / CFO / Legal Farhan Ahmed · Rajesh Menon · Omar Al Mansoori Resources · Budget · Regulatory
| ISMS MANAGER Meera Iyer Programme delivery · Document register Consulting engagement · Reporting |  |  |  | Dept. Heads (8 functions) Control owners in their domain |  | External Consulting Team (Engagement Lead + 5 consultants) Phase 1–10 delivery Stage 1 & 2 facilitation
| DEPT. SECURITY CHAMPIONS (1 per department, ~8 total) Named end of Phase 2 4 hrs/week from Phase 3 Local implementation & evidence |  |  |  | INTERNAL AUDIT LEAD (independent of implementing functions) Phase 6 audit programme Findings and corrective actions |  |  | Certification Body Stage 1 & 2 Audits
ALL STAFF (~430) Bengaluru · Pune · Hyderabad · Dubai Policy compliance · Awareness training Incident reporting
Key: | Board | Steering Committee | Executive / C-suite | ISMS / GRC / Champions | Department owners | External parties | All staff

## Roles & Responsibilities
ISMS-LDR-003 ¦ Roles & Responsibilities Reference ¦ Companion to the Governance Structure Chart
How to read: Each row is one governance role. The "Reports To / Accountable To" column shows the authority relationship. "ISMS Responsibility" is what that role owns within the ISMS — not their full job description.
Tier | Role | Current Holder | ISMS Responsibility | Reports To / Accountable To | ISMS-LDR-005 Ref
1 — Board | Board of Directors | 5 members (2 independent) | Ultimate accountability. Approves material security investments. Receives quarterly Executive Summary Report. Exercises oversight over MediSync's risk profile. | Shareholders / regulatory obligations | R-01
2 — Steering Cmt | ISMS Steering Committee | CEO (Chair) + CISO, CTO, COO, CFO, Head of Legal, ISMS Manager | Quarterly decision-making forum. Approves phase-gate closures, risk above appetite, scope changes, and budget releases. May call out-of-cycle meetings if the critical path is at risk. | Board of Directors | R-02
3 — Executive | Chief Executive Officer (CEO) / Executive Sponsor | Ananya Rao | Owns the Information Security Policy (ISMS-LDR-001). Signs the Management Commitment Statement. Approves gate closures M-08 to M-10. Chairs the ISMS Steering Committee. | Board of Directors | R-03
3 — Executive | Chief Information Security Officer (CISO) | Vikram Sundaram | Day-to-day accountability for the ISMS. Holds veto over any system or process change creating unacceptable security risk. Signs off the risk register, SoA and operational procedures. Reports security posture to the Steering Committee. | CEO / Steering Committee | R-04
3 — Executive | Chief Technology Officer (CTO) / Project Sponsor | Ridhima Kapoor | Releases Engineering capacity to the project. Approves architecture decisions that affect the ISMS scope or shared platform layer. Endorses the scope document. | CEO / Steering Committee | R-05
3 — Executive | Chief Operating Officer (COO) | Farhan Ahmed | Confirms departmental resource availability against ISMS-INI-002 plan. Owns ISMS-SUP-001 Resource Allocation Plan. Confirms Security Champion nominations. | CEO / Steering Committee | R-06
3 — Executive | Chief Financial Officer (CFO) | Rajesh Menon | Controls budget and releases phase-gate consulting tranches against accepted deliverables. Owns the cyber insurance relationship. Confirms budget phasing in ISMS-INI-002. | CEO / Steering Committee | R-07
3 — Executive | Head of Legal & Compliance (UAE) | Omar Al Mansoori | Owns the Legal & Regulatory Register (ISMS-INI-010). Approves all regulatory and contractual mappings across India and UAE. Reviews data processing agreements. Leads the UAE jurisdictional scope. | CEO / Steering Committee | R-08
4 — ISMS / GRC | Head of GRC & Compliance / ISMS Manager | Meera Iyer | Runs programme delivery day-to-day. Owns the document register, project schedule, and consulting engagement. Chairs the weekly working group. Primary point of contact for the certification body from Month 7. Single largest key-person dependency — deputy named in Phase 2. | CISO | R-09
4 — Dept Owners | Head of Cloud Infrastructure | Sana Al Farsi | Owns cloud and network controls. Responsible for the end-to-end DR test (M-05 gate). Leads evidence collection for cloud configuration, backup integrity and network segmentation. | CTO / CISO | R-10
4 — Dept Owners | SOC Manager | Neha Choudhury | Owns security monitoring, detection and incident response. Co-manages SOC with SentinelWatch MSSP. Responsible for rewriting ISMS-OPS-005 and leading the incident response tabletop exercise at M-05. | CISO | R-11
4 — Dept Owners | VP Engineering | Advait Deshmukh | Owns secure SDLC controls and evidence. Confirms that ISMS-OPS-001 SDLC procedure formalises existing Engineering practice rather than replacing it. Releases Engineering time to the Security Champions. | CTO | R-12
4 — Dept Owners | Head of HR | Priya Subramaniam | Owns the Security Awareness Programme (ISMS-SUP-005). Accountable for 95% completion per department by M-04. Manages joiner–mover–leaver process in the context of ISMS access control. | COO | R-13
4 — Dept Owners | Head of Customer Success | Divya Nair | Routes all enterprise customer right-to-audit and security questionnaire requests through the ISMS Manager. Coordinates customer notice for the DR test window. Manages certification status communication to customers. | COO | R-14
4 — Dept Owners | Head of Sales | Karan Bhatia | Enforces the certification claims control — no certification claim beyond what is permitted at each project stage. Briefed at M-02 on what Sales may say. Owns the commercial relationship with the two UAE certification-precondition prospects. | CEO | R-15
4 — Dept Owners | Head of Clinical Integration | Dr. Ahmed Al Balushi | Owns customer-specific integration risk and the ABDM interoperability boundary. Confirms that TELE-PLT and EHR-CORE procedures are consistent with MoHFW standards. | CTO | R-16
4 — Dept Owners | Head of Procurement | Vacant — ISMS Manager holds interim ownership | Owns vendor onboarding and the Supplier Register (ISMS-OPS-004). Tier 1 vendor assessments required by M-05. Appointment required by Month 4 — escalation risk PR-02 in ISMS-INI-002. | COO | R-17
5 — Champions | Department Security Champions | 1 per department — named end of Phase 2 (~8 total) | Local ISMS implementation, evidence collection and awareness follow-through within their department. ~4 hours per week from Phase 3. Attend the monthly Security Champions Forum. Not the security owner for their department — that's the department head. | ISMS Manager (functional) / Dept Head (line) | R-18
5 — Internal Audit | Internal Audit Lead | Drawn from functions independent of implementation | Executes the Phase 6 internal audit programme. Must be independent of the controls being audited — no implementing-function staff. Signs a written independence declaration (ISMS-PEV-003). Produces the Internal Audit Report (ISMS-PEV-005). | ISMS Manager / Steering Committee | R-19
5 — External | External Information Security Consulting Team | Engagement Lead + Lead Consultant + 4 specialists | Produces the majority of Phase 1–3 documentation, facilitates risk workshops, supports Stage 1 and Stage 2 audit preparation. Paid against accepted deliverables at each gate — not elapsed time. | ISMS Manager (day-to-day) | R-20
5 — External | Certification Body | To be selected — Month 7 | Conducts Stage 1 (documentation review) and Stage 2 (implementation audit) and issues the certificate. Independent of MediSync. Selected from accredited bodies under IAF MD1 and ISO 17021-1. | Independent | R-21
6 — All Staff | All employees and contractors | ~430 staff across 4 locations | Read and comply with the Information Security Policy (ISMS-LDR-001). Complete mandatory awareness training. Report suspected incidents immediately to the SOC and their Security Champion. Follow the acceptable-use and access-control rules. | Dept Head (line) / ISMS Manager (policy compliance) | R-22
Key: Arrows on the Chart tab flow from authority to accountability. "Reports To" means who the role is accountable to for ISMS decisions. ISMS-LDR-005 Ref: corresponding entry in the Roles, Responsibilities & Authorities Register.