## Executive Responsibility Matrix
ISMS-LDR-004 ¦ Executive Responsibility Matrix ¦ Project HealthSec — ISO/IEC 27001:2022 ¦ MediSync Technologies Pvt. Ltd.
Owner: Vikram Sundaram, CISO ¦ Version 1.0 ¦ April 2026 ¦ Classification: Confidential — Internal Use Only ¦ RACI key: A = Accountable (owns the outcome) R = Responsible (does the work) C = Consulted I = Informed — = Not involved
Category | ISMS Responsibility Area | CEO Ananya Rao | CISO Vikram Sundaram | CTO Ridhima Kapoor | COO Farhan Ahmed | CFO Rajesh Menon | Head Legal Omar Al M. | ISMS Mgr Meera Iyer | Head HR Priya S. | Head Cloud Sana Al F. | SOC Mgr Neha C. | VP Eng Advait D. | Head CS Divya N.
Governance
Governance | ISMS establishment, maintenance and certification | A | R | C | C | I | I | R | I | I | I | I | I
Governance | ISMS Steering Committee — chair, convene and approve | A: A; R: C; C: C; C: C; I: C; I: C; R: R
Governance | Management review — conduct and document | A: I; R: C; C: I; C: I; I: I; I: I; R: A/R
Governance | Phase gate approvals (M-01 to M-10) | A: A; R: C; C: C; C: C; I: C; I: I; R: R
Governance | ISMS document register — ownership and version control | A: I; R: C; C: I; C: I; I: I; I: I; R: A/R
Risk
Risk | Risk assessment methodology — define and approve | I | A | I | I | I | I | R |  | I | I | I
Risk | Risk register — own and maintain | I | A | I | I | I | I | R |  | C | C | C
Risk | Risk treatment decisions — approve | C | A | I | I | I | I | R |  | C | C | C
Risk | Risk above appetite — escalate and decide | A | R | C | I | I | I | C |  | I | I | I
Risk | Statement of Applicability — sign off | I | A | I | I | I | C | R |  | C | I | C
Policy
Policy | Information Security Policy — own and approve | A | R | I | I | I | C | C | I
Policy | Supporting policies — produce and maintain | I | A | I | I | I | C | R | C | C | C | C
Policy | Policy exceptions — review and approve | I | A | I | I | I | I | R
Policy | Policy breach investigation and outcome | I | A | I | C | I | C | R | C
Operations
Operations | Access control — define procedure and review cadence | I | A | I | I | I | I | R |  | C | C | C
Operations | Cloud infrastructure security — own and evidence | I | C | A | I | I | I | I |  | R | C | C
Operations | Secure SDLC — own and evidence | I | C | A | I | I | I | I |  | I | I | R
Operations | Incident management — own procedure and escalation path | I | A | I | I | I | C | R |  | C | R | I
Operations | Business continuity and DR — own plan and test | I | A | R | C | I | I | R |  | R | I | I
Operations | Vendor / supplier security assessments | I | C | I | A | I | C | R |  | I
Operations | Security monitoring (SIEM / EDR) — own and operate | I | A | C | I | I | I | I |  | C | R | I
Operations | Vulnerability management — own cadence and remediation | I | A | C | I | I | I | I |  | C | R | C
Compliance
Compliance | Legal & Regulatory Register — own and maintain | I | C | I | I | I | A | R
Compliance | DPDP Act obligations — manage and evidence | I | C | I | I | I | A | R
Compliance | UAE PDPL obligations — manage and evidence | I | C | I | I | I | A | R
Compliance | CERT-In 6-hour reporting — execute on incident | I | A | I | I | I | C | C |  |  | R
Compliance | Customer contractual obligations — track and evidence | I | I | I | I | I | A | R |  |  |  |  | C
Compliance | Cyber insurance renewal — own and negotiate | I | C | I | I | A | I | C
People
People | Security awareness programme — own and deliver | I | C | I | C | I | I | C | A
People | Security Champions — nominate and release | I | I | C | A | I | I | C | C
People | Joiner-mover-leaver access controls — execute | I | C | I | C | I | I | C | A | C
People | ISMS training — competence matrix and records | I | C | I | I | I | I | C | A
Commercial
Commercial | Certification claims to prospects — approve what can be said | A | C | I | I | I | R | C |  |  |  |  | C
Commercial | Customer security questionnaires — coordinate and respond | I | C | I | I | I | C | A |  |  |  |  | R
Commercial | Right-to-audit requests — manage and schedule | I | C | I | I | I | C | A |  |  |  |  | R
Commercial | UAE enterprise deal — certification precondition | A | C | I | I | I | C | C |  |  |  |  | C
Programme
Programme | Project budget — approve and release tranches | C | I | I | I | A | I | R
Programme | Consulting engagement — manage day-to-day | I | C | I | I | I | I | A/R
Programme | Certification body — select and manage relationship | I | C | I | I | I | I | A/R
Programme | Resource allocation — confirm departmental availability | I | I | C | A | C | I | R | C
Programme | Scope change — approve | A | C | C | I | I | C | R
Key: | A — Accountable (owns outcome; exactly one per row) | I: R — Responsible (does the work); I: C — Consulted (input before decision); C: I — Informed (told after)

## Decision Authority
ISMS-LDR-004 ¦ Decision Authority Table ¦ Who Approves What in the MediSync ISMS
These are the specific decisions that require named approval. No ISMS decision may be made informally — verbal agreement in a meeting does not constitute a decision under this table.
Ref | Decision | Approving Authority | Escalates To If Disputed | ISMS Document | Notes
D-01 | ISMS project launch and Charter approval | CEO on behalf of Board | Board of Directors | ISMS-INI-001 | One-time decision at programme start. Already executed January 2026.
D-02 | Phase gate closure (M-01 to M-10) | ISMS Steering Committee (Accountable: CEO for M-08 to M-10) | Board (for M-09 / M-10) | ISMS-INI-002 (gate evidence) | Gate is closed only when documentary evidence exists. Verbal confirmation does not close a gate.
D-03 | ISMS scope change — any addition or exclusion | Steering Committee; CEO for new country of operation | CEO / Board | ISMS-INI-011 | Triggers review of asset register, risk register and SoA. Cannot be done in isolation.
D-04 | Re-baselining of milestone dates (any gate slip beyond 15 days) | Steering Committee | CEO | ISMS-INI-002 | Original baseline retained in version history for variance reporting.
D-05 | Risk above appetite — formal risk acceptance | ISMS Steering Committee | CEO | ISMS-PLN-004 / PLN-005 | Verbal or informal risk acceptance is not permitted once the ISMS is operational.
D-06 | Risk appetite and criteria — define and approve | ISMS Steering Committee | Board (for material changes) | ISMS-PLN-002 | Reviewed at each annual management review cycle.
D-07 | Information Security Policy — approve and issue | CEO | Board (for fundamental changes) | ISMS-LDR-001 | CEO signs the policy. CISO owns it day-to-day. Any change requires a version increment and re-publication.
D-08 | Policy exception — grant and time-limit | CISO (above appetite: Steering Committee) | Steering Committee / CEO | ISMS-PLN-009 (Change Mgmt) | No exception is permanent. All exceptions logged and reviewed at annual policy review.
D-09 | Incident severity classification and external notification trigger | CISO (operational); CEO informed for High and above | CEO / Steering Committee | ISMS-OPS-005 | External notification to CERT-In, customers and UAE PDPL authority must follow the timelines in ISMS-INI-010. The CISO cannot waive a regulatory notification.
D-10 | DR test scope and customer notification window | CISO and COO jointly | CEO | ISMS-OPS-007 | Enterprise customers require contractual notice before the DR test window. Customer Success owns outreach.
D-11 | Regulatory obligation — formally accept a gap or defer remediation | Steering Committee on advice of Head of Legal | CEO / Board | ISMS-INI-010 | No regulatory gap may be deferred informally. Deferral must be documented with a rationale and a remediation timeline.
D-12 | Data processing agreement — sign or materially amend | Head of Legal (UAE) and CEO | Board | ISMS-INI-010 (contract annex) | DPAs with customers cover DPDP Act and UAE PDPL obligations simultaneously.
D-13 | What Sales may claim about certification status at each stage | CEO on advice of Head of Legal and ISMS Manager | CEO | ISMS-INI-005 (E-03) | Briefed to Sales at M-02 and updated at each subsequent gate. No certification claim before ISMS-CRT-002 is issued.
D-14 | Certification body — select and contract | ISMS Manager with CISO approval; contract signed by CEO | CEO | ISMS-ST1-001 | Shortlisting starts Month 7. Application due Month 9. Two-to-three month lead time is the most common cause of a slipped certification date.
D-15 | Budget release — consulting tranche at each gate | CFO on gate closure confirmation from ISMS Manager | CEO | ISMS-INI-002 Section 10 | Released against accepted deliverables, not elapsed time. CFO and ISMS Manager must not be the same person approving payment.
D-16 | Internal audit independence declaration — approve audit team | CISO | Steering Committee | ISMS-PEV-003 | Audit team members must not have implemented the controls they are auditing. Written independence declaration required before Phase 6 starts.
D-17 | Deputy ISMS Manager — nominate | CEO on recommendation of CISO | Steering Committee | ISMS-INI-003 (SK-09) | Must be named by end of Phase 2. Key-person risk mitigation for the single largest dependency in the programme.