## Risk Register
ISMS-PLN-004 ¦ Risk Register ¦ Project HealthSec — ISO/IEC 27001:2022 ¦ MediSync Technologies Pvt. Ltd.
Owner: Vikram Sundaram, CISO ¦ Maintained by: Meera Iyer, ISMS Manager ¦ v1.0 ¦ April 2026 ¦ Methodology: ISMS-PLN-001 ¦ Appetite: ISMS-PLN-002 ¦ Classification: Confidential — Internal Use Only
Risk ID | Source | Category | Affected Asset(s) | Threat | Vulnerability | Consequence (CIA impact) | L | I | Inherent Score | Inherent Rating | Existing Controls | Control Effectiveness | Residual Score | Residual Rating | Risk Owner | Treatment Option | Treatment Action / Plan | Due | Status
R-001 | RISK-PRE-01 | Technical | SH-PLAT-004 API-GW; SH-PLAT-001 Entra ID; SH-PLAT-006/007 Data Tiers | Targeted cyberattack or supply-chain compromise of the shared identity or API gateway layer | No dedicated threat model for shared platform layer; no API-GW-specific SIEM alert rules; correlated failure not modelled | Simultaneous breach across all products in the region; all Restricted patient data in scope; CERT-In + DPDP/PDPL notification triggered; enterprise customer termination risk | 4 | 5 | 20 | CRITICAL | MFA via Entra ID (fully effective); NGFW segmentation (fully effective); CrowdStrike EDR (fully effective); TLS at API-GW (fully effective). No unified threat model or API-GW-specific Sentinel rules. | Fully effective | 10 | MED-HIGH | Vikram Sundaram (CISO) | Treat — Reduce | Produce shared-platform threat model; add API-GW-specific Sentinel alert rules; document in ISMS-OPS-001; evidence in ISMS-OPS-002 | M-05 Oct 2026 | Not started
R-002 | RISK-PRE-02 | Human | SH-PLAT-001 Entra ID; CD-004 Financial records; DA-002 Patient PII | Phishing / spear-phishing leading to credential compromise or fraudulent payment instruction | Awareness training limited to Engineering (~140 staff); Finance and Sales have no phishing awareness; near-miss confirmed 2024 (payment instruction) | Account compromise enabling lateral movement to patient data; fraudulent payment; CERT-In reportable incident if credential exfiltration confirmed | 4 | 4 | 16 | HIGH | MFA via Entra ID (fully effective — reduces credential-theft blast radius); CrowdStrike EDR (fully effective). No awareness controls for non-Engineering staff. | Fully effective | 8 | MED-HIGH | Priya Subramaniam (Head of HR) / Neha Choudhury (SOC) | Treat — Reduce | Mandatory phishing awareness all departments; Finance anti-phishing module mandatory; phishing simulation from Phase 4 (ISMS-SUP-005) | M-04 Jul 2026 | Not started
R-003 | RISK-PRE-03 | Technical | SH-PLAT-006 India Data Tier; SH-PLAT-007 UAE Data Tier; all data assets | Cloud misconfiguration exposing patient data to internet or unauthorised internal access | No documented configuration baseline or review cadence; SIEM not monitoring for config drift; near-miss confirmed 2024 (storage bucket — found by review, not monitoring) | Patient data exposed; DPDP Act / UAE PDPL breach notification triggered; regulatory penalty; customer trust damage | 3 | 5 | 15 | HIGH | AWS KMS / Azure Key Vault encryption (fully effective — data encrypted at rest); NGFW segmentation (fully effective — data tier not internet-accessible); Tenable Nessus scanning (in use, not scheduled). | Fully effective | 5 | MEDIUM | Sana Al Farsi (Head of Cloud Infra) | Treat — Reduce | Document cloud config baseline and change review process; add Sentinel config-drift alert rules; document in ISMS-OPS-001; scan evidence in ISMS-OPS-002 | M-05 Oct 2026 | Not started
R-004 | RISK-PRE-04 | Access Control | SH-PLAT-001 Entra ID; DA-001 EHR; DA-002 Patient PII; all Restricted assets | Exploitation of stale access rights on hospital-facing admin accounts to gain unauthorised access to patient records | Last full access review >12 months ago; no consistent quarterly cadence; some departed customer staff may have active accounts | Unauthorised access to patient EHR data; potential insider misuse; DPDP / UAE PDPL breach; CERT-In reportable if data exfiltration confirmed | 4 | 4 | 16 | HIGH | MFA enforced (fully effective — reduces credential theft risk but does not address the authorisation gap; stale accounts with MFA are still stale accounts) | Fully effective | 8 | MED-HIGH | Vikram Sundaram (CISO) | Treat — Reduce | Immediate full access review of all hospital-facing admin accounts; document quarterly review cadence and automate JML triggers; ISMS-OPS-009 | M-05 Oct 2026 | Not started
R-005 | New (asset-based) | Technical | SC-002 CI/CD Pipeline; PR-001 to PR-008 All Products | Supply-chain compromise of the CI/CD pipeline introducing malicious code into a production deployment | SDLC procedure not formally documented; no formal third-party dependency review policy; pipeline secrets in GitHub Actions not governed by a formal secrets management procedure | Malicious code in all eight products at next deployment; data exfiltration or backdoor; existential commercial risk | 2 | 5 | 10 | MED-HIGH | GitHub branch protection and mandatory code review (fully effective); pipeline security scanning (in use, not documented or consistently evidenced). | Fully effective | 5 | MEDIUM | Advait Deshmukh (VP Engineering) | Treat — Reduce | Document SDLC security procedure in ISMS-OPS-001; add automated dependency vulnerability scanning; penetration test before Stage 2; evidence in ISMS-OPS-002 | M-05 Oct 2026 | Not started
R-006 | RISK-PRE-05 | Process | All products; SH-PLAT-008 SIEM; all Restricted data assets | Security incident handled by improvisation instead of the incident response plan, causing delayed containment and notification deadline breach | IR plan predates CERT-In 2022 Rules; no DPDP or UAE PDPL notification paths documented; plan never tested; both 2024 incidents handled by Engineering improvisation | Delayed containment; CERT-In 6-hour deadline missed; customer breach notification SLAs breached (contractual penalty); regulatory exposure | 3 | 4 | 12 | HIGH | CrowdStrike EDR detection (fully effective); SentinelWatch co-management (capability exists but escalation procedure undocumented). IR plan is not effective — out of date and untested. | Not effective | 12 | HIGH | Neha Choudhury (SOC Manager) | Treat — Reduce | Rewrite ISMS-OPS-005 with all three notification tracks (CERT-In, DPDP customer, UAE PDPL); tabletop exercise before M-05 including phishing scenario; evidence in ISMS-OPS-002 | M-05 Oct 2026 | Not started
R-007 | RISK-PRE-06 | Business Cont. | SH-PLAT-011/012 Backup archives; SH-PLAT-006/007 Data Tiers | Extended outage or data loss following infrastructure failure or ransomware where RTO exceeds customer SLA commitments | DR never tested; actual RTO unknown; no documented RTO/RPO targets; backup integrity unverified through a live test; 14 enterprise customers have dedicated infrastructure | Data loss or extended unavailability; enterprise SLA breach; DPDP/PDPL breach if data unrecoverable; hospital operations affected at customer sites | 2 | 5 | 10 | MED-HIGH | Regional backups operational and encrypted (fully effective — backups running and regionally appropriate); VaultArchive DR partnership (not tested; VaultArchive unassessed). | Fully effective | 5 | MEDIUM | Sana Al Farsi (Head of Cloud Infra) | Treat — Reduce | Produce ISMS-OPS-007 BCDR Plan; end-to-end DR test including ransomware scenario; issue customer notice to 14 enterprise customers by Month 7; document RTO/RPO; evidence in ISMS-OPS-002 | M-05 Oct 2026 | Not started
R-008 | RISK-PRE-07 | Third-Party | SH-PLAT-011/012 Backup Archives; TP-002 VaultArchive DR Services | VaultArchive DR Services breach or insider incident exposing MediSync customer backup archives | VaultArchive never formally security-assessed; holds encrypted backup archives for both regions; most privileged external access of any third party; no formal security schedule in contract | Backup archive exposure; potential decryption if key management compromised; CERT-In reportable; customer notification; loss of DR capability during incident | 3 | 4 | 12 | HIGH | Archives encrypted via AWS KMS and Azure Key Vault (fully effective — data encrypted at rest in VaultArchive). No other mitigating controls against VaultArchive-side breach. | Fully effective | 4 | MEDIUM | ISMS Manager (interim — Procurement vacant) | Treat — Reduce | Formal Tier 1 vendor security assessment of VaultArchive before M-05; include security schedule in contract; confirm backup immutability; evidence in ISMS-OPS-003 | M-05 Oct 2026 | Not started
R-009 | RISK-PRE-08 | Compliance | All in-scope assets; ISMS-INI-010 Legal Register | Regulatory non-compliance with DPDP Act, CERT-In Rules 2022 or UAE PDPL identified during a customer audit or regulatory inspection | 8 of 22 customer DPA reviews still outstanding; CERT-In 6-hour path not documented in any procedure; ABDM scope not fully mapped; per-contract UAE healthcare obligations partially mapped | Regulatory enforcement action; financial penalty; mandatory remediation under regulatory supervision; customer loss if gap disclosed | 3 | 4 | 12 | HIGH | ISMS-INI-010 Legal Register established (partially effective — register complete but gap actions in progress); DPO assessment complete (fully effective for that obligation). | Partially effective | 8 | MED-HIGH | Omar Al Mansoori (Head of Legal) | Treat — Reduce | Complete 8 outstanding DPA reviews by 30 Apr 2026; document CERT-In path in ISMS-OPS-005 by M-05; confirm ABDM scope in ISMS-INI-011; maintain ISMS-INI-010 as live document | M-05 Oct 2026 (CERT-In); 30 Apr 2026 (DPAs) | In progress
R-010 | New (asset-based) | Third-Party | SH-PLAT-008 Sentinel SIEM; TP-001 SentinelWatch MSSP | SentinelWatch MSSP insider incident or breach giving unauthorised access to SIEM data and incident response workflows | MSSP operates under commercial agreement with no formal security schedule; access scope not documented; MSSP staff have read access to all SIEM data and alert configurations | SIEM data exfiltrated; incident response playbooks exposed; attack intelligence harvested; potential lateral movement if MSSP access is broader than assumed | 2 | 4 | 8 | MED-HIGH | MFA assumed but not confirmed as a formal MSSP requirement; MSSP industry certifications (third-party assurance, not a MediSync control). No formal security schedule. | Partially effective | 4 | MEDIUM | Neha Choudhury (SOC Manager) | Treat — Reduce | Formal Tier 1 vendor assessment of SentinelWatch; include security schedule defining access scope in contract; evidence in ISMS-OPS-003 | M-05 Oct 2026 | Not started
R-011 | New (asset-based) | Technical | SH-PLAT-015 Kubernetes; all products | Container or Kubernetes misconfiguration enabling privilege escalation or cross-container data access | Kubernetes config never formally reviewed against a security baseline; no documented hardening standard; secrets management in containerised environment relies on developer practice | Cross-product data access within cluster; privilege escalation to underlying infrastructure; unauthorised image deployment | 3 | 3 | 9 | MED-HIGH | NGFW network segmentation (fully effective); container registry access via GitHub permissions (partially effective). | Partially effective | 6 | MEDIUM | Sana Al Farsi (Head of Cloud Infra) | Treat — Reduce | Kubernetes security baseline review; document hardening standard in ISMS-OPS-001; confirm secrets management; evidence in ISMS-OPS-002 | M-05 Oct 2026 | Not started
R-012 | New (asset-based) | Technical | SH-PLAT-003 API Keys; SC-001 GitHub; SC-002 CI/CD | API key or secret credential leakage via GitHub repositories, CI/CD pipeline logs or developer error | No formal secrets management procedure; no documented rotation schedule; pipeline logs may contain secrets if developer error occurs | API key exposure enabling impersonation of legitimate services; access to data tier or external integrations | 3 | 4 | 12 | HIGH | Azure Key Vault and AWS Secrets Manager for production secrets (fully effective); GitHub branch protection (fully effective). No secret scanning documented on repositories. | Fully effective | 4 | MEDIUM | Advait Deshmukh (VP Engineering) | Treat — Reduce | Document secrets management procedure in ISMS-OPS-001; enable automated secret scanning on all GitHub repositories; add key rotation schedule to ISMS-OPS-001 | M-05 Oct 2026 | Not started
R-013 | RISK-PRE-09 | Human | All corporate systems; CD-004 Financial records | Social engineering or pretexting attack succeeding against non-Engineering staff due to absence of awareness training | Awareness training for Engineering only; Finance targeted in 2024 payment near-miss; Sales and Customer Success handle customer data without awareness training; no phishing simulation | Credential compromise or fraudulent data disclosure; payment fraud; customer data inadvertently disclosed | 3 | 3 | 9 | MED-HIGH | MFA (fully effective — reduces credential-theft impact). No phishing simulation or awareness controls for the at-risk non-Engineering population. | Fully effective | 3 | LOW | Priya Subramaniam (Head of HR) | Treat — Reduce | Mandatory all-staff awareness programme including phishing simulation by M-04; Finance anti-phishing mandatory; 95% completion tracked per department; evidence in ISMS-SUP-006 | M-04 Jul 2026 | Not started
R-014 | New (asset-based) | Process | SH-PLAT-008 Sentinel SIEM; SH-PLAT-009 CrowdStrike EDR | Security monitoring gap — threat goes undetected due to undocumented alert rules, coverage gaps or alert fatigue in the co-managed SOC | SIEM alert rules not documented or reviewed against a defined coverage standard; EDR configured but alert triage procedure not documented; SOC escalation path is informal | Breach or lateral movement goes undetected; CERT-In reporting delayed; evidence quality compromised for post-incident forensics | 3 | 3 | 9 | MED-HIGH | CrowdStrike EDR deployed and operational (fully effective — detection capability exists); SentinelWatch 24/7 co-management (capability exists but procedure informal). | Fully effective | 3 | LOW | Neha Choudhury (SOC Manager) | Treat — Reduce | Document SOC procedures and alert rules in ISMS-OPS-001; define alert coverage standard in ISMS-PEV-001; evidence in ISMS-OPS-002 | M-05 Oct 2026 | Not started
R-015 | New (asset-based) | Business Cont. | All products; DA-001 to DA-005 Clinical data | Ransomware attack encrypting production data and backups causing extended outage and potential data loss | Backup immutability not verified; end-to-end recovery from ransomware not tested; RTO unknown; SOC containment speed depends on undocumented procedures | Complete production unavailability; data potentially unrecoverable; enterprise SLA breach; hospital operations affected; existential commercial risk | 3 | 5 | 15 | HIGH | CrowdStrike EDR (fully effective — ransomware detection); regional backups operational (partially effective — backups exist but not verified as immutable or tested for ransomware recovery). | Partially effective | 10 | MED-HIGH | Sana Al Farsi (Head of Cloud Infra) | Treat — Reduce | Verify backup immutability configuration; include ransomware scenario in DR test at M-05; document recovery runbook in ISMS-OPS-007; evidence in ISMS-OPS-002 | M-05 Oct 2026 | Not started
R-016 | New (asset-based) | Physical | PH-001 to PH-004 All offices; PH-005 Corporate endpoints | Tailgating or physical intrusion into a MediSync office leading to device theft, system access or physical media compromise | Physical controls (access card, CCTV) in place but not formally documented; clean-desk and screen-lock policies not written or distributed; visitor management not procedurally governed | Stolen device potentially enabling system access; physical access to unattended screens or printed materials | 2 | 3 | 6 | MEDIUM | Access card control and CCTV (partially effective — controls exist but undocumented); MDM enrolment (fully effective — lost device can be remotely wiped); full-disk encryption on laptops (fully effective). | Partially effective | 3 | LOW | IT Operations Lead | Treat — Reduce | Document clean-desk, screen-lock and visitor management procedures in ISMS-OPS-001; distribute and acknowledge across all four offices | M-05 Oct 2026 | Not started
R-017 | New (asset-based) | Human | All corporate systems; SH-PLAT-001 Entra ID | Shadow IT — staff using unsanctioned cloud tools or personal email to transfer or store MediSync data outside the ISMS boundary | No formal sanctioned-tools policy enforcement; rapid growth has normalised ad-hoc tool adoption; Sales and Customer Success most affected; no DLP tooling | Customer or patient data shared via unsanctioned channel; data leaves ISMS scope undetected; DPDP/PDPL breach if patient data involved | 3 | 3 | 9 | MED-HIGH | GlobalProtect VPN enforcing network-level controls for remote access (partially effective); MDM managed devices (partially effective — limits personal app installation). No web DLP. | Partially effective | 6 | MEDIUM | Vikram Sundaram (CISO) | Treat — Reduce | Acceptable-use policy in ISMS-LDR-001 (done); enforce via awareness in ISMS-SUP-005; DLP assessment in Phase 5 if residual risk remains HIGH after awareness programme | M-04 Jul 2026 (awareness); M-05 (DLP assessment) | Not started
R-018 | RISK-PRE-10 | Commercial | Commercial pipeline; UAE enterprise accounts | Continued inability to respond to enterprise security questionnaires within acceptable timelines causing lost or delayed deals | No certification evidence package; questionnaire responses reconstructed ad hoc per deal (2–4 weeks average); two UAE deals stalled | Revenue loss from deals requiring certification; competitive disadvantage; continued overhead on Sales and Customer Success | 4 | 2 | 8 | MED-HIGH | ISMS programme underway (partially effective — project launched, no certification artefacts yet); certification claims control in place (fully effective — prevents premature claims). | Partially effective | 6 | MEDIUM | Karan Bhatia (Head of Sales) / Meera Iyer (ISMS Manager) | Treat — Reduce | Maintain certification timeline (M-10 Apr 2027); Sales briefed per ISMS-INI-005 E-03; interim questionnaire response package produced from current ISMS documentation | M-10 Apr 2027 (certification); ongoing (questionnaires) | In progress
R-019 | New (asset-based) | Third-Party | TP-004 PulseMail; TP-005 PayBridge; TP-006 TrustID | Tier 2/3 vendor breach exposing patient contact details, tokenised payment references or UAE identity verification data | PulseMail, PayBridge and TrustID not yet formally assessed or tiered; vendor security posture unknown; no contractual security requirements confirmed | Patient contact data exposed (PulseMail); payment reference data exposed (PayBridge — DPDP reportable); UAE identity data exposed (TrustID — UAE PDPL) | 2 | 3 | 6 | MEDIUM | Tokenisation at PayBridge (fully effective — full card data not held). No other documented controls for PulseMail or TrustID. | Fully effective | 3 | LOW | ISMS Manager (interim) | Treat — Reduce | Tier and assess PulseMail, PayBridge and TrustID under ISMS-OPS-003; confirm contractual security requirements; evidence in ISMS-OPS-004 | M-05 Oct 2026 | Not started
R-020 | New (asset-based) | Access Control | CD-002 Employee Records; SH-PLAT-001 Entra ID; all production systems | Joiner-mover-leaver process failure leaving active accounts for departed staff or incorrect access for role-changers | JML process exists but not formally documented; no confirmed same-day access revocation SLA; access change cadence for role movers not formalised | Departed staff retaining access to production and patient data; DPDP/PDPL exposure if access is exploited | 2 | 4 | 8 | MED-HIGH | Entra ID centralised access management (fully effective — single source of truth); HR notification to IT Operations on departure (process exists but timing not formalised). | Fully effective | 4 | MEDIUM | Priya Subramaniam (Head of HR) | Treat — Reduce | Document JML procedure in ISMS-OPS-009; confirm same-day revocation SLA; evidence access log in ISMS-OPS-009 | M-05 Oct 2026 | Not started
Rating key: CRITICAL (20–25) ¦ HIGH (12–19) ¦ MED-HIGH (8–11) ¦ MEDIUM (4–7) ¦ LOW (1–3) ¦ L=Likelihood(1–5) I=Impact(1–5) ¦ Methodology: ISMS-PLN-001 ¦ Appetite: ISMS-PLN-002

## Risk Summary
ISMS-PLN-004 ¦ Risk Summary Dashboard ¦ As at April 2026 ¦ MediSync Technologies Pvt. Ltd.
CISO review: Vikram Sundaram ¦ Last updated: April 2026 ¦ Next update: monthly
Residual Rating | Count | Required Action
HIGH | 1 | Treatment plan within 90 days
MED-HIGH | 5 | 120 days
MEDIUM | 10 | 12-month cycle
LOW | 4 | Monitor annually
Risks above appetite (Steering Committee visibility required per ISMS-PLN-002):
Risk ID | Residual Rating | Risk Description (summary) | Owner | Due | Status
R-001 | MED-HIGH | Targeted cyberattack or supply-chain compromise of the … | Vikram Sundaram (CISO) | M-05 Oct 2026 | Not started
R-002 | MED-HIGH | Phishing / spear-phishing leading to credential comprom… | Priya Subramaniam (Head of HR) / Neha Choudhury (SOC) | M-04 Jul 2026 | Not started
R-004 | MED-HIGH | Exploitation of stale access rights on hospital-facing … | Vikram Sundaram (CISO) | M-05 Oct 2026 | Not started
R-006 | HIGH | Security incident handled by improvisation instead of t… | Neha Choudhury (SOC Manager) | M-05 Oct 2026 | Not started
R-009 | MED-HIGH | Regulatory non-compliance with DPDP Act, CERT-In Rules … | Omar Al Mansoori (Head of Legal) | M-05 Oct 2026 (CERT-In); 30 Apr 2026 (DPAs) | In progress
R-015 | MED-HIGH | Ransomware attack encrypting production data and backup… | Sana Al Farsi (Head of Cloud Infra) | M-05 Oct 2026 | Not started

## Risk Acceptance Log
ISMS-PLN-004 ¦ Risk Acceptance Log ¦ All formally accepted risks — per ISMS-PLN-002 Section 3
A risk is only accepted when ALL conditions in ISMS-PLN-002 Section 3 are met. No verbal or informal acceptance is valid.
Risk ID | Residual Rating | Risk Description | Acceptance Date | Risk Owner (signed) | Rationale | CISO Review | Steering Cmt (if req'd) | Expires | Renewed?
No risks formally accepted at baseline (April 2026). All risks above appetite are in treatment. Populate as acceptances are granted per ISMS-PLN-002 Section 3.

## Change Log
ISMS-PLN-004 ¦ Risk Register Change Log ¦ Record of all risk additions, closures and rescores
Updated by ISMS Manager within 5 business days of any change. Reviewed at each quarterly Steering Committee.
Change Ref | Date | Risk ID | Change Type | Previous State | New State | Changed By
CL-001 | Apr 2026 | R-001 to R-020 | Initial population | No risk register existed | 20 risks identified, scored and registered at v1.0 | Consulting Team / Meera Iyer
CL-002 | Apr 2026 | RISK-PRE-01 to 10 | Formalised from preliminary register | Preliminary ratings in ISMS-INI-006 (unscored) | Formally scored per ISMS-PLN-001 methodology | Vikram Sundaram / Consulting Team
CL-XXX | DD MMM YYYY | R-XXX | [Type] | [Previous] | [New] | [Name]