## Treatment Plan
ISMS-PLN-005 ¦ Risk Treatment Plan ¦ Project HealthSec — ISO/IEC 27001:2022 ¦ MediSync Technologies Pvt. Ltd.
Owner: Vikram Sundaram, CISO ¦ Maintained by: Meera Iyer, ISMS Manager ¦ v1.0 ¦ April 2026 ¦ Source: ISMS-PLN-004 Risk Register ¦ Appetite: ISMS-PLN-002 ¦ Classification: Confidential — Internal Use Only
Risk ID | Residual Rating | Treatment Option | Treatment Priority | Treatment Action | Specific Controls / Deliverables | Implementation Detail | Risk Owner | Action Owner | Target Date | ISMS Document | Approver | Budget Required | Status
1 — IMMEDIATE (HIGH residual — above appetite)
R-006 | HIGH | Treat — Reduce | 1 — Immediate | Rewrite incident response procedure with all three notification tracks; conduct tabletop exercise | ISMS-OPS-005 (rewritten); Tabletop exercise record; CERT-In notification path documented; DPDP customer notification path; UAE PDPL path | New ISMS-OPS-005 must include: (1) CERT-In 6-hour reporting track as a separate procedure step with named executor; (2) DPDP customer notification timeline (per contract SLA); (3) UAE PDPL supervisory authority path. Tabletop must include a phishing-based scenario. Exercise facilitator: Consulting Team. Exercise record stored in GRC Repository. | Neha Choudhury (SOC Manager) | Neha Choudhury + Consulting Team | M-05 Oct 2026 | ISMS-OPS-005 | Vikram Sundaram (CISO) | Within consulting scope | Not started
2 — 120 DAYS (MED-HIGH residual — above appetite)
R-001 | MED-HIGH | Treat — Reduce | 2 — 120 days | Produce dedicated shared-platform threat model; add API-GW-specific Sentinel alert rules | Threat model document (shared platform layer); API-GW Sentinel alert rules; ISMS-OPS-001 procedure; ISMS-OPS-002 evidence | Threat model must cover: identity layer (Entra ID), API-GW, data tier (India + UAE), backup infrastructure, logging stack. Risk scenarios drawn from ISMS-INI-008 threat landscape. Sentinel rules to cover: unusual API-GW traffic volume, authentication anomalies, cross-region data flows, privilege escalation signals. Rules reviewed against a defined coverage standard in ISMS-PEV-001. | Vikram Sundaram (CISO) | Sana Al Farsi + Neha Choudhury + Consulting Team | M-05 Oct 2026 | ISMS-OPS-001; ISMS-OPS-002 | Vikram Sundaram (CISO) | Within consulting scope | Not started
R-002 | MED-HIGH | Treat — Reduce | 2 — 120 days | Launch mandatory all-staff security awareness programme including phishing simulation | ISMS-SUP-005 (Awareness Programme Plan); ISMS-SUP-006 (Attendance/Completion Records); Phishing simulation records; Finance anti-phishing module | Awareness programme must cover all ~430 staff across all four locations. Finance and Customer Success to receive a dedicated anti-phishing module given the 2024 near-miss. Phishing simulation to be conducted within 60 days of programme launch, with results feeding into follow-up training. Dubai team covered via UAE-hours session (Omar Al Mansoori). Department completion rates reported to Steering Committee monthly. | Priya Subramaniam (Head of HR) | Priya Subramaniam + Security Champions | M-04 Jul 2026 | ISMS-SUP-005; ISMS-SUP-006 | Vikram Sundaram (CISO) | ₹6,00,000 (training programme budget — ISMS-INI-001 Section 9) | Not started
R-004 | MED-HIGH | Treat — Reduce | 2 — 120 days | Conduct full access review of hospital-facing admin accounts; formalise quarterly review cadence | Access review log (ISMS-OPS-009); quarterly review schedule; JML procedure update; evidence in ISMS-OPS-002 | Immediate full access review to be completed before other Phase 5 controls. Review must cover all accounts with admin-level access to any hospital-facing system or interface. Accounts for departed customer staff to be revoked same day. Quarterly review schedule to be documented and automated where possible using Entra ID access review features. JML trigger for customer-side account changes confirmed with Customer Success. | Vikram Sundaram (CISO) | IT Operations Lead + Vikram Sundaram | M-05 Oct 2026 | ISMS-OPS-009; ISMS-OPS-002 | Vikram Sundaram (CISO) | Within internal resource scope | Not started
R-009 | MED-HIGH | Treat — Reduce | 2 — 120 days | Complete outstanding DPA reviews; document CERT-In notification path; finalise ABDM scope mapping | ISMS-INI-010 (updated); 22 customer DPAs reviewed; CERT-In path in ISMS-OPS-005; ABDM scope confirmed in ISMS-INI-011 | OA-02 from LDR-009 Leadership Meeting: 8 DPAs still outstanding — all to be completed by 30 April 2026. CERT-In notification path to be added to ISMS-OPS-005 as a separately tracked procedure step (distinct from DPDP and UAE PDPL paths). ABDM scope — Head of Clinical Integration to confirm which products connect to ABDM ecosystem and document in ISMS-INI-011. | Omar Al Mansoori (Head of Legal) | Omar Al Mansoori + Dr. Ahmed Al Balushi (ABDM) | 30 Apr 2026 (DPAs); M-05 Oct 2026 (CERT-In path) | ISMS-INI-010; ISMS-OPS-005; ISMS-INI-011 | Vikram Sundaram (CISO) | Within internal resource scope | In progress
R-015 | MED-HIGH | Treat — Reduce | 2 — 120 days | Verify backup immutability; include ransomware recovery scenario in DR test; document recovery runbook | ISMS-OPS-007 (BCDR Plan with ransomware scenario); backup immutability configuration evidence; DR test record; recovery runbook | Backup immutability verification: confirm AWS S3 Object Lock (India) and Azure Immutable Blob Storage (UAE) are configured and tested. DR test must simulate a ransomware encryption event and demonstrate clean recovery from an unaffected immutable backup. Recovery time must be recorded as the baseline RTO. Customer notice for 14 enterprise customers must go out by Month 7 (ISMS-INI-002). VaultArchive cooperation confirmed before test is scheduled. | Sana Al Farsi (Head of Cloud Infra) | Sana Al Farsi + VaultArchive + Consulting Team | M-05 Oct 2026 | ISMS-OPS-007; ISMS-OPS-002 | Vikram Sundaram (CISO) | Within consulting scope | Not started
3 — 12-MONTH CYCLE (MEDIUM residual — within appetite but requiring treatment)
R-003 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Document cloud configuration baseline; add config-drift Sentinel alert rules; formalise Nessus scanning cadence | Cloud config baseline document; Sentinel config-drift alert rules; vulnerability scanning schedule in ISMS-OPS-001; evidence in ISMS-OPS-002 | Config baseline to cover: AWS ap-south-1 and Azure UAE North — network ACLs, storage bucket access policies, IAM permission boundaries, Kubernetes RBAC settings. Nessus scanning: document schedule (minimum monthly for production, weekly for critical shared-platform components). Config-drift alerts in Sentinel: trigger on any change to storage access policies, IAM roles or security group rules. | Sana Al Farsi (Head of Cloud Infra) | Sana Al Farsi + Consulting Team | M-05 Oct 2026 | ISMS-OPS-001; ISMS-OPS-002 | Vikram Sundaram (CISO) | Within consulting scope | Not started
R-005 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Document SDLC security procedure; add automated dependency vulnerability scanning; confirm secrets management | ISMS-OPS-001 SDLC section; automated dep scanning in CI/CD; secrets scanning on all GitHub repos; evidence in ISMS-OPS-002; penetration test before Stage 2 | SDLC procedure must document: branch protection rules, mandatory code review requirements, security scanning steps in pipeline, secret scanning configuration, dependency vulnerability scanning tooling. GitHub secret scanning to be enabled on all repositories. Penetration test scope and provider to be agreed with CISO before Stage 2 (Month 12). Formalise pipeline secrets as a policy: all secrets via Key Vault / Secrets Manager, no hardcoded values, rotation schedule documented. | Advait Deshmukh (VP Engineering) | Advait Deshmukh + DevSecOps Lead | M-05 Oct 2026 | ISMS-OPS-001; ISMS-OPS-002 | Vikram Sundaram (CISO) | Within internal resource scope | Not started
R-007 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Produce BCDR Plan; conduct end-to-end DR test; establish documented RTO/RPO targets | ISMS-OPS-007 (BCDR Plan); end-to-end DR test record; RTO/RPO targets; customer notice issued | BCDR Plan must cover: failure scenarios (infrastructure failure, ransomware — see R-015, sustained regional outage); recovery procedures for India and UAE regions; roles and responsibilities during a DR event; customer communication plan; RTO/RPO targets per service tier. DR test must be end-to-end — not a backup restore test. 14 enterprise customers with dedicated infrastructure require advance notice (Month 7). VaultArchive assessment (R-008) must be completed before the DR test is scheduled. | Sana Al Farsi (Head of Cloud Infra) | Sana Al Farsi + Consulting Team | M-05 Oct 2026 | ISMS-OPS-007; ISMS-OPS-002 | Vikram Sundaram (CISO) | Within consulting scope | Not started
R-008 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Formal Tier 1 vendor security assessment of VaultArchive; add security schedule to contract; confirm backup immutability | VaultArchive security assessment report (ISMS-OPS-003); security schedule in contract; backup immutability confirmation; evidence in ISMS-OPS-002 | VaultArchive assessment: conduct against MediSync's Tier 1 vendor assessment framework once ISMS-OPS-003 is drafted. Assessment must cover: physical security, access control, incident response capability, sub-processor chain, encryption key handling, and their own security certifications. Security schedule to be added to the existing VaultArchive contract before the DR test (R-007) is executed — VaultArchive cooperation in the DR test must not proceed without a formal security schedule in place. | ISMS Manager (interim — Procurement vacant) | Meera Iyer + Legal (contract amendment) | M-05 Oct 2026 | ISMS-OPS-003; ISMS-OPS-004 | CISO (assessment); CEO (contract amendment) | Within consulting scope | Not started
R-010 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Formal Tier 1 vendor assessment of SentinelWatch; include security schedule defining MSSP access scope in contract | SentinelWatch assessment report (ISMS-OPS-003); security schedule in contract; access scope documented; evidence in ISMS-OPS-002 | SentinelWatch assessment must cover: staff vetting process, privileged access controls, their own SOC security, incident response for MSSP-side breach, and confirmation of MFA requirement for all MSSP staff accessing MediSync SIEM. Security schedule must define: exact scope of SIEM data accessible to MSSP, audit log of MSSP actions, requirement for MFA, and breach notification obligation from MSSP to MediSync. | Neha Choudhury (SOC Manager) | Neha Choudhury + Meera Iyer | M-05 Oct 2026 | ISMS-OPS-003 | Vikram Sundaram (CISO) | Within consulting scope | Not started
R-011 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Kubernetes security baseline review; document hardening standard; confirm secrets management in containerised environment | Kubernetes hardening baseline document; secrets management procedure in ISMS-OPS-001; evidence in ISMS-OPS-002 | Hardening standard to cover: RBAC configuration, pod security policies, network policies, image signing and registry trust, secrets injection via Key Vault / Secrets Manager (no environment variables for secrets). Review to be conducted by Cloud Infrastructure and DevSecOps jointly. Reference CIS Kubernetes Benchmark and AWS/Azure managed Kubernetes security baselines. | Sana Al Farsi (Head of Cloud Infra) | Sana Al Farsi + DevSecOps Lead | M-05 Oct 2026 | ISMS-OPS-001; ISMS-OPS-002 | Vikram Sundaram (CISO) | Within internal resource scope | Not started
R-012 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Document secrets management procedure; enable automated secret scanning on all GitHub repos; add key rotation schedule | Secrets management procedure in ISMS-OPS-001; GitHub secret scanning enabled; rotation schedule; evidence in ISMS-OPS-002 | Enable GitHub Advanced Security secret scanning across all eight product repositories and shared library repositories. Procedure to document: approved secret storage locations (Key Vault / Secrets Manager only), prohibited patterns (hardcoded credentials, environment variables for secrets in production), rotation frequency per secret type (API keys: 90 days; service account tokens: 180 days; DB passwords: 90 days), and the process for rotating a compromised secret under an incident scenario. | Advait Deshmukh (VP Engineering) | Advait Deshmukh + DevSecOps Lead | M-05 Oct 2026 | ISMS-OPS-001; ISMS-OPS-002 | Vikram Sundaram (CISO) | Within internal resource scope | Not started
R-013 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Mandatory all-staff awareness programme with phishing simulation — specifically covering non-Engineering departments | ISMS-SUP-005; ISMS-SUP-006; phishing simulation records; Finance anti-phishing module completion records | Covered by the same treatment as R-002 — same awareness programme, same completion target (95% per department by M-04). Finance-specific anti-phishing content addresses the 2024 near-miss directly. Phishing simulation results segmented by department so non-Engineering completion and susceptibility rates are visible separately. | Priya Subramaniam (Head of HR) | Priya Subramaniam + Security Champions | M-04 Jul 2026 | ISMS-SUP-005; ISMS-SUP-006 | Vikram Sundaram (CISO) | Covered under R-002 budget | Not started
R-014 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Document SOC procedures and alert rules; define SIEM alert coverage standard in ISMS-PEV-001 | SOC procedures in ISMS-OPS-001; alert rules documented; ISMS-PEV-001 coverage standard; evidence in ISMS-OPS-002 | SOC procedures to document: alert triage process, escalation path from MSSP to internal SOC to CISO, severity classification thresholds, initial containment actions by severity, and handover from detection to incident response procedure (ISMS-OPS-005). Alert coverage standard in ISMS-PEV-001 to define minimum required coverage: authentication anomalies, privilege escalation, config drift, data exfiltration patterns, API-GW anomalies, ransomware indicators. | Neha Choudhury (SOC Manager) | Neha Choudhury + Consulting Team | M-05 Oct 2026 | ISMS-OPS-001; ISMS-PEV-001; ISMS-OPS-002 | Vikram Sundaram (CISO) | Within consulting scope | Not started
R-016 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Document office physical security procedures across all four locations | Physical security procedures in ISMS-OPS-001; clean-desk and screen-lock policies; visitor management procedure; acknowledged by all staff | Procedures to cover: clean-desk policy (no Restricted or Confidential materials left on desk when unattended), screen-lock enforcement (5-minute idle timeout, confirmed via MDM policy), visitor management (pre-registration, badge, escort at all times in production-adjacent areas, log signed). To be distributed across all four locations and included in the awareness programme. Dubai office: coordinated by Omar Al Mansoori. | IT Operations Lead | IT Operations Lead + Security Champions | M-05 Oct 2026 | ISMS-OPS-001 | Vikram Sundaram (CISO) | Within internal resource scope | Not started
R-017 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Enforce acceptable-use policy via awareness programme; conduct DLP assessment in Phase 5 | ISMS-LDR-001 acceptable-use section (in force); ISMS-SUP-005 awareness module on sanctioned tools; DLP assessment report (Phase 5) | Acceptable-use policy already published in ISMS-LDR-001 Section 5.7. Awareness programme to include a specific module on approved tools and the risk of personal email / messaging apps for business data. DLP assessment in Phase 5: evaluate whether residual risk warrants DLP tooling investment — if awareness programme reduces the risk to LOW, DLP investment may not be required. Assessment to be completed before M-05 and documented. | Vikram Sundaram (CISO) | Vikram Sundaram + Priya Subramaniam | M-04 Jul 2026 (awareness); M-05 Oct 2026 (DLP assessment) | ISMS-OPS-001; ISMS-SUP-005 | Vikram Sundaram (CISO) | Within internal resource scope (assessment only) | Not started
R-018 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Maintain certification timeline; produce interim questionnaire response package from current ISMS documentation | Certification at M-10 (Apr 2027); interim questionnaire response pack; Sales briefing record | Interim questionnaire response package: compile from approved Phase 1 and 2 documents (Charter, Policy, Context Analysis, Gap Assessment, Governance structure) to produce a "ISMS in implementation" evidence pack that Sales and Customer Success can use for RFP responses before certification. Sales briefed per ISMS-INI-005 E-03 on what may be stated at each stage. Package updated at each phase gate as new documents are approved. | Karan Bhatia (Head of Sales) | Meera Iyer + Karan Bhatia | M-10 Apr 2027 (certification); Apr 2026 (interim pack) | ISMS-CRT-002 (certificate); interim pack from current docs | CEO (certification); ISMS Manager (interim pack) | Within programme budget | In progress
R-019 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Tier and formally assess PulseMail, PayBridge and TrustID; confirm contractual security requirements | Vendor assessment reports (ISMS-OPS-003); Supplier Register entries (ISMS-OPS-004); contractual security requirements confirmed | Assess against MediSync Tier 2/3 vendor assessment framework. PayBridge: confirm PCI-DSS certification and scope; confirm tokenisation is end-to-end. PulseMail: assess data handling of patient contact details; confirm retention and deletion obligations. TrustID: assess UAE PDPL compliance; confirm data residency in UAE. All assessments to include contractual security schedule or minimum security requirements clause. | ISMS Manager (interim) | Meera Iyer + Omar Al Mansoori (TrustID / UAE PDPL) | M-05 Oct 2026 | ISMS-OPS-003; ISMS-OPS-004 | Vikram Sundaram (CISO) | Within consulting scope | Not started
R-020 | MEDIUM | Treat — Reduce | 3 — 12-month cycle | Document JML procedure; confirm same-day access revocation SLA; evidence access log | JML procedure in ISMS-OPS-009; same-day revocation SLA confirmed; access review log evidenced in ISMS-OPS-002 | JML procedure to cover: new joiner provisioning timeline (access granted on day 1, not day 5); mover access change (role change confirmed to IT Operations within 24 hours by HR); leaver revocation (IT Operations to confirm revocation within 4 hours of HR departure notification, not end of day). Automate where Entra ID supports it. Customer-side JML: confirm with Customer Success how departed customer staff are notified to MediSync for account revocation. | Priya Subramaniam (Head of HR) | Priya Subramaniam + IT Operations Lead | M-05 Oct 2026 | ISMS-OPS-009; ISMS-OPS-002 | Vikram Sundaram (CISO) | Within internal resource scope | Not started
LOW RESIDUAL — MONITOR (no mandatory treatment; reviewed annually)
No risks scored LOW residual at April 2026 baseline. All identified risks are rated MEDIUM or above and are in the treatment plan above.
Treatment options: Reduce = implement additional controls ¦ Transfer = shift risk to a third party (insurance, contract) ¦ Avoid = discontinue the activity ¦ Accept = formally accept residual risk per ISMS-PLN-002 Section 3 ¦ Status: Not started (red) ¦ In progress (amber) ¦ Complete (green) ¦ Accepted (blue)

## Status Tracker
ISMS-PLN-005 ¦ Treatment Status Tracker ¦ Updated monthly — reviewed at Steering Committee
Red = not started ¦ Amber = in progress ¦ Green = complete ¦ Blue = residual accepted ¦ Update this tab after each weekly working group meeting
Risk ID | Residual Rating | Priority | Action Summary | Action Owner | Target Date | % Complete | Status
R-006 | HIGH | 1 — Immediate | Rewrite ISMS-OPS-005 + tabletop exercise | Neha Choudhury | Oct 2026 | 0% | Not started
R-001 | MED-HIGH | 2 — 120 days | Shared-platform threat model + API-GW Sentinel rules | Sana Al Farsi + Neha Choudhury | Oct 2026 | 0% | Not started
R-002 | MED-HIGH | 2 — 120 days | All-staff awareness programme + phishing simulation | Priya Subramaniam | Jul 2026 | 0% | Not started
R-004 | MED-HIGH | 2 — 120 days | Full access review + quarterly cadence | IT Operations Lead | Oct 2026 | 0% | Not started
R-009 | MED-HIGH | 2 — 120 days | DPA reviews + CERT-In path + ABDM scope | Omar Al Mansoori | Oct 2026 (Apr for DPAs) | 15% | In progress
R-015 | MED-HIGH | 2 — 120 days | Backup immutability verification + ransomware DR scenario | Sana Al Farsi | Oct 2026 | 0% | Not started
R-003 | MEDIUM | 3 — 12-month | Cloud config baseline + Sentinel config-drift rules | Sana Al Farsi | Oct 2026 | 0% | Not started
R-005 | MEDIUM | 3 — 12-month | SDLC procedure + dep scanning + secrets management | Advait Deshmukh | Oct 2026 | 0% | Not started
R-007 | MEDIUM | 3 — 12-month | BCDR Plan + end-to-end DR test | Sana Al Farsi | Oct 2026 | 0% | Not started
R-008 | MEDIUM | 3 — 12-month | VaultArchive Tier 1 vendor assessment + security schedule | Meera Iyer (interim) | Oct 2026 | 0% | Not started
R-010 | MEDIUM | 3 — 12-month | SentinelWatch vendor assessment + security schedule | Neha Choudhury | Oct 2026 | 0% | Not started
R-011 | MEDIUM | 3 — 12-month | Kubernetes security baseline + hardening standard | Sana Al Farsi | Oct 2026 | 0% | Not started
R-012 | MEDIUM | 3 — 12-month | Secrets management procedure + GitHub secret scanning | Advait Deshmukh | Oct 2026 | 0% | Not started
R-013 | MEDIUM | 3 — 12-month | Awareness programme (non-Engineering focus) | Priya Subramaniam | Jul 2026 | 0% | Not started
R-014 | MEDIUM | 3 — 12-month | SOC procedures + alert rules + coverage standard | Neha Choudhury | Oct 2026 | 0% | Not started
R-016 | MEDIUM | 3 — 12-month | Physical security procedures — all four offices | IT Operations Lead | Oct 2026 | 0% | Not started
R-017 | MEDIUM | 3 — 12-month | Awareness — sanctioned tools + DLP assessment | Vikram Sundaram | Oct 2026 | 0% | Not started
R-018 | MEDIUM | 3 — 12-month | Certification timeline + interim questionnaire pack | Meera Iyer | Apr 2027 | 10% | In progress
R-019 | MEDIUM | 3 — 12-month | Tier 2/3 vendor assessments — PulseMail, PayBridge, TrustID | Meera Iyer (interim) | Oct 2026 | 0% | Not started
R-020 | MEDIUM | 3 — 12-month | JML procedure + same-day revocation SLA | Priya Subramaniam | Oct 2026 | 0% | Not started

## Residual Sign-off Log
ISMS-PLN-005 ¦ Residual Risk Sign-off Log ¦ Evidence that treatment is complete and residual risk is accepted
Populate after each treatment action is verified complete. Sign-off constitutes formal acceptance of the post-treatment residual risk. CISO must countersign all entries.
Risk ID | Post-Treatment Residual Rating | Treatment Completed | Evidence Reference | Risk Owner (signed) | CISO (signed) | Steering Cmt (if required) | Date Signed off | Valid Until
No treatments complete at April 2026 baseline. Populate this log as each treatment action in Tab 1 is verified complete per the evidence reference. Tab 3 (Risk Acceptance Log in PLN-004) is the mirror register for formally accepted risks.