## Training Log
ISMS-SUP-004 ¦ Training Records / Training Log ¦ ISO/IEC 27001:2022 Clause 7.2(d) ¦ Project HealthSec ¦ MediSync Technologies Pvt. Ltd.
Owner: Priya Subramaniam, Head of HR ¦ ISMS Owner: Meera Iyer ¦ v1.0 ¦ July 2026 ¦ This log is an audit-controlled document. Every row is a training completion record retained as evidence of competence. ¦ Classification: Confidential — Internal Use Only
Record ID | Training Item (TNA Ref) | Trainee Name | Department | Training Title | Delivery Method | Completion Date | Score / Result | Evidence Reference | Expiry Date (if applicable) | Verified By | Status
TNA-003 — ISMS Policy Acknowledgement (in progress — 30-day window from 1 Apr 2026)
TR-001 | TNA-003 | Ananya Rao | Executive | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 2 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Ananya Rao | Annual review (Apr 2027) | Meera Iyer | Complete
TR-002 | TNA-003 | Vikram Sundaram | GRC / CISO | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 2 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Vikram Sundaram | Annual review (Apr 2027) | Meera Iyer | Complete
TR-003 | TNA-003 | Meera Iyer | GRC | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 2 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Meera Iyer | Annual review (Apr 2027) | Meera Iyer | Complete
TR-004 | TNA-003 | Rohan Sharma | GRC | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 3 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Rohan Sharma | Annual review (Apr 2027) | Meera Iyer | Complete
TR-005 | TNA-003 | Ridhima Kapoor | Engineering | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 3 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Ridhima Kapoor | Annual review (Apr 2027) | Meera Iyer | Complete
TR-006 | TNA-003 | Farhan Ahmed | Executive | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 3 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Farhan Ahmed | Annual review (Apr 2027) | Meera Iyer | Complete
TR-007 | TNA-003 | Rajesh Menon | Finance | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 4 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Rajesh Menon | Annual review (Apr 2027) | Meera Iyer | Complete
TR-008 | TNA-003 | Omar Al Mansoori | Legal | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 4 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Omar Al Mansoori | Annual review (Apr 2027) | Meera Iyer | Complete
TR-009 | TNA-003 | Sana Al Farsi | Cloud & Infra | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 5 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Sana Al Farsi | Annual review (Apr 2027) | Meera Iyer | Complete
TR-010 | TNA-003 | Neha Choudhury | SOC | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 5 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Neha Choudhury | Annual review (Apr 2027) | Meera Iyer | Complete
TR-011 | TNA-003 | Advait Deshmukh | Engineering | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 6 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Advait Deshmukh | Annual review (Apr 2027) | Meera Iyer | Complete
TR-012 | TNA-003 | Priya Subramaniam | Human Resources | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 6 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Priya Subramaniam | Annual review (Apr 2027) | Meera Iyer | Complete
TR-013 | TNA-003 | Divya Nair | Customer Success | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 7 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Divya Nair | Annual review (Apr 2027) | Meera Iyer | Complete
TR-014 | TNA-003 | Karan Bhatia | Sales | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 7 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Karan Bhatia | Annual review (Apr 2027) | Meera Iyer | Complete
TR-015 | TNA-003 | Dr. Ahmed Al Balushi | Clinical Integration | ISMS-LDR-001 Policy Acknowledgement | Self-study + acknowledgement | 8 Apr 2026 | Acknowledged | ISMS-LDR-001 Ack Form — Dr. Ahmed Al Balushi | Annual review (Apr 2027) | Meera Iyer | Complete
TNA-001 — Core Security Awareness (all staff — pending platform selection)
TR-016 | TNA-001 | [All staff — ~430 records to be added when awareness platform is live] | [All departments] | Core Security Awareness Module | E-learning + platform | [Completion date] | [Score] | [Platform record ID] | Annual renewal (Jul 2027) | [Platform auto-record] | Pending — platform not yet live
TNA-002 — Finance Anti-Phishing Module (pending platform selection)
TR-017 | TNA-002 | [Finance + payment-handling staff — ~25 records] | Finance | Finance Anti-Phishing Module | E-learning + workshop | [Completion date] | [Score ≥80%] | [Platform record ID] | Annual renewal (Jul 2027) | [Platform auto-record] | Pending — platform not yet live
TNA-010 — Security Champion Onboarding (pending nominations)
TR-018 | TNA-010 | [Security Champions ×8 — nominations pending] | [All departments] | Security Champion Onboarding Programme | Workshop + self-paced | [Completion date] | Passed | [Attendance record + platform completion] | N/A — ongoing forum attendance | Meera Iyer | Pending — Champions not yet nominated
← ADD FUTURE RECORDS BELOW — copy this row format for each new completion
TR-XXX | TNA-XXX | [Full name] | [Department] | [Training title] | [Method] | DD Mon YYYY | [Score or Pass] | [Evidence ref or platform record] | [Expiry if applicable] | [Verifier name] | [Complete / Pending / Expired]
Retention: Training records are retained for the life of the ISMS plus 3 years (per ISMS-SUP-010 records retention schedule). ¦ Evidence: platform completion records are the primary evidence for e-learning; attendance records + facilitator sign-off for workshops; certificates for external courses. ¦ Verification: the ISMS Manager confirms that evidence has been received before marking a record Complete.

## Dept Completion Summary
ISMS-SUP-004 ¦ Department Completion Summary ¦ Management view — awareness training completion rates by department
Updated monthly by HR. Reported to Steering Committee quarterly. M-04 gate condition: ≥95% per department by July 2026. ¦ Sources: awareness platform completion reports + policy acknowledgement forms.
Department | Total Staff | TNA-003 Policy Ack. (required: 100%) | TNA-001 Core Awareness (required: 95%) | TNA-002 Finance Anti-Phish. | Champion Nominated? | Champion Onboarded (TNA-010) | Overall Status (worst of above) | Last Updated
Engineering | ~145 | Partial (30/145) | Not started | N/A | Pending | Not started | In progress | Jul 2026
Cloud & Infrastructure | ~30 | Partial (8/30) | Not started | N/A | Pending | Not started | In progress | Jul 2026
Security Operations | ~10 | Partial (3/10) | Not started | N/A | Pending | Not started | In progress | Jul 2026
Human Resources | ~18 | Partial (4/18) | Not started | N/A | Pending | Not started | Not started | Jul 2026
Customer Success | ~48 | Partial (7/48) | Not started | N/A | Pending | Not started | Not started | Jul 2026
Sales | ~22 | Partial (3/22) | Not started | N/A | Pending | Not started | Not started | Jul 2026
Finance | ~25 | Partial (5/25) | Not started | Not started | Pending | Not started | Not started | Jul 2026
Legal & Compliance | ~12 | Partial (4/12) | Not started | N/A | Pending | Not started | Not started | Jul 2026
GRC / CISO | ~5 | Complete (5/5) | Not started | N/A | N/A (GRC is ISMS core) | N/A | In progress | Jul 2026
Procurement | ~2 | Not started | Not started | N/A | Pending | Not started | Not started | Appointment overdue
Clinical Integration | ~15 | Partial (3/15) | Not started | N/A | Pending | Not started | Not started | Jul 2026
Executive | ~8 | Partial (4/8) | Not started | N/A | N/A | N/A | In progress | Jul 2026
TOTAL / AVERAGE | ~430 | Partial (~18%) | Not started | ~25 staff req. | 0/8 confirmed | Not started | NOT MET | Jul 2026
M-04 gate condition (July 2026): 95% awareness training completion per department. At Phase 4 baseline (July 2026) no department has completed TNA-001. The awareness platform must be selected and configured by June 2026 for the 95% target to be achievable. COO (Farhan Ahmed) follows up with any department below 80% completion at the two-week mark (ISMS-LDR-009 Action A-08).

## Certificate Register
ISMS-SUP-004 ¦ Certificate Register ¦ External qualifications and certifications held by ISMS team members
Records: certificates from accredited bodies (IRCA, BSI, ISACA, ISC2, etc.) and vendor training. ¦ Expiry dates monitored by ISMS Manager — renewal flagged 90 days in advance. ¦ Certificates stored in GRC Repository > Training Records > Certificates.
Cert ID | Certificate Name | Holder | Issuing Body | Date Achieved | Expiry Date | Days to Expiry (as at Jul 2026) | Stored In GRC Repo? | Status
CERT-001 | CISM — Certified Information Security Manager | Vikram Sundaram (CISO) | ISACA | 2021 | 2024 (CPE renewal due) | Renewal in CPE cycle | Yes — GRC Repo | Active — CPE required
CERT-002 | AWS Certified Solutions Architect — Professional | Sana Al Farsi | Amazon Web Services | 2023 | Aug 2026 | Expires soon — renewal pending | Yes — GRC Repo | Renewal required
CERT-003 | Microsoft Azure Security Engineer Associate (AZ-500) | Sana Al Farsi | Microsoft | 2022 | Aug 2025 (expired) | EXPIRED | Yes — GRC Repo | Expired — renewal overdue
CERT-004 | CompTIA Security+ | Neha Choudhury (SOC Manager) | CompTIA | 2021 | 2024 (CE renewal due) | Renewal in CE cycle | Yes — GRC Repo | Active — CE renewal required
CERT-005 | Certified Ethical Hacker (CEH) | Neha Choudhury (SOC Manager) | EC-Council | 2020 | 2023 (expired — not renewed) | EXPIRED | No — to be obtained | Expired — not renewed
CERT-006 | ISO 27001:2022 Lead Implementer | Meera Iyer (ISMS Manager) | PECB / BSI (TBC) | Planned | N/A — not yet achieved | N/A | N/A — pending course | Planned — TNA-004 (Jul–Aug 2026)
CERT-007 | ISO 27001:2022 Lead Auditor | Meera Iyer (ISMS Manager) | IRCA (CQI registered) | Planned | N/A — not yet achieved | N/A | N/A — pending course | Planned — TNA-005 (Sep–Oct 2026)
CERT-008 | ISO 27001:2022 Foundation | Rohan Sharma (Deputy ISMS Manager) | PECB / BSI (TBC) | Planned | N/A — not yet achieved | N/A | N/A — pending course | Planned — TNA-004 (Jul–Aug 2026)

## New Joiner Induction
ISMS-SUP-004 ¦ New Joiner Induction Tracker ¦ ISMS induction completion for all staff joining from Phase 4 onward
Triggered by HR on every new joiner's first day. System access must not be granted until TNA-016 is complete and TNA-003 is acknowledged. ¦ HR (Priya Subramaniam) updates this tab within 1 business day of a new joiner completing induction. ¦ This tab feeds into the Department Completion Summary (Tab 2) monthly.
Record ID | Full Name | Department | Start Date | TNA-016 Module Completed | TNA-003 Policy Ack. | Access Granted Date | Manager Confirmed | Verified By (HR) | Status
This tracker activates when the awareness platform is live (Jun 2026). New joiners after that date will be recorded here. Existing staff who joined before Phase 4 are covered by TNA-001 and TNA-003 in Tabs 1 and 2.
NJ-XXX | [Full name] | [Department] | DD Mon YYYY | DD Mon YYYY / Pending | DD Mon YYYY / Pending | DD Mon YYYY | [Manager name] | [HR name] | Complete / Pending
Process: (1) HR creates record on day 1 → (2) New joiner completes TNA-016 module on awareness platform (max 2 hours) → (3) New joiner acknowledges ISMS-LDR-001 via platform → (4) HR confirms completion and notifies IT Operations → (5) IT Operations grants system access → (6) HR marks record Complete and updates Department Completion Summary.