MEDISYNC TECHNOLOGIES PVT. LTD.

Bengaluru  |  Pune  |  Hyderabad  |  Dubai

PROJECT CHARTER

Project HealthSec — ISO/IEC 27001:2022 ISMS Implementation

| Field | Detail |
| --- | --- |
| Document Title | Project Charter |
| Document Reference Number | ISMS-INI-001 |
| Master List Entry | Phase 1 — ISMS Initiation (Clause 4), Item 1 of 16 |
| Version | 1.0 |
| Status | Approved — Project Authorised |
| Document Classification | Confidential — Internal Use Only |
| Document Owner | Meera Iyer — Head of GRC & Compliance / ISMS Manager |
| Approving Authority | Ananya Rao — Chief Executive Officer |
| Issue Date | 2 February 2026 |
| Effective Date | 2 February 2026 |
| Next Scheduled Review | At each Steering Committee gate; formal reissue required for any change to scope, budget or duration |
| Applicable Programme | Project HealthSec — ISO/IEC 27001:2022 ISMS Implementation |

This document is the property of MediSync Technologies Pvt. Ltd. It is issued under the company's document control process and must not be copied, forwarded or disclosed outside the company without written approval from the Head of GRC & Compliance.

# Document Control

## 1. Document Information

This is a document registered in the MediSync ISMS Document Repository. The version held in the repository is the only valid version. Any printed or forwarded copy is not valid and may be out of date.

| Field | Detail |
| --- | --- |
| Reference Number | ISMS-INI-001 |
| Series | INI — ISMS Initiation (Clause 4) |
| Document Type | Charter (Project Authorisation Document) |
| Owning Function | Information Security & GRC / ISMS Steering Committee |
| Retention Period | Life of the ISMS plus seven (7) years from certification withdrawal or programme closure |
| Distribution | Executive Management, ISMS Steering Committee, Department Security Champions, Information Security & GRC, External Consulting Team |
| Governing Baseline | ISMS-CSD-001 Company Case Study Document, Version 1.0 |

## 2. Version History

| Version | Date | Author | Summary of Change | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | 12 Jan 2026 | Information Security Consulting Team | Initial draft prepared following the Board's January 2026 decision to implement ISO/IEC 27001:2022. | Not applicable — draft |
| 0.2 | 22 Jan 2026 | Meera Iyer | Governance structure, milestone schedule and budget lines aligned to the company profile in ISMS-CSD-001. | Not applicable — draft |
| 0.3 | 28 Jan 2026 | Vikram Sundaram | Initial risks and security constraints reviewed and expanded; CISO appointment referenced. | Not applicable — draft |
| 1.0 | 2 Feb 2026 | Meera Iyer | Review comments closed. Project formally authorised by the Chief Executive Officer. | Ananya Rao, CEO |

## 3. Review and Approval Record

| Name | Role | Responsibility | Date |
| --- | --- | --- | --- |
| Meera Iyer | Head of GRC & Compliance / ISMS Manager | Author & Project Owner | 28 Jan 2026 |
| Vikram Sundaram | Chief Information Security Officer | Security Constraints Sign-off | 29 Jan 2026 |
| Ridhima Kapoor | Chief Technology Officer | Technical Feasibility & Sponsor Endorsement | 30 Jan 2026 |
| Omar Al Mansoori | Head of Legal & Compliance (UAE) | Legal & Regulatory Review | 30 Jan 2026 |
| Rajesh Menon | Chief Financial Officer | Budget Confirmation | 31 Jan 2026 |
| Farhan Ahmed | Chief Operating Officer | Operational Readiness Acceptance | 31 Jan 2026 |
| Ananya Rao | Chief Executive Officer | Executive Sponsor — Approving Authority | 2 Feb 2026 |

## 4. Related Documents

This document is the founding record of the Project HealthSec governance set. Where a conflict arises between this document and ISMS-CSD-001 Company Case Study Document, the case study's company profile prevails; where a conflict arises with a later-issued policy, the later policy prevails once approved.

| Reference | Document | Relationship |
| --- | --- | --- |
| ISMS-CSD-001 | Company Case Study Document | Provides the company profile, current-state problems and preliminary risk view this Charter is built on. |
| ISMS-INI-002 | ISMS Project Plan | Translates the milestones in Section 7 into a detailed, resourced schedule. |
| ISMS-INI-003 | Stakeholder Register | Expands the governance roles in Section 8 into a full stakeholder list. |
| ISMS-INI-006 | Context Analysis Report | Formalises the internal and external context this Charter summarises in Section 2. |
| ISMS-INI-009 | Interested Parties Register | Records the interested parties and requirements referenced in Section 2 and Section 10. |
| ISMS-INI-010 | Legal & Regulatory Register | Completes the jurisdiction-by-jurisdiction compliance mapping referenced in Section 10. |
| ISMS-INI-011 | ISMS Scope Document | Formally ratifies the draft scope boundary set out in Section 5. |
| ISMS-INI-012 | Gap Assessment Report | Validates the baseline maturity assumptions carried into Section 9 and Section 11. |
| ISMS-PLN-004 | Risk Register | Carries the initial risks in Section 11 forward as the live record. |

# Table of Contents

Document Control	2

1. Document Information	2

2. Version History	2

3. Review and Approval Record	3

4. Related Documents	3

Table of Contents	5

1. Project Authorisation	6

2. Background and Justification	6

3. Project Vision	7

4. Objectives	7

5. Scope	8

5.1 In scope	8

5.2 Out of scope	9

5.3 ISMS scope statement (draft)	9

6. Deliverables	9

7. Milestone Schedule	10

8. Governance and Project Organisation	11

8.1 Governance sequence	12

9. Budget and Financial Authority	13

10. Constraints and Assumptions	13

10.1 Constraints	14

10.2 Assumptions	14

11. Success Criteria	15

12. Charter Approval	15

# 1. Project Authorisation

This Charter formally authorises Project HealthSec and appoints the individuals named in Section 8 to their roles. It is issued on the authority of the Chief Executive Officer following the Board of Directors' decision, minuted in the January 2026 Board meeting, to implement an Information Security Management System aligned with ISO/IEC 27001:2022 and to pursue external certification.

From the effective date of this Charter, the ISMS Manager is authorised to commit approved budget, direct the project team and the external consulting engagement, and proceed with the ten-phase programme described in ISMS-CSD-001.

| Field | Detail |
| --- | --- |
| Project name | Project HealthSec |
| Programme name | ISO/IEC 27001:2022 ISMS Implementation |
| Project type | Governance, Risk & Compliance investment — certification-driven |
| Funding source | Internal operating budget, approved by the Board as part of the January 2026 decision |
| Approved external consulting budget | ₹1,10,00,000 (indicative — see Section 9) |
| Total approved programme investment | ₹1,71,00,000 (indicative — see Section 9) |
| Approved duration | 14 months from Charter effective date to Stage 2 certification decision |
| Delivery model | Internal ownership (GRC, CISO, department owners) supported by an external information security consulting team for design, implementation and audit preparation |
| Certification body | To be confirmed under ISMS-ST1-001 Certification Application (Phase 8) |
| Charter effective date | 2 February 2026 |

# 2. Background and Justification

MediSync has built a genuinely capable product organisation without a matching investment in security governance. Growth since 2018 came from subscription revenue rather than external funding, which gave the founders control over pace but also meant that security and compliance work competed directly with product and sales headcount for budget. The company holds no formal security certification today and has instead answered customer security questions individually, case by case, for as long as it has been asked them.

The problem became visible in late 2024, when a Dubai hospital group MediSync's Middle East sales team considered close to signing sent back a 140-question security questionnaire. Several answers could not be given — there was no current asset register, and the documented incident response plan had been written by an engineer who had since left the company and had never been tested. The deal stalled for four months while sales and engineering reconstructed answers, and the prospect's procurement team said, informally, that ISO/IEC 27001 certification would have made the exercise unnecessary.

An internal review triggered by routine questions from a newly hired VP of Engineering found that password policy differed across products, that quarterly access reviews for hospital-facing admin accounts had not been completed in full for over a year, and that no single person could produce a current list of every system touching patient data. Two incidents followed within months of each other: a well-crafted phishing email came close to redirecting a vendor payment, caught only by a colleague's second look at the invoice, and a routine configuration review — not a monitoring alert — found a cloud storage bucket holding de-identified analytics data with broader access permissions than intended. Neither incident caused confirmed data loss. Both showed that MediSync had been relying on the absence of an attacker rather than the presence of a control.

India's DPDP Act, 2023 has raised what “reasonable security safeguards” means for a company handling data at MediSync's scale, and hospital customers — themselves Data Fiduciaries under the Act — have started asking MediSync, as their processor, to demonstrate exactly how it meets that bar. None of these pressures alone would have moved the Board. Together, they led to the January 2026 decision to stop managing security department by department and start treating it as a governance responsibility, with a named owner, a Steering Committee, and an external, verifiable certification as the proof point.

# 3. Project Vision

Project HealthSec will give MediSync a certified, functioning Information Security Management System that runs as part of how the company operates, not as a compliance exercise bolted on top of it: every information asset with a named owner, every significant risk with a documented and monitored treatment, every policy followed rather than merely written, and every customer security question answered from current evidence rather than assembled under deadline pressure.

Certification is the visible outcome of this project, but the process behind it is the actual point.

The ISMS is designed to keep running after the Stage 2 audit — internal audits, management reviews and continual improvement are built in from Phase 1. This is a fixed characteristic of the programme and is not subject to change during delivery.

# 4. Objectives

The objectives below are the business objectives the Board approved in January 2026. They are the basis for the requirements documented in the Phase 3 planning suite (ISMS-PLN-001 through ISMS-PLN-010).

| Ref | Objective | How Success Is Measured |
| --- | --- | --- |
| BO-01 | Achieve ISO/IEC 27001:2022 certification | Certificate issued following a successful Stage 2 audit (Phase 9) |
| BO-02 | Remove security as a blocker in the UAE sales pipeline | Security questionnaire response time cut from weeks to days; certification cited directly in enterprise RFP responses |
| BO-03 | Demonstrate DPDP Act alignment to Indian customers | Documented, reusable compliance mapping available for every customer request |
| BO-04 | Establish organisation-wide risk ownership | 100% of identified risks assigned a named owner and treatment plan |
| BO-05 | Build tested incident response capability | Incident response plan exercised at least twice a year, going forward |
| BO-06 | Build tested business continuity / disaster recovery capability | DR plan tested end-to-end at least once during the engagement |
| BO-07 | Standardise vendor security assessment | 100% of Tier 1 vendors formally assessed and documented |
| BO-08 | Establish security awareness as an organisation-wide practice, not only an engineering one | 95%+ completion of awareness training across all departments |
| BO-09 | Reduce cyber insurance cost and exposure | Updated insurance renewal terms reflecting demonstrable control maturity |

# 5. Scope

## 5.1 In scope

- Design and implementation of an ISMS aligned to all clauses (4–10) of ISO/IEC 27001:2022 and the applicable Annex A controls.

- All eight MediSync products and the shared platform layer — identity, API gateway, regional data tier, logging/monitoring and backup.

- Corporate functions supporting the platform: Software Engineering, DevSecOps, Cloud Infrastructure, IT Operations, the Security Operations Center, HR, Finance, Procurement, Legal & Compliance, Customer Success, Sales, Clinical Integration and Quality Assurance.

- The Bengaluru, Pune, Hyderabad and Dubai offices.

- The AWS (ap-south-1) and Microsoft Azure (UAE North) hosting environments, including the six dedicated single-tenant customer environments.

- External Stage 1 and Stage 2 certification audits.

- Establishment of the ISMS Steering Committee, the CISO role, the ISMS Manager function and the Department Security Champion network.

## 5.2 Out of scope

- Clinical decision-making and care delivery carried out by hospitals, clinics and physicians using MediSync's platforms — MediSync is the technology processor, not the care provider.

- Legacy on-premises hospital systems, such as customer-owned lab or PACS equipment, beyond the MediSync-built integration point.

- Certification of individual customer organisations — ISO/IEC 27001 certification applies to MediSync, not to the hospitals and clinics it serves.

- Commercial pricing, go-to-market or new product development decisions unrelated to information security.

## 5.3 ISMS scope statement (draft)

“The information security management system covering the design, development, hosting, and support of MediSync's healthcare SaaS platforms, and the corporate functions that support them, across the Bengaluru, Pune, Hyderabad, and Dubai offices.”

This statement is a draft carried forward from ISMS-CSD-001 and is formally ratified in ISMS-INI-011 ISMS Scope Document, a separate Phase 1 deliverable.

Any proposal to narrow or extend this boundary once ratified is a change requiring Steering Committee approval.

# 6. Deliverables

| Ref | Deliverable | Produced By | Accepted By |
| --- | --- | --- | --- |
| D-01 | Context Analysis Report, Interested Parties Register & Legal and Regulatory Register | Consulting Team | ISMS Manager |
| D-02 | ISMS Scope Document & Gap Assessment Report | Consulting Team | CISO |
| D-03 | Information Security Policy Suite & Governance Structure (Clause 5) | Consulting Team + GRC | CEO and CISO |
| D-04 | Risk Assessment Methodology, Asset Register, Risk Register, Risk Treatment Plan & Statement of Applicability | Consulting Team + ISMS Manager | Steering Committee |
| D-05 | Competence, Training & Security Awareness Programme | GRC + HR | CISO |
| D-06 | Operational Procedures & Control Implementation Evidence (per control domain) | Department Owners + GRC | CISO |
| D-07 | Internal Audit Programme, Reports & Management Review Cadence | Consulting Team + ISMS Manager | Steering Committee |
| D-08 | Corrective Action & Continual Improvement Records | ISMS Manager | CISO |
| D-09 | Stage 1 and Stage 2 Audit Readiness and Certification | Consulting Team | CEO and Steering Committee |
| D-10 | Excel Operational Registers & Power BI Executive Dashboard Suite | Consulting Team | CISO |

# 7. Milestone Schedule

Months are counted from the Charter effective date. Milestone dates become binding on Steering Committee ratification of the ISMS Project Plan (ISMS-INI-002). The maximum acceptable delay against any milestone is 15 calendar days.

| Ref | Milestone | Target | Gate Condition |
| --- | --- | --- | --- |
| M-00 | Charter approved; ISMS Steering Committee constituted; CISO appointed | Month 0 | Charter signed under Section 13; CISO Appointment Record (ISMS-LDR-007) issued |
| M-01 | Initiation complete — scope, context, gap assessment and legal register issued | Month 1 | ISMS-INI-011 through ISMS-INI-013 approved by the Steering Committee |
| M-02 | Leadership complete — policy suite approved, governance structure ratified | Month 2 | ISMS-LDR-001 and ISMS-LDR-008 approved by the CEO |
| M-03 | Risk assessment and Statement of Applicability approved | Month 4 | ISMS-PLN-006 signed by the Steering Committee |
| M-04 | Support functions operational — training, competence and awareness programme live | Month 5 | ISMS-SUP-005 launched; baseline completion tracked |
| M-05 | Operational controls implemented across all control domains | Month 8 | ISMS-OPS-002 evidence log shows no open control gaps above Medium |
| M-06 | First internal audit cycle and management review complete | Month 10 | ISMS-PEV-005 and ISMS-PEV-008 signed by the CISO |
| M-07 | Corrective actions closed; improvement log current | Month 11 | ISMS-IMP-004 shows no overdue corrective actions |
| M-08 | Stage 1 certification audit passed | Month 12 | ISMS-ST1-005 shows no major nonconformities |
| M-09 | Stage 2 certification audit passed | Month 13 | ISMS-ST2-007 Certification Recommendation Report issued |
| M-10 | Certification granted | Month 14 | ISMS-CRT-002 certificate issued |

# 8. Governance and Project Organisation

| Role | Holder | Authority Under This Charter |
| --- | --- | --- |
| Executive Sponsor | Ananya Rao, CEO | Owns the Charter. Chairs the ISMS Steering Committee. Approves changes to scope, budget or duration. Final authority on certification body engagement. |
| Project Sponsor | Ridhima Kapoor, CTO | Endorses technical direction and architecture decisions affecting the platform. |
| ISMS Manager & Project Owner | Meera Iyer, Head of GRC & Compliance | Runs the project day to day. Owns documentation, the risk register and internal audit coordination. Manages the consulting engagement. |
| Chief Information Security Officer | Vikram Sundaram | Accountable for the ISMS- day to day. Sets and enforces security requirements. Holds veto on any control or deliverable failing security review. |
| Business Owners | Divya Nair, Head of Customer Success Karan Bhatia, Head of Sales | Represent customer-facing and commercial impact. Own customer security questionnaire response and RFP alignment. |
| Legal & Compliance | Omar Al Mansoori, Head of Legal & Compliance (UAE) | Approves all regulatory mapping and contract-related documents. Owns the Legal & Regulatory Register. |
| Finance | Rajesh Menon, CFO | Controls budget. Releases phase-gate funding against accepted deliverables. |
| Chief Operating Officer | Farhan Ahmed | Confirms operational readiness across departments. Owns the Resource Allocation Plan. |
| Department Security Champions | One nominee per department (confirmed under ISMS-INI-003, Phase 2) | Implement controls locally and drive awareness follow-through within their department. |
| External Consulting Team | Information Security Consulting Team (engaged under this Charter) | Delivers ISMS design, implementation support, internal audit facilitation and certification readiness per Section 6. |

## 8.1 Governance sequence

| Forum | Frequency | Purpose and Output |
| --- | --- | --- |
| ISMS working group stand-up | Weekly | Progress, blockers and issue escalation. Output: Weekly Status Note. |
| GRC / ISMS Manager review | Monthly | Documentation status, control implementation progress, risk register currency. Output: Monthly GRC Status Report. |
| ISMS Steering Committee | Quarterly | Decisions, risk acceptance above threshold, budget and phase-gate approvals. Output: Steering Committee Minutes. |
| Security review | At each phase gate | Deliverable and control review before gate closure. Output: Phase Gate Review Record. |
| Executive briefing | Quarterly | Programme health and certification trajectory to the Board. Output: Executive Summary Report. |

# 9. Budget and Financial Authority

| Item | Amount | Control |
| --- | --- | --- |
| External information security consulting engagement | ₹1,10,00,000 | Milestone-based payment against accepted phase deliverables only |
| Certification body fees (Stage 1 audit, Stage 2 audit, certificate issuance) | ₹12,00,000 | Paid on invoice from the certification body confirmed under ISMS-ST1-001 |
| GRC tooling, Excel register templates and dashboards build | ₹8,00,000 | Monitored monthly by Finance against forecast |
| Internal resource allocation (GRC, IT Operations, department time) | ₹35,00,000 | Standard internal cost allocation |
| Security awareness and training programme | ₹6,00,000 | Tracked against ISMS-SUP-003 Training Needs Analysis |
| Total approved investment | ₹1,71,00,000 | — |
| Contingency | Not held within the project | Any overrun requires Executive Sponsor approval and a Charter reissue |

The figures above are indicative planning numbers pending detailed costing in ISMS-SUP-001 Resource Allocation Plan; they are not a substitute for that document. No payment is released without a signed deliverable acceptance record confirmed by the ISMS Manager, and the person who accepts a deliverable may not be the person who approves its payment.

# 10. Constraints and Assumptions

## 10.1 Constraints

| Constraint | Detail |
| --- | --- |
| Duration | 14 months to Stage 2 certification decision. Non-negotiable without Executive Sponsor approval. |
| Budget | ₹1.10 crore external consulting cost. Non-negotiable without Executive Sponsor approval. |
| Data residency | India-originated data remains in the AWS ap-south-1 region; UAE-originated data remains in the Azure UAE North region, including backups. |
| Delay tolerance | Maximum 15 calendar days against any milestone. |
| Regulatory alignment | Must demonstrate alignment with the DPDP Act, 2023 (India) and the PDPL (UAE) alongside ISO/IEC 27001:2022. |
| Secure development | Existing GitHub Enterprise branch protection and code review practice must be formalised into a documented secure SDLC. |
| Encryption | Encryption at rest and in transit, must be formally evidenced. |
| Access control | Role-based access control and quarterly access review must be evidenced as consistently performed. |
| Documentation | Must be maintained throughout the project in the formats set out in ISMS-CSD-001 (Excel registers, dashboards). |

## 10.2 Assumptions

- The extended departmental ownership team named in Section 8 remains available at the planned allocation for the full fourteen months.

- The Head of Procurement role, currently unfilled per ISMS-CSD-001, is confirmed early enough in Phase 2 to support the Supplier Register in Phase 5.

- The external certification body is selected and contracted within the timeline set out in ISMS-ST1-001.

- Sanitised or synthetic data is sufficient for any control-testing activity.

- The approximately 430-person headcount and departmental structure described in ISMS-CSD-001 remain materially stable for the duration of the engagement.

- Existing technical controls — MFA, Microsoft Entra ID, CrowdStrike Falcon, Microsoft Sentinel, Tenable Nessus — continue to operate at their current baseline and are not replaced mid-engagement.

# 11. Success Criteria

Project HealthSec is considered successfully delivered when all of the following are true. Partial achievement does not constitute success, and no criterion may be waived below Executive Sponsor level.

| Ref | Criterion | Verified By |
| --- | --- | --- |
| S-01 | ISO/IEC 27001:2022 certification is achieved with no major nonconformities outstanding | Certification Recommendation Report (ISMS-ST2-007) / Certification Decision Record (ISMS-CRT-001) |
| S-02 | Every information asset in scope has a documented owner and classification | Information Asset Register (ISMS-PLN-003) |
| S-03 | Every risk above the defined appetite threshold has an approved treatment plan | Risk Treatment Plan (ISMS-PLN-005) and Risk Treatment Approval Record |
| S-04 | Incident response and disaster recovery plans have each been tested at least once, with gaps closed | Incident Log (ISMS-OPS-006) and BCDR test evidence in ISMS-OPS-007 |
| S-05 | 100% of Tier 1 vendors have a completed, current security assessment | Supplier Register (ISMS-OPS-004) |
| S-06 | Security awareness training completion exceeds 95% across all departments | Awareness Session Attendance Records (ISMS-SUP-006) |
| S-07 | The ISMS Steering Committee and management review cadence operate on schedule independent of consultant involvement | Management Review Minutes (ISMS-PEV-008) for at least one cycle run without consulting-team facilitation |
| S-08 | At least one enterprise sales cycle is measurably shortened by citing certification directly | Sales team record comparing questionnaire response time before and after certification |

# 12. Charter Approval

By signing below, the approvers authorise Project HealthSec to proceed, confirm the appointment of the roles in Section 8, and commit the resources set out in Section 9.

| Name | Role | Decision | Date |
| --- | --- | --- | --- |
| Meera Iyer | Head of GRC & Compliance / ISMS Manager | Prepared | 28 Jan 2026 |
| Ridhima Kapoor | Chief Technology Officer | Endorsed as Project Sponsor | 30 Jan 2026 |
| Rajesh Menon | Chief Financial Officer | Budget confirmed | 31 Jan 2026 |
| Ananya Rao | Chief Executive Officer | Approved as Executive Sponsor | 2 Feb 2026 |

Signature: _______________________________          Date: _______________________

Ananya Rao, Chief Executive Officer and Executive Sponsor, MediSync Technologies Pvt. Ltd.