MEDISYNC TECHNOLOGIES PVT. LTD.

Bengaluru  |  Pune  |  Hyderabad  |  Dubai

ISMS PROJECT PLAN

Project HealthSec — ISO/IEC 27001:2022 ISMS Implementation

| Field | Detail |
| --- | --- |
| Document Title | ISMS Project Plan |
| Document Reference Number | ISMS-INI-002 |
| Master List Entry | Phase 1 — ISMS Initiation (Clause 4), Item 2 of 16 |
| Version | 1.0 |
| Status | Approved — Baseline Schedule Ratified |
| Document Classification | Confidential — Internal Use Only |
| Document Owner | Meera Iyer — Head of GRC & Compliance / ISMS Manager |
| Approving Authority | ISMS Steering Committee, chaired by Ananya Rao — Chief Executive Officer |
| Authorising Document | ISMS-INI-001 Project Charter, Version 1.0 |
| Issue Date | 16 February 2026 |
| Effective Date | 16 February 2026 |
| Next Scheduled Review | Re-forecast monthly by the ISMS Manager; formal reissue at any Level 3 or Level 4 change under Section 13 |
| Applicable Programme | Project HealthSec — ISO/IEC 27001:2022 ISMS Implementation |

This document is the property of MediSync Technologies Pvt. Ltd. It is issued under the company's document control process and must not be copied, forwarded or disclosed outside the company without written approval from the Head of GRC & Compliance.

# Document Control

## 1. Version History

| Version | Date | Author | Summary of Change | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | 5 Feb 2026 | Information Security Consulting Team | First schedule draft built from the milestone table in ISMS-INI-001 Section 7. | Not applicable — draft |
| 0.2 | 10 Feb 2026 | Meera Iyer | Work breakdown, deliverable schedule and internal resource allocation added. Phase 4 deliverable list reconciled against ISMS-CSD-001 Section 14. | Not applicable — draft |
| 0.3 | 12 Feb 2026 | Vikram Sundaram | Internal audit independence constraint and certification body lead time added to Sections 8 and 9. | Not applicable — draft |
| 0.4 | 13 Feb 2026 | Rajesh Menon | Budget drawdown profile in Section 11 aligned to the Finance release calendar. | Not applicable — draft |
| 1.0 | 16 Feb 2026 | Meera Iyer | Baseline ratified. The milestone dates in ISMS-INI-001 Section 7 become binding from this date. | ISMS Steering Committee |

## 2. Review and Approval Record

| Name | Role | Responsibility | Date |
| --- | --- | --- | --- |
| Meera Iyer | Head of GRC & Compliance / ISMS Manager | Author & Schedule Owner | 13 Feb 2026 |
| Vikram Sundaram | Chief Information Security Officer | Sequencing & Audit Independence Review | 13 Feb 2026 |
| Ridhima Kapoor | Chief Technology Officer | Engineering & Cloud Resource Commitment | 14 Feb 2026 |
| Farhan Ahmed | Chief Operating Officer | Departmental Resource Release | 14 Feb 2026 |
| Rajesh Menon | Chief Financial Officer | Budget Phasing Confirmation | 14 Feb 2026 |
| Omar Al Mansoori | Head of Legal & Compliance (UAE) | UAE Working Calendar & Review Windows | 15 Feb 2026 |
| Priya Subramaniam | Head of Human Resources | Training & Awareness Scheduling | 15 Feb 2026 |
| Ananya Rao | Chief Executive Officer | Steering Committee Chair — Baseline Ratification | 16 Feb 2026 |

# Table of Contents

Document Control	2

1. Version History	2

2. Review and Approval Record	2

Table of Contents	4

1. Purpose and Scope of This Plan	6

2. Planning Basis	6

2.1 Month Numbering	7

3. Delivery Approach	8

3.1 Rolling Wave Planning	8

4. Phase Structure and Schedule	8

4.1 Planned Overlaps	9

5. Work Breakdown Structure	9

6. Deliverable Schedule	13

6.1 Naming and Version Convention	14

7. Milestones and Phase Gates	14

7.1 How a Gate Is Closed	16

8. Critical Path, Float and Sequencing Constraints	16

8.1 Float Held Against Non-Critical Packages	17

8.2 Hard Sequencing Rules	17

9. Dependencies	18

9.1 Internal Dependencies	18

9.2 External Dependencies	19

9.3 Cross-Jurisdiction Working	19

10. Resource Plan	20

10.1 Internal Resource	20

10.2 External Consulting Team	21

10.3 Effort Profile	22

11. Budget Phasing and Drawdown	22

11.1 Payment Control	23

12. Project Delivery Risks	23

12.1 Schedule Recovery Options	25

13. Issue, Action and Change Management	25

13.1 Change Levels	26

13.2 Issues and Actions	26

13.3 Open Actions at Baseline	26

14. Quality Management and Deliverable Acceptance	27

14.1 Acceptance Criteria	27

15. Communication, Reporting and Progress Measurement	27

15.1 Metrics Reported	28

16. Tools, Registers and Dashboards	29

16.1 Operational Registers	29

16.2 Register Design Rules	29

16.3 Dashboard Build Sequence	30

17. Constraints and Assumptions	30

17.1 Constraints and Their Effect on the Schedule	30

17.2 Assumptions	31

18. Plan Maintenance and Baseline Control	31

19. Plan Approval	32

# 1. Purpose and Scope of This Plan

The Charter authorised Project HealthSec, fixed the fourteen-month duration, named the people who hold each role and set ten milestones. It breaks the ten phases into work packages, puts dates and named leads against them, allocates people and money across the fourteen months, and sets out what happens when something goes wrong.

Three things this plan is:

- The baseline schedule. From the effective date, the dates in Section 4 and Section 7 are what progress is measured against.

- The resource commitment. Section 10 records what each department has agreed to release, in days. Recording it here means a conflict with product delivery becomes a visible decision.

- The change control mechanism for the schedule itself, set out in Section 13.

Two things it is not:

- It is not part of the ISMS. Nothing in this document is a control, a policy or a record required by ISO/IEC 27001:2022. An auditor will not assess this plan; they will assess what it produced.

- It is not a substitute for ISMS-SUP-001 Resource Allocation Plan. The effort figures in Section 10 are planning estimates used to build a schedule. Costed allocation is Phase 4 work.

# 2. Planning Basis

Each planning input below came from a document that has already been approved, so that a later challenge to a date can be traced to the decision it came from.

| Input | Source | What it fixed |
| --- | --- | --- |
| Duration | ISMS-INI-001 1 | Fourteen months, running from the Charter effective date of 2 February 2026 to the Stage 2 certification decision. |
| Milestones | ISMS-INI-001 7 | M-00 to M-10, and the maximum acceptable delay of 15 calendar days against any milestone. |
| Budget | ISMS-INI-001 9 | ₹1,71,00,000 total approved investment, of which ₹1,10,00,000 is external consulting. |
| Scope boundary | ISMS-INI-001 5 | Eight products and the shared platform layer, fifteen departments, four offices, two cloud regions, six single-tenant customer environments. |
| Deliverable list | ISMS-CSD-001 §14 | The documents to be produced in each phase and the series code each one carries. |
| Baseline maturity | ISMS-CSD-001 §18 | The starting maturity score per control domain, used to size Phase 5 effort. |
| Headcount | ISMS-CSD-001 §9 | Approximately 430 people across fifteen departments — the denominator for awareness training completion and access review. |
| Methodology | ISMS-CSD-001 §21 | The eleven-phase structure. This plan covers Phases 1 to 10. |

## 2.1 Month Numbering

The Charter counts months from its effective date.

| Month | Calendar | Phases active | Milestone due |
| --- | --- | --- | --- |
| M0 | Feb 2026 | Phase 1 — Initiation | M-00 |
| M1 | Mar 2026 | Phase 1 closing, Phase 2 starting | M-01 |
| M2 | Apr 2026 | Phase 2 closing, Phase 3 starting | M-02 |
| M3 | May 2026 | Phase 3 — Planning | — |
| M4 | Jun 2026 | Phase 3 closing, Phase 4 starting | M-03 |
| M5 | Jul 2026 | Phase 4 closing, Phase 5 starting | M-04 |
| M6 | Aug 2026 | Phase 5 — Operation | — |
| M7 | Sep 2026 | Phase 5 — Operation | — |
| M8 | Oct 2026 | Phase 5 closing, Phase 6 starting | M-05 |
| M9 | Nov 2026 | Phase 6 — Performance Evaluation | — |
| M10 | Dec 2026 | Phase 6 closing, Phase 7 starting | M-06 |
| M11 | Jan 2027 | Phase 7 closing, Phase 8 starting | M-07 |
| M12 | Feb 2027 | Phase 8 closing, Phase 9 starting | M-08 |
| M13 | Mar 2027 | Phase 9 closing, Phase 10 starting | M-09 |
| M14 | Apr 2027 | Phase 10 — Certification & Reporting | M-10 |

# 3. Delivery Approach

The programme runs as a phase-gated sequence. Certification depends on a chain where each link requires the one before it.

These working rules apply across every phase.

- Documents are produced when the work is completed. The Charter is the main thing that makes a fourteen-month timeline survivable.

- Consultants design and facilitate; MediSync staff own and operate. A deliverable is not accepted if the only person who can explain it is a consultant.

- Evidence is named before implementation. Every control that Phase 5 implements have its evidence artefact identified at the point the procedure is written.

## 3.1 Rolling Wave Planning

Planning detail varies. Phases 1 to 3 are planned to task level in this baseline. Phases 4 to 7 are planned to work-package level and are decomposed to task level immediately preceding each of them. Phases 8 to 10 are planned to deliverable level only, because the dates inside them are set by the certification body.

# 4. Phase Structure and Schedule

Durations below are working durations. Where a phase is shorter than the gap to its milestone, the difference is review and approval time, which for a document-heavy programme is the part that is most often underestimated.

| Phase | Clause / Focus | Code | Start | Finish | Duration | Milestone |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | Clause 4 — ISMS Initiation | INI | M0 (Feb 26) | M1 (Mar 26) | 6 weeks | M-01 |
| Phase 2 | Clause 5 — Leadership | LDR | M1 (Mar 26) | M2 (Apr 26) | 5 weeks | M-02 |
| Phase 3 | Clause 6 — Planning | PLN | M2 (Apr 26) | M4 (Jun 26) | 10 weeks | M-03 |
| Phase 4 | Clause 7 — Support | SUP | M4 (Jun 26) | M5 (Jul 26) | 6 weeks | M-04 |
| Phase 5 | Clause 8 — Operation | OPS | M5 (Jul 26) | M8 (Oct 26) | 14 weeks | M-05 |
| Phase 6 | Clause 9 — Performance Evaluation | PEV | M8 (Oct 26) | M10 (Dec 26) | 9 weeks | M-06 |
| Phase 7 | Clause 10 — Improvement | IMP | M10 (Dec 26) | M11 (Jan 27) | 5 weeks | M-07 |
| Phase 8 | Stage 1 Certification Audit | ST1 | M11 (Jan 27) | M12 (Feb 27) | 5 weeks | M-08 |
| Phase 9 | Stage 2 Certification Audit | ST2 | M12 (Feb 27) | M13 (Mar 27) | 5 weeks | M-09 |
| Phase 10 | Certification, Surveillance & Reporting | CRT | M13 (Mar 27) | M14 (Apr 27) | 5 weeks | M-10 |

## 4.1 Planned Overlaps

Six overlaps may happen. Each one exists because the receiving phase has preparation work that does not depend on the outgoing phase closing.

- Phase 1 / Phase 2 at M1 — policy drafting begins while the gap assessment is still being written, because policy structure does not depend on gap findings.

- Phase 2 / Phase 3 at M2 — risk methodology and appetite work starts while the policy suite is in approval.

- Phase 3 / Phase 4 at M4 — the competence matrix and training needs analysis start as soon as the Statement of Applicability is stable in draft.

- Phase 4 / Phase 5 at M5 — procedure writing begins while awareness training is being launched.

- Phase 5 / Phase 6 at M8 — the monitoring and measurement plan and the audit checklist are prepared while the control evidence is being logged.

- Phase 7 / Phase 8 at M11 — Stage 1 readiness work runs alongside the closure of corrective actions.

# 5. Work Breakdown Structure

The work breakdown below is the level at which progress is tracked in the Weekly Status. Leads are accountable for the package being delivered.

| WBS | Work package | Deliverables | Lead | Window |
| --- | --- | --- | --- | --- |
| 1.1 | Project authorisation and governance stand-up | ISMS-INI-001, LDR-007 trigger | Meera Iyer | M0 |
| 1.2 | Stakeholder mapping, RACI and communication set-up | ISMS-INI-003 to 005 | Meera Iyer | M0 |
| 1.3 | Context analysis, SWOT, PESTLE, interested parties | ISMS-INI-006 to 009 | Consulting Team | M0 – M1 |
| 1.4 | Legal and regulatory register across India and UAE | ISMS-INI-010 | Omar Al Mansoori | M0 – M1 |
| 1.5 | Scope boundary ratification | ISMS-INI-011 | Vikram Sundaram | M1 |
| 1.6 | Gap assessment and gap analysis matrix | ISMS-INI-012, 013 | Consulting Team | M1 |
| 1.7 | Management commitment, kickoff and approval record | ISMS-INI-014 to 016 | Meera Iyer | M1 |
| 2.1 | Information security policy and objectives | ISMS-LDR-001, 002 | Consulting Team + GRC | M1 – M2 |
| 2.2 | Governance structure and executive responsibility matrix | ISMS-LDR-003, 004 | Vikram Sundaram | M1 – M2 |
| 2.3 | Roles, responsibilities and authorities register | ISMS-LDR-005 | Priya Subramaniam | M2 |
| 2.4 | Management review committee charter; CISO appointment record | ISMS-LDR-006, 007 | Ananya Rao | M2 |
| 2.5 | Policy approval and leadership commitment minutes | ISMS-LDR-008, 009 | Meera Iyer | M2 |
| 2.6 | Department Security Champion nomination across 15 departments | Input to ISMS-INI-003 | Farhan Ahmed | M2 |
| 3.1 | Risk assessment methodology and risk appetite | ISMS-PLN-001, 002 | Consulting Team | M2 |
| 3.2 | Information asset register build across 8 products and the shared platform | ISMS-PLN-003 | Sana Al Farsi + Advait Deshmukh | M2 – M3 |
| 3.3 | Asset-based and scenario-based risk assessment | ISMS-PLN-010, 011 | Consulting Team + asset owners | M3 |
| 3.4 | Risk register consolidation and rating | ISMS-PLN-004 | Meera Iyer | M3 – M4 |
| 3.5 | Risk treatment planning and approval | ISMS-PLN-005, 012 | Risk owners + Steering Committee | M4 |
| 3.6 | Statement of Applicability and Annex A justification | ISMS-PLN-006, 007 | Vikram Sundaram | M4 |
| 3.7 | ISMS objectives and change management procedure | ISMS-PLN-008, 009 | GRC | M4 |
| 4.1 | Resource allocation plan | ISMS-SUP-001 | Rajesh Menon + Meera Iyer | M4 |
| 4.2 | Competence matrix and training needs analysis | ISMS-SUP-002, 003 | Priya Subramaniam | M4 – M5 |
| 4.3 | Security awareness programme design and launch | ISMS-SUP-005 | GRC + HR | M5 |
| 4.4 | Training delivery and attendance record capture | ISMS-SUP-004, 006 | Priya Subramaniam | M5 – M8 |
| 4.5 | Documented information controls for the repository | Input to ISMS-OPS-001 | Meera Iyer | M4 |
| 5.1 | Operational procedures per applicable control domain | ISMS-OPS-001 | Department owners | M5 – M7 |
| 5.2 | Access control procedure and first full access review | ISMS-OPS-009 | IT Operations + CISO | M5 – M6 |
| 5.3 | Incident management procedure and tabletop exercise | ISMS-OPS-005, 006 | Neha Choudhury | M6 – M7 |
| 5.4 | Business continuity plan, backup procedure and end-to-end DR test | ISMS-OPS-007, 008 | Sana Al Farsi | M6 – M8 |
| 5.5 | Tier 1 supplier security assessment and register | ISMS-OPS-003, 004 | Procurement + GRC | M5 – M7 |
| 5.6 | Change management log brought into operation | ISMS-OPS-010 | DevSecOps | M5 – M6 |
| 5.7 | Control implementation evidence log, maintained continuously | ISMS-OPS-002 | GRC | M5 – M8 |
| 5.8 | Operational risk reassessment | ISMS-OPS-011 | Meera Iyer | M8 |
| 6.1 | Monitoring and measurement plan | ISMS-PEV-001 | Vikram Sundaram | M8 |
| 6.2 | Security metrics dashboard build | ISMS-PEV-002 | Consulting Team | M8 – M9 |
| 6.3 | Internal audit programme and checklist | ISMS-PEV-003, 004 | Internal Audit Lead | M8 – M9 |
| 6.4 | Internal audit execution across all applicable control domains | ISMS-PEV-005, 006 | Internal Audit Lead | M9 – M10 |
| 6.5 | First full management review cycle | ISMS-PEV-007 to 009 | Ananya Rao | M10 |
| 7.1 | Nonconformity register and corrective action requests | ISMS-IMP-001, 002 | Meera Iyer | M10 |
| 7.2 | Root cause analysis on all major findings | ISMS-IMP-003 | Control owners | M10 – M11 |
| 7.3 | Corrective action tracking to closure | ISMS-IMP-004 | Meera Iyer | M11 |
| 7.4 | Effectiveness verification of closed actions | ISMS-IMP-005 | Vikram Sundaram | M11 |
| 7.5 | Continual improvement and lessons learned logs | ISMS-IMP-006, 007 | GRC | M11 |
| 8.1 | Certification body selection, due diligence and contracting | Input to ISMS-ST1-001 | Meera Iyer | M9 – M10 |
| 8.2 | Certification application submitted | ISMS-ST1-001 | Meera Iyer | M11 |
| 8.3 | Stage 1 readiness checklist and internal dry run | ISMS-ST1-003 | Consulting Team | M11 |
| 8.4 | Stage 1 audit execution | ISMS-ST1-002, 004, 005, 008 | Certification Body | M12 |
| 8.5 | Stage 1 nonconformity response | ISMS-ST1-006, 007 | Meera Iyer | M12 |
| 9.1 | Stage 2 audit planning and scheduling | ISMS-ST2-001 | Certification Body + ISMS Manager | M12 |
| 9.2 | Evidence pack assembly and rehearsal | ISMS-ST2-003 | GRC | M12 |
| 9.3 | Stage 2 audit execution | ISMS-ST2-002, 004, 005 | Certification Body | M13 |
| 9.4 | Stage 2 corrective action and evidence submission | ISMS-ST2-006 | Control owners | M13 |
| 9.5 | Certification recommendation | ISMS-ST2-007 | Certification Body | M13 |
| 10.1 | Certification decision and certificate issuance | ISMS-CRT-001, 002 | Certification Body | M13 – M14 |
| 10.2 | Surveillance audit schedule agreed for the three-year cycle | ISMS-CRT-003 | Meera Iyer | M14 |
| 10.3 | Dashboard suite consolidated and published | ISMS-CRT-004 | Consulting Team + GRC | M13 – M14 |
| 10.4 | Executive summary and project closure report | ISMS-CRT-005, 006 | Meera Iyer | M14 |
| 10.5 | Lessons learned and handover to business as usual | ISMS-CRT-007 | Vikram Sundaram | M14 |

# 6. Deliverable Schedule

Ninety-two documents are produced across the ten phases.

| Phase | Series | Documents | Due | Accepted by |
| --- | --- | --- | --- | --- |
| Phase 1 | INI | 16 — ISMS-INI-001 to ISMS-INI-016 | M1 | Steering Committee |
| Phase 2 | LDR | 9 — ISMS-LDR-001 to ISMS-LDR-009 | M2 | CEO and CISO |
| Phase 3 | PLN | 12 — ISMS-PLN-001 to ISMS-PLN-012 | M4 | Steering Committee |
| Phase 4 | SUP | 6 — ISMS-SUP-001 to ISMS-SUP-006 | M5 | CISO |
| Phase 5 | OPS | 11 — ISMS-OPS-001 to ISMS-OPS-011 | M8 | CISO |
| Phase 6 | PEV | 9 — ISMS-PEV-001 to ISMS-PEV-009 | M10 | Steering Committee |
| Phase 7 | IMP | 7 — ISMS-IMP-001 to ISMS-IMP-007 | M11 | CISO |
| Phase 8 | ST1 | 8 — ISMS-ST1-001 to ISMS-ST1-008 | M12 | CEO and Steering Committee |
| Phase 9 | ST2 | 7 — ISMS-ST2-001 to ISMS-ST2-007 | M13 | CEO and Steering Committee |
| Phase 10 | CRT | 7 — ISMS-CRT-001 to ISMS-CRT-007 | M14 | Steering Committee |
| Total | — | 92 d documents | M14 | — |

## 6.1 Naming and Version Convention

- File name format: ISMS-<SERIES>-<###>_<Document_Title>_v<major>_<minor>.docx — for example, ISMS-INI-002_ISMS_Project_Plan_v1_0.docx.

- Versions 0.1 upward are drafts. The first approved version of any document is 1.0. Approved versions only ever increment on the major or minor number after a documented review.

- Superseded versions are retained, not deleted. An auditor asking how a decision changed over time is a reasonable question and the repository should be able to answer it.

# 7. Milestones and Phase Gates

The milestones are carried unchanged from ISMS-INI-001 Section 7. This plan adds the calendar date and the approver who closes each gate.

| Ref | Milestone | Due | Gate condition | Gate approver |
| --- | --- | --- | --- | --- |
| M-00 | Charter approved; Steering Committee constituted; CISO appointed | M0 — Feb 2026 | Charter signed under ISMS-INI-001 13; ISMS-LDR-007 issued | Executive Sponsor |
| M-01 | Initiation complete — scope, context, gap assessment and legal register issued | M1 — Mar 2026 | ISMS-INI-011 through ISMS-INI-013 approved | Steering Committee |
| M-02 | Leadership complete — policy suite approved, governance ratified | M2 — Apr 2026 | ISMS-LDR-001 and ISMS-LDR-008 approved by the CEO | Chief Executive Officer |
| M-03 | Risk assessment and Statement of Applicability approved | M4 — Jun 2026 | ISMS-PLN-006 signed by the Steering Committee | Steering Committee |
| M-04 | Support functions operational — training and awareness programme live | M5 — Jul 2026 | ISMS-SUP-005 launched; baseline completion tracked | CISO |
| M-05 | Operational controls implemented across all applicable domains | M8 — Oct 2026 | ISMS-OPS-002 shows no open control gaps above Medium | CISO |
| M-06 | First internal audit cycle and management review complete | M10 — Dec 2026 | ISMS-PEV-005 and ISMS-PEV-008 signed by the CISO | CISO |
| M-07 | Corrective actions closed; improvement log current | M11 — Jan 2027 | ISMS-IMP-004 shows no overdue corrective actions | CISO |
| M-08 | Stage 1 certification audit passed | M12 — Feb 2027 | ISMS-ST1-005 shows no major nonconformities | Steering Committee |
| M-09 | Stage 2 certification audit passed | M13 — Mar 2027 | ISMS-ST2-007 Certification Recommendation Report issued | Steering Committee |
| M-10 | Certification granted; dashboard suite live | M14 — Apr 2027 | ISMS-CRT-002 issued; ISMS-CRT-004 published to the Steering Committee | Steering Committee |

## 7.1 How a Gate Is Closed

A gate closes in four steps and in this order.

- The ISMS Manager assembles the evidence pack: every deliverable at version 1.0, the acceptance record for each, and the open action list for the phase.

- The CISO runs the security review and either signs the Phase Gate Review Record or returns the pack with named gaps. A returned pack does not stop the next phase from starting, but it does stop funding release.

- The gate approver named in Section 7 confirms the milestone as met.

- Finance releases the next phase's funding within ten working days of the signed gate record, under the payment control in Section 11.1.

A milestone reached up to fifteen calendar days late is within the Charter tolerance and is recorded as a Level 2 change. Beyond fifteen days it is a Level 3 change and goes to the Steering Committee, whether or not the phase eventually completes.

# 8. Critical Path, Float and Sequencing Constraints

The critical path runs through sixteen work packages. A day lost on any of them is a day lost on the certification date unless it is recovered from within the same phase.

1.5 Scope ratification → 1.6 Gap assessment → 3.1 Risk methodology → 3.2 Asset register → 3.3 Risk assessment → 3.4 Risk register → 3.5 Risk treatment plan → 3.6 Statement of Applicability → 5.1 Operational procedures → 5.7 Control implementation evidence → 6.3 Audit programme → 6.4 Internal audit → 6.5 Management review → 7.3 Corrective action closure → 8.4 Stage 1 → 9.3 Stage 2 → 10.1 Certification decision.

The single most fragile point is 3.2, the asset register. MediSync scores 1 on asset management today, meaning there is no centralised inventory to start from. Everything downstream of it — risk assessment, Statement of Applicability, control scoping — depends on it being both complete and owned.

## 8.1 Float Held Against Non-Critical Packages

| Work package | Float | Note |
| --- | --- | --- |
| 3.2 Asset register | 0 days | On the critical path. Longest single build in the plan and the lowest starting maturity. |
| 5.4 DR test | 0 days | Runs in a production maintenance window. One window reserved in M7 and a second held in M8; a failed first test is expected to be recoverable. |
| 2.3 Roles and authorities register | 5 working days | Depends on HR availability. |
| 4.2 Competence matrix | 10 working days | Can start on the draft Statement of Applicability. |
| 5.5 Supplier assessment | 10 working days | Vendor response time is outside MediSync's control. |
| 6.2 Security metrics dashboard | 15 working days | Not a certification dependency. First candidate for compression under Section 12.1. |
| 10.3 Dashboard suite | 15 working days | Not a certification dependency. Second candidate for compression. |

## 8.2 Hard Sequencing Rules

- No control is implemented before the Statement of Applicability justifies it. Implementing controls ahead of Phase 3 produces controls that cannot be traced back to a risk, which is a routine Stage 2 finding and an avoidable one.

- Internal audit cannot be performed by anyone who wrote the document or operates the control being audited. Clause 9.2 requires objectivity and impartiality, and GRC will have authored most of the documentation by M8. The Phase 6 audit team is therefore drawn from the external consulting team plus two internal auditors seconded from Quality Assurance who have had no ISMS authoring role. They are named in ISMS-PEV-003 before the audit begins.

- Management review follows internal audit, because audit results are a required input to it.

- Stage 2 requires the ISMS to have been operating and generating records.

- Stage 1 nonconformities are closed, or have an accepted and dated action plan, before Stage 2 opens.

# 9. Dependencies

## 9.1 Internal Dependencies

| Ref | Dependency | Needed by | Owner | Impact if late |
| --- | --- | --- | --- | --- |
| D-I-01 | CISO appointed and in post | M0 | Ananya Rao | Phase 2 cannot start. The ISMS has no accountable owner and no one can sign a gate. |
| D-I-02 | Steering Committee constituted and first meeting held | M0 | Ananya Rao | No gate authority exists, so no phase can formally close. |
| D-I-03 | Department Security Champions nominated across all 15 departments | M2 | Farhan Ahmed | Phase 5 loses its local implementation route and control work falls back on GRC. |
| D-I-04 | Head of Procurement appointed | M4 | Priya Subramaniam | Supplier assessments in 5.5 stall. The role is currently vacant per ISMS-CSD-001 11. |
| D-I-05 | Engineering and Cloud capacity released for asset register and secure SDLC evidence | M2 – M7 | Ridhima Kapoor | Hits the critical path directly at 3.2 and again at 5.1. The highest-consequence internal dependency in the plan. |
| D-I-06 | Production maintenance window for the end-to-end DR test | M7 | Sana Al Farsi | The one Phase 5 deliverable that cannot be satisfied by simulation or document review. |
| D-I-07 | HR system access for joiner-mover-leaver evidence | M5 | Priya Subramaniam | Access control evidence in 5.2 is incomplete and the access review cannot be closed. |
| D-I-08 | Finance release of phase-gate funding within 10 working days of gate closure | Each gate | Rajesh Menon | The consulting team demobilises between phases and remobilisation costs roughly one week. |

## 9.2 External Dependencies

| Ref | Dependency | Needed by | Owner | Impact if late |
| --- | --- | --- | --- | --- |
| D-E-01 | Certification body selected and contracted | M9 – M10 | Meera Iyer | The longest external lead time in the programme. Certification bodies commonly need 8 to 12 weeks to schedule a Stage 1 audit. If contracting slips past M10, M-08 moves and every milestone after it moves with it. |
| D-E-02 | Stage 1 audit dates confirmed in writing | M10 | Certification Body | Phase 8 cannot be decomposed to task level and the readiness dry run has no target date. |
| D-E-03 | Stage 2 audit dates confirmed in writing | M12 | Certification Body | Evidence pack assembly in 9.2 has no deadline to work back from. |
| D-E-04 | Continuity of named consulting personnel | M0 – M14 | Consulting Team | Re-briefing a replacement engagement lead costs roughly two weeks of critical path. |
| D-E-05 | Tier 1 vendor responses to security assessments | M6 | Procurement | Vendors are under no contractual obligation to respond quickly. Assessments are issued with a 20 working-day response window. |

## 9.3 Cross-Jurisdiction Working

The UAE working week and public holiday calendar do not line up with India's. Every review window that requires Dubai sign-off — the legal and regulatory register, UAE contract terms, supplier terms with UAE vendors, and evidence drawn from the Azure UAE North environment — carries three additional working days in the schedule. This is built into the dates in Section 5.

Evidence from the UAE environment is collected in-region and reviewed in-region, consistent with the data residency constraint in ISMS-INI-001 Section 10.1. There is no consolidated cross-region evidence store, and the audit evidence pack in 9.2 is assembled as two region-tagged sets.

# 10. Resource Plan

Effort below is expressed in person-days and is a planning estimate used to build the schedule. ISMS-SUP-001 converts it into a costed allocation in Phase 4. A day here means a working day.

## 10.1 Internal Resource

| Role | Holder | Allocation | Peak phases | Effort (days) |
| --- | --- | --- | --- | --- |
| ISMS Manager | Meera Iyer | 60% for 14 months | 1, 3, 6, 7 | 185 |
| Chief Information Security Officer | Vikram Sundaram | 50% for 14 months | 3, 5, 6 | 155 |
| GRC Analysts (×2) | Information Security & GRC | 100% each, 14 months | 3, 5, 6 | 600 |
| Executive Sponsor | Ananya Rao, CEO | Gates and quarterly Steering | 1, 2, 10 | 14 |
| Project Sponsor | Ridhima Kapoor, CTO | Gates and architecture input | 3, 5 | 22 |
| Chief Financial Officer | Rajesh Menon | Gate funding release | All | 10 |
| Chief Operating Officer | Farhan Ahmed | Departmental resource release | 2, 4, 5 | 16 |
| VP Engineering | Advait Deshmukh | Asset register, secure SDLC | 3, 5 | 40 |
| Head of Cloud Infrastructure | Sana Al Farsi | Asset register, cloud controls, DR test | 3, 5 | 55 |
| SOC Manager | Neha Choudhury | Incident procedure, tabletop, monitoring | 5, 6 | 35 |
| Head of Human Resources | Priya Subramaniam | Competence, training, joiner-mover-leaver | 4, 5 | 30 |
| Head of Legal & Compliance | Omar Al Mansoori | Legal register, contract and supplier terms | 1, 5 | 25 |
| Head of Procurement | To be appointed | Supplier assessment coordination | 5 | 25 |
| Head of Customer Success | Divya Nair | Customer data handling, questionnaires | 5 | 15 |
| Head of Sales | Karan Bhatia | Contractual security commitments | 5, 10 | 10 |
| Head of Clinical Integration | Dr. Ahmed Al Balushi | Integration-specific risk and controls | 3, 5 | 20 |
| Department Security Champions (×15) | Nominated in Phase 2 | ~2 days per month from M2 | 4, 5 | 360 |
| Internal Auditors (×2) | Quality Assurance secondment | Phase 6 and Phase 8 only | 6, 8 | 40 |
| Total internal | — | — | — | 1,657 |

## 10.2 External Consulting Team

| Role | Window | Allocation | Effort (days) and note |
| --- | --- | --- | --- |
| Engagement Lead | M0 – M14 | 30% | 90 — continuity of this individual is dependency D-E-04 |
| Senior ISMS Consultant | M0 – M8 | 100% | 180 |
| Risk Consultant | M2 – M5 | 100% | 70 — Phase 3 only, demobilises after M-03 |
| Technical Security Consultant | M5 – M8 | 80% | 60 — control implementation support in Phase 5 |
| Internal Audit Lead | M8 – M13 | 60% | 65 — independent of the delivery team, per Section 8.2 |
| Documentation & Dashboard Analyst | M0 – M14 | 50% | 150 — registers, templates and the dashboard build |
| Total external | — | — | 615 |

## 10.3 Effort Profile

Roughly 45% of total internal effort falls between M5 and M8, which is Phase 5. That is the peak, it collides with normal product delivery, and it is where the plan is most likely to fail on resource difficulty.

# 11. Budget Phasing and Drawdown

The totals below reconcile to ISMS-INI-001 Section 9. This plan adds the phasing. The Charter holds no contingency, so a phase overspend goes to the Executive Sponsor as a Level 4 change.

| Phase | Consulting | Cert. body | Tooling & training | Internal | Phase total |
| --- | --- | --- | --- | --- | --- |
| Phase 1 | ₹12,00,000 | — | ₹1,00,000 | ₹3,00,000 | ₹16,00,000 |
| Phase 2 | ₹8,00,000 | — | — | ₹1,50,000 | ₹9,50,000 |
| Phase 3 | ₹22,00,000 | — | ₹2,00,000 | ₹6,00,000 | ₹30,00,000 |
| Phase 4 | ₹9,00,000 | — | ₹2,50,000 | ₹2,50,000 | ₹14,00,000 |
| Phase 5 | ₹28,00,000 | — | ₹2,50,000 | ₹10,00,000 | ₹40,50,000 |
| Phase 6 | ₹13,00,000 | — | ₹3,50,000 | ₹5,00,000 | ₹21,50,000 |
| Phase 7 | ₹6,00,000 | — | — | ₹2,50,000 | ₹8,50,000 |
| Phase 8 | ₹6,00,000 | ₹5,00,000 | — | ₹2,00,000 | ₹13,00,000 |
| Phase 9 | ₹4,00,000 | ₹6,00,000 | — | ₹1,50,000 | ₹11,50,000 |
| Phase 10 | ₹2,00,000 | ₹1,00,000 | ₹2,50,000 | ₹1,00,000 | ₹6,50,000 |
| Total | ₹1,10,00,000 | ₹12,00,000 | ₹14,00,000 | ₹35,00,000 | ₹1,71,00,000 |

## 11.1 Payment Control

- Consulting payments are milestone-based and released only against accepted phase deliverables, per ISMS-INI-001 Section 9.

- No payment is released without a signed deliverable acceptance record confirmed by the ISMS Manager.

- The person who accepts a deliverable is not the person who approves its payment.

- Finance releases funding within ten working days of a signed Phase Gate Review Record. Beyond that, the delay is recorded as an issue against D-I-08.

- Certification body fees are paid on invoice from the body confirmed under ISMS-ST1-001.

# 12. Project Delivery Risks

These are risks to delivering the project. They are not information security risks and they do not belong in ISMS-PLN-004.

| Ref | Risk | L / I | Response | Owner |
| --- | --- | --- | --- | --- |
| PR-01 | The asset register takes longer than planned because there is no centralised inventory to start from — asset management scores 1 today | High / High | Start discovery in M2 in parallel with methodology work rather than after it. Use cloud provider inventory exports as the first pass instead of building from interviews. Both GRC analysts assigned full time. | Meera Iyer |
| PR-02 | Engineering capacity contention between Phase 5 control work and the product roadmap | High / High | Champion-led model so control work sits with one nominated person per team. The CTO confirms release of named individuals at the M-02 gate. | Ridhima Kapoor |
| PR-03 | Certification body not contracted early enough to secure Stage 1 dates at M12 | Medium / High | Selection starts at M9, two months ahead of the Phase 8 deliverable date. Three bodies shortlisted rather than one, so a scheduling refusal does not restart the process. | Meera Iyer |
| PR-04 | The Head of Procurement vacancy delays Tier 1 supplier assessments | Medium / Med-High | If the role is unfilled at M4, GRC runs the assessments directly and Legal handles contract terms. Decision taken at M4. | Farhan Ahmed |
| PR-05 | Internal audit independence is challenged at Stage 2 because GRC authored the documents it would be auditing | Medium / High | Audit team drawn from the consulting team plus two Quality Assurance auditors with no ISMS authoring role. Independence documented in ISMS-PEV-003 before the audit runs. | Vikram Sundaram |
| PR-06 | Awareness training completion falls short of 95% outside Engineering | Medium / Medium | Completion tracked weekly from M5 by department rather than company-wide. Department heads own their own number and see it in the monthly report. | Priya Subramaniam |
| PR-07 | Controls are operating but not evidenced, and this is discovered at Stage 1 | Medium / High | Evidence artefact named for every control before implementation starts. ISMS-OPS-002 updated weekly rather than at phase end. | Meera Iyer |
| PR-08 | The DR test window is unavailable, or the test fails and needs a second run | Medium / Med-High | Two windows reserved, M7 primary and M8 reserve. A failed first test is treated as a planned outcome with corrective action. | Sana Al Farsi |
| PR-09 | Key person dependency on the ISMS Manager | Low / High | GRC analysts stores all Steering Committee and gate activity in the repository. | Vikram Sundaram |
| PR-10 | The ISMS cannot run without the consulting team once the engagement ends | Medium / High | The consulting team facilitates but does not chair the second management review. Handover is a Phase 10 deliverable with named successors. | Vikram Sundaram |
| PR-11 | Scope pressure from customers asking for their own environments to be included in certification | Medium / Medium | The scope boundary is ratified in ISMS-INI-011. Any extension is a Level 4 change requiring Charter reissue, and the sales team is briefed on this before Phase 5. | Divya Nair |

## 12.1 Schedule Recovery Options

No central contingency is held. If the schedule needs recovering, these are the options in the order they should be used.

- Compress the Phase 6 metrics dashboard (6.2) and the Phase 10 dashboard suite (10.3). Fifteen working days each and neither is a certification dependency.

- Reduce Phase 5 procedure documentation to the control domains the Statement of Applicability marks applicable. Needs CISO sign-off so that the reduction is a decision on record.

- Extend the working day or bring in additional consulting capacity for Phase 3 or Phase 5. Costs money and therefore requires a Level 4 change.

- Move the certification date. Executive Sponsor decision, Charter reissue, and the last resort.

# 13. Issue, Action and Change Management

## 13.1 Change Levels

| Level | Change | Approver | Record |
| --- | --- | --- | --- |
| Level 1 | Re-sequencing tasks within a phase where no milestone moves | ISMS Manager | Weekly Status Note |
| Level 2 | A milestone date moving within the 15 calendar day Charter tolerance | CISO | Monthly GRC Status Report |
| Level 3 | A milestone slipping beyond 15 days; a deliverable added or removed; a resource allocation change above 10% | Steering Committee | Steering Committee Minutes; this plan reissued at v1.x |
| Level 4 | A change to ISMS scope, total budget, or the 14-month duration | Executive Sponsor | ISMS-INI-001 reissued; this plan reissued at v2.0 |

## 13.2 Issues and Actions

- Anything blocking a work package for more than five working days is an issue and goes to the ISMS Manager on the day it becomes visible.

- An issue that cannot be resolved within the phase escalates to the CISO, and from there to the Steering Committee.

- Every action carries a named owner and a date. Open actions appear in the Weekly Status Note; actions overdue by more than ten working days are reported by owner name in the Monthly GRC Status Report.

- Actions are closed on evidence and the person who raised the action confirms closure.

## 13.3 Open Actions at Baseline

| Ref | Action | Owner | Due |
| --- | --- | --- | --- |
| A-01 | Correct the Phase 4 entry in the ISMS-CSD-001 Section 14 repository index, which currently repeats six Phase 3 document IDs in place of Phase 4 entries | Meera Iyer | M1 |
| A-02 | Confirm Department Security Champion nominations for all fifteen departments | Farhan Ahmed | M2 |
| A-03 | Confirm the appointment route and target date for the vacant Head of Procurement role | Priya Subramaniam | M4 |
| A-04 | Shortlist three certification bodies and confirm their typical scheduling lead times in writing | Meera Iyer | M9 |
| A-05 | Name the two Quality Assurance internal auditors and confirm neither has an ISMS authoring role | Vikram Sundaram | M8 |
| A-06 | Confirm the M7 and M8 production maintenance windows for the DR test with Cloud Infrastructure | Sana Al Farsi | M5 |

# 14. Quality Management and Deliverable Acceptance

Every deliverable follows the same route: draft at 0.1, peer review within the producing team, owner review, approval by the authority named in Section 6, baseline at 1.0, and lodgement in the repository. No step is skipped for a document that seems minor.

## 14.1 Acceptance Criteria

| Criterion | What it means in practice |
| --- | --- |
| Traceable | Every material statement traces to a source: the Charter, the case study baseline, a risk in ISMS-PLN-004, or a clause of the standard. |
| Owned | A named individual is recorded as owner, not a department. |
| Current | It describes how MediSync actually works today. Aspirational text is the fastest route to a nonconformity. |
| Evidenced | Where the document asserts that a control operates, the evidence artefact is named and can be located by anyone. |
| Consistent | It uses the same department names, system names (HIS-CORE, EHR-CORE, TELE-PLT, PAT-PORTAL, LAB-INT, PHARM-INT, CLAIMS-PLT, API-GW), classification tiers and vendor names as ISMS-CSD-001. |
| Usable by someone else | A person other than the author can pick it up and act on it. The reviewer confirms this, not the author. |

A deliverable that fails any criterion is returned with the reasons written down and does not count toward gate completion.

# 15. Communication, Reporting and Progress Measurement

The cadence below extends the governance forums in ISMS-INI-001 Section 8.1 with the two working-level forums the project needs day to day. ISMS-INI-005 Communication Plan carries the full detail including distribution lists.

| Forum | Frequency | Attendees | Output | Owner |
| --- | --- | --- | --- | --- |
| ISMS working group stand-up | Weekly | ISMS Manager, GRC analysts, consulting lead, affected Champions | Weekly Status Note | ISMS Manager |
| GRC / ISMS Manager review | Monthly | ISMS Manager, CISO | Monthly GRC Status Report | ISMS Manager |
| Department Champion forum | Monthly | All 15 Champions, GRC | Champion Action Log | GRC |
| Security review | At each phase gate | CISO, ISMS Manager, consulting lead | Phase Gate Review Record | CISO |
| ISMS Steering Committee | Quarterly, plus each gate | Committee as constituted in ISMS-INI-001 §8 | Steering Committee Minutes | CEO |
| Executive briefing to the Board | Quarterly | CEO, CISO | Executive Summary Report | CEO |

## 15.1 Metrics Reported

Six metrics are reported against thresholds.

| Metric | Definition | Reported | Threshold and response |
| --- | --- | --- | --- |
| Deliverable completion | Documents baselined at v1.0 against documents planned to date | Monthly | Below 90% triggers a Level 2 review with the CISO |
| Milestone variance | Calendar days between planned and actual milestone date | At each gate | Above 15 days becomes a Level 3 change |
| Control implementation | Applicable Annex A controls with evidence logged in ISMS-OPS-002 | Monthly from M5 | Below 85% at M7 triggers recovery planning under Section 12.1 |
| Budget drawdown | Spend released against the phase plan in Section 11 | Monthly | Variance above 10% is reported to the CFO in the same month |
| Overdue actions | Actions past their due date | Weekly | Any action overdue by 10 working days escalates to the CISO |
| Awareness completion | Employees completing training, reported by department | Weekly from M5 | Any department below 80% at M7 escalates to the COO |

# 16. Tools, Registers and Dashboards

Operational records are documented Excel registers because they are straightforward to version, audit and hand to an external auditor. Dashboards sits on top as the reporting layer and nothing is entered directly into a dashboard.

## 16.1 Operational Registers

| Register | Document | Built in | Maintained by |
| --- | --- | --- | --- |
| Information Asset Register | ISMS-PLN-003 | Phase 3 | Asset owners, consolidated by GRC |
| Risk Register | ISMS-PLN-004 | Phase 3 | ISMS Manager |
| Statement of Applicability | ISMS-PLN-006 | Phase 3 | CISO |
| Training Log | ISMS-SUP-004 | Phase 4 | Human Resources |
| Control Implementation Evidence Log | ISMS-OPS-002 | Phase 5 | GRC |
| Supplier Register | ISMS-OPS-004 | Phase 5 | Procurement with GRC sign-off |
| Incident Log | ISMS-OPS-006 | Phase 5 | Security Operations Center |
| Access Review Log | ISMS-OPS-009 | Phase 5 | IT Operations |
| Internal Audit Findings Register | ISMS-PEV-006 | Phase 6 | Internal Audit Lead |
| Corrective Action Tracker | ISMS-IMP-004 | Phase 7 | ISMS Manager |

## 16.2 Register Design Rules

Every register is built to the same structural rules so that it can be read by any reporting tool without rework:

- One row per record and one fact per column.

- Colour is for presentation.

- A stable primary key in the first column — ASSET-###, RISK-###, SUP-###, CAR-### — that never changes once issued.

- Free text is separated and columns use a fixed value list defined once and reused across registers.

- Every record carries an owner, a last-reviewed date and a status.

## 16.3 Dashboard Build Sequence

Dashboards are published when the register behind them has real data.

| Dashboard | Source register | First published |
| --- | --- | --- |
| Enterprise Risk Heat Map | ISMS-PLN-004 | M4 |
| Asset Inventory Dashboard | ISMS-PLN-003 | M4 |
| Statement of Applicability Progress | ISMS-PLN-006 | M4 |
| Annex A Control Implementation Status | ISMS-OPS-002 | M6 |
| Security Awareness Dashboard | ISMS-SUP-004 and ISMS-SUP-006 | M6 |
| Supplier Risk Dashboard | ISMS-OPS-004 | M7 |
| Compliance Dashboard | ISMS-INI-010 and ISMS-PLN-006 | M8 |
| Internal Audit Dashboard | ISMS-PEV-006 | M10 |
| Corrective Action Tracker Dashboard | ISMS-IMP-004 | M11 |
| Executive ISMS Dashboard | Consolidated from all of the above | M14 |

The first three are published at M4 because the Steering Committee needs a view of risk from the moment the risk register exists.

# 17. Constraints and Assumptions

## 17.1 Constraints and Their Effect on the Schedule

| Constraint | Effect on this plan |
| --- | --- |
| Fourteen months, no contingency held | Recovery must come from within the plan. The options and their order are set out in Section 12.1. |
| Fifteen-day milestone tolerance | Sets the boundary between a Level 2 and a Level 3 change in Section 13.1. |
| Data residency across AWS ap-south-1 and Azure UAE North | Evidence from the UAE environment is collected and reviewed in-region. The Stage 2 evidence pack is assembled as two region-tagged sets, which adds roughly three days to work package 9.2. |
| No production patient data used in testing | Test evidence uses sanitised or synthetic data, which adds a preparation step ahead of every Phase 5 test. |
| Existing practice is formalised | Secure SDLC, encryption and access control are documented and evidenced, as per ISMS-INI-001 §10.1. This reduces Phase 5 build effort but increases evidence-gathering effort. |
| Consulting support is not a substitute for ownership | Every deliverable has an internal accepting authority. |
| UAE working calendar and public holidays | Three additional working days are built into any review window requiring Dubai sign-off. |

## 17.2 Assumptions

- The fifteen departments release the effort recorded in Section 10. A shortfall is raised as an issue under Section 13.2.

- The baseline maturity ratings in ISMS-CSD-001 Section 18 are broadly accurate.

- No major product launch or platform migration is scheduled between M5 and M8.

- Headcount stays materially stable at approximately 430

- Existing tooling stays in place and is not replaced mid-engagement: Microsoft Entra ID, MFA, endpoint detection and response, the SIEM, and GitHub Enterprise branch protection.

- A certification body with healthcare SaaS experience is available to audit in the M12 and M13 windows.

- Sanitised or synthetic data is acceptable to the certification body for yesting evidence.

- The Head of Procurement role is filled.

# 18. Plan Maintenance and Baseline Control

- The ISMS Manager re-forecasts monthly against the baseline. A re-forecast is a working view.

- The baseline changes only through Section 13.

- Level 3 changes produce a v1.x reissue. Level 4 changes follow a Charter reissue and produce v2.0.

- Phases 4 to 7 are decomposed to task level at the gate before each one. That decomposition is issued as a dated annex.

- Superseded versions are retained in the repository for the full retention period..

- This plan closes at M14 and is replaced by the surveillance audit schedule in ISMS-CRT-003. Closure is recorded in ISMS-CRT-006 Project Closure Report, with anything unfinished transferred to a named owner.

# 19. Plan Approval

By approving this plan, the Steering Committee ratifies the milestone dates in ISMS-INI-001 Section 7 as binding, commits the resource allocation in Section 10, and confirms the phase funding profile in Section 11.

| Name | Role | Decision | Date |
| --- | --- | --- | --- |
| Meera Iyer | Head of GRC & Compliance / ISMS Manager | Prepared | 13 Feb 2026 |
| Vikram Sundaram | Chief Information Security Officer | Reviewed — sequencing and audit independence | 13 Feb 2026 |
| Ridhima Kapoor | Chief Technology Officer | Engineering and cloud resource committed | 14 Feb 2026 |
| Farhan Ahmed | Chief Operating Officer | Departmental resource released | 14 Feb 2026 |
| Rajesh Menon | Chief Financial Officer | Budget phasing confirmed | 14 Feb 2026 |
| Ananya Rao | Chief Executive Officer | Ratified as Steering Committee Chair | 16 Feb 2026 |

Signature: ______________________________________         Date: _______________________

Ananya Rao, Chief Executive Officer and Chair of the ISMS Steering Committee, MediSync Technologies Pvt. Ltd.