## RACI Matrix
ISMS-INI-004 ¦ RACI Matrix ¦ Project HealthSec — ISO/IEC 27001:2022
Phase | Doc ID | Deliverable / Activity | CEO / Exec Sponsor | CTO / Proj Sponsor | CISO | ISMS Manager | CFO | COO | Head of Legal (UAE) | Head of HR | Head of Cloud Infra | Head of Eng (VP) | SOC Manager | Head of Cust Success | Head of Sales | Dept Security Champions | Consulting Team | Internal Audit Lead
PHASE 1 — ISMS Initiation (Clause 4)
1 | ISMS-INI-001 | Project Charter | A |  | C | R | C | C | C | [7 empty] | R
1 | ISMS-INI-002 | ISMS Project Plan |  |  | C | A/R |  | C | [8 empty] | R
1 | ISMS-INI-003 | Stakeholder Register |  |  | C | A/R |  | C | C |  |  |  |  | C | C |  | R
1 | ISMS-INI-004 | RACI Matrix |  |  | C | A/R |  | C | [8 empty] | R
1 | ISMS-INI-005 | Communication Plan |  |  | C | A/R |  | C | C | I |  |  |  | I | I |  | R
1 | ISMS-INI-006 | Context Analysis Report |  |  | C | R |  |  | C | [7 empty] | A/R
1 | ISMS-INI-007 | SWOT Analysis |  |  | C | R | [10 empty] | A/R
1 | ISMS-INI-008 | PESTLE Analysis |  |  | C | R |  |  | C | [7 empty] | A/R
1 | ISMS-INI-009 | Interested Parties Register |  |  | C | A/R |  |  | C |  |  |  |  | C | C |  | R
1 | ISMS-INI-010 | Legal & Regulatory Register | I |  | C | C |  |  | A/R | [7 empty] | R
1 | ISMS-INI-011 | ISMS Scope Document | C |  | A | R | I | I | C | [7 empty] | R
1 | ISMS-INI-012 | Gap Assessment Report |  |  | A | R |  |  |  |  | C | C |  |  |  |  | R
1 | ISMS-INI-013 | Gap Analysis Matrix |  |  | A | R |  |  |  |  | C | C |  |  |  |  | R
1 | ISMS-INI-014 | Management Commitment Statement | A |  | C | R | [10 empty] | R
1 | ISMS-INI-015 | Kickoff Meeting Minutes |  |  | I | A/R | [10 empty] | R
1 | ISMS-INI-016 | Project Approval Record | A |  | C | R
PHASE 2 — Leadership (Clause 5)
2 | ISMS-LDR-001 | Information Security Policy | A |  | R | C |  |  | C | [7 empty] | R
2 | ISMS-LDR-002 | IS Objectives Document |  |  | A | R | [10 empty] | R
2 | ISMS-LDR-003 | ISMS Governance Structure Chart |  |  | C | R | [10 empty] | A/R
2 | ISMS-LDR-004 | Executive Responsibility Matrix |  |  | C | R | [10 empty] | A/R
2 | ISMS-LDR-005 | Roles, Responsibilities & Authorities Register |  |  | A | R |  | C | [8 empty] | R
2 | ISMS-LDR-006 | Management Review Committee Charter | A |  | C | R | [10 empty] | R
2 | ISMS-LDR-007 | CISO Appointment Record | A |  | R | C
2 | ISMS-LDR-008 | Policy Approval Record | A |  | R | R
2 | ISMS-LDR-009 | Leadership Commitment Meeting Minutes |  |  | C | A/R | [10 empty] | R
PHASE 3 — Planning (Clause 6)
3 | ISMS-PLN-001 | Risk Assessment Methodology |  |  | A | R | [10 empty] | R
3 | ISMS-PLN-002 | Risk Appetite & Criteria Document | C |  | A | R | C | [9 empty] | R
3 | ISMS-PLN-003 | Information Asset Register |  |  | A | R |  |  |  |  | C | C |  |  |  | C | R
3 | ISMS-PLN-004 | Risk Register |  |  | A | R |  |  |  |  | C | C | C |  |  | C | R
3 | ISMS-PLN-005 | Risk Treatment Plan |  |  | A | R |  |  |  |  | C | C |  |  |  | C | R
3 | ISMS-PLN-006 | Statement of Applicability | I |  | A | R |  |  | C |  | C | C |  |  |  |  | R
3 | ISMS-PLN-007 | Annex A Control Justification Matrix |  |  | A | R |  |  |  |  | C | C |  |  |  |  | R
3 | ISMS-PLN-008 | ISMS Objectives & Planning Document |  |  | A | R | [10 empty] | R
3 | ISMS-PLN-009 | Change Management Procedure |  |  | C | R |  |  |  |  | C | C |  |  |  |  | A/R
3 | ISMS-PLN-010 | Risk Assessment Report — Asset-Based |  |  | A | R |  |  |  |  | C | C |  |  |  |  | R
3 | ISMS-PLN-011 | Risk Assessment Report — Scenario-Based |  |  | A | R |  |  |  |  | C | C | C |  |  |  | R
3 | ISMS-PLN-012 | Risk Treatment Approval Record | I |  | A | R | I
PHASE 4 — Support (Clause 7)
4 | ISMS-SUP-001 | Resource Allocation Plan |  |  | C | R |  | A | C | C | [6 empty] | R
4 | ISMS-SUP-002 | Competence Matrix |  |  | C | R |  |  |  | A | C | C |  |  |  |  | R
4 | ISMS-SUP-003 | Training Needs Analysis |  |  | C | C |  |  |  | A/R | C | C |  |  |  |  | R
4 | ISMS-SUP-004 | Training Records / Log |  |  | I | I |  |  |  | A/R | [5 empty] | R
4 | ISMS-SUP-005 | Security Awareness Program Plan |  |  | C | C |  |  |  | A/R | [5 empty] | R | R
4 | ISMS-SUP-006 | Awareness Session Attendance Records |  |  | I | I |  |  |  | A | [5 empty] | R
PHASE 5 — Operation (Clause 8)
5 | ISMS-OPS-001 | Operational Procedures (per control domain) |  |  | A | R |  |  |  |  | C | C | C |  |  | R | R
5 | ISMS-OPS-002 | Control Implementation Evidence Log |  |  | A | R |  |  |  |  | C | C | C |  |  | R | R
5 | ISMS-OPS-003 | Vendor / Supplier Security Assessment Reports |  |  | C | R |  |  | C | [7 empty] | A/R
5 | ISMS-OPS-004 | Supplier Register |  |  | C | A/R |  |  | C | [7 empty] | R
5 | ISMS-OPS-005 | Incident Management Procedure |  |  | A | R |  |  |  |  | C | C | C |  |  |  | R
5 | ISMS-OPS-006 | Incident Log / Register |  |  | A | R | [6 empty] | R
5 | ISMS-OPS-007 | BCDR Plan (tested end-to-end) |  | C | A | R |  |  |  |  | R | [5 empty] | R
5 | ISMS-OPS-008 | Backup & Recovery Procedure |  |  | C | R |  |  |  |  | A/R | [5 empty] | R
5 | ISMS-OPS-009 | Access Control Procedure & Access Review Log |  |  | A | R |  |  |  |  | C | C |  |  |  | C | R
5 | ISMS-OPS-010 | Change Management Log |  |  | I | R |  |  |  |  | C | C |  |  |  |  | A
5 | ISMS-OPS-011 | Operational Risk Reassessment Report |  |  | A | R |  |  |  |  | C | C | C |  |  |  | R
PHASE 6 — Performance Evaluation (Clause 9)
6 | ISMS-PEV-001 | Monitoring & Measurement Plan |  |  | A | R |  |  |  |  | C | C | C |  |  |  | R
6 | ISMS-PEV-002 | Security Metrics Dashboard (Power BI) |  |  | I | A/R | [10 empty] | R
6 | ISMS-PEV-003 | Internal Audit Program (Annual Plan) |  |  | A | C | [10 empty] | R | R
6 | ISMS-PEV-004 | Internal Audit Checklist |  |  | C | [11 empty] | R | A/R
6 | ISMS-PEV-005 | Internal Audit Report |  |  | A | C | [10 empty] | R | R
6 | ISMS-PEV-006 | Internal Audit Findings Register |  |  | A | R | [10 empty] | R | R
6 | ISMS-PEV-007 | Management Review Meeting Agenda |  |  | C | A/R | [10 empty] | R
6 | ISMS-PEV-008 | Management Review Minutes | C |  | C | A/R | [10 empty] | R
6 | ISMS-PEV-009 | Management Review Input/Output Record |  |  | A | R | [10 empty] | R
PHASE 7 — Improvement (Clause 10)
7 | ISMS-IMP-001 | Nonconformity Register |  |  | A | R | [11 empty] | C
7 | ISMS-IMP-002 | Corrective Action Request Forms |  |  | A | R |  |  |  |  | C | C | C |  |  |  |  | R
7 | ISMS-IMP-003 | Root Cause Analysis Reports |  |  | A | R |  |  |  |  | C | C | C |  |  |  | R | C
7 | ISMS-IMP-004 | Corrective Action Tracker |  |  | A | A/R |  |  |  |  | C | C | C |  |  |  | R
7 | ISMS-IMP-005 | Effectiveness Verification Records |  |  | A | R | [11 empty] | R
7 | ISMS-IMP-006 | Continual Improvement Log |  |  | A | R
7 | ISMS-IMP-007 | Lessons Learned Register |  |  | C | A/R | [10 empty] | R
PHASE 8 — Stage 1 Certification Audit
8 | ISMS-ST1-001 | Certification Application | I |  | A | R | [10 empty] | R
8 | ISMS-ST1-002 | Stage 1 Audit Plan | I |  | A | R | [10 empty] | R
8 | ISMS-ST1-003 | Stage 1 Readiness Checklist |  |  | A | R | [10 empty] | R
8 | ISMS-ST1-004 | Stage 1 Opening Meeting Minutes |  |  | A | R | [10 empty] | R
8 | ISMS-ST1-005 | Stage 1 Audit Findings Report | I |  | A | R | [10 empty] | C
8 | ISMS-ST1-006 | Stage 1 Nonconformity Register |  |  | A | R | [10 empty] | R
8 | ISMS-ST1-007 | Stage 1 Corrective Action Responses |  |  | A | R |  |  |  |  | C | C |  |  |  |  | R
8 | ISMS-ST1-008 | Stage 1 Closing Meeting Minutes |  |  | A | R | [10 empty] | R
PHASE 9 — Stage 2 Certification Audit
9 | ISMS-ST2-001 | Stage 2 Audit Plan | I |  | A | R | [10 empty] | R
9 | ISMS-ST2-002 | Stage 2 Opening Meeting Minutes | I |  | A | R | [10 empty] | R
9 | ISMS-ST2-003 | Stage 2 Audit Evidence Log |  |  | A | R |  |  |  |  | C | C |  |  |  |  | R
9 | ISMS-ST2-004 | Stage 2 Findings & Nonconformity Report | I |  | A | R | [10 empty] | C
9 | ISMS-ST2-005 | Stage 2 Closing Meeting Minutes | I |  | A | R | [10 empty] | R
9 | ISMS-ST2-006 | Stage 2 Corrective Action Plan & Evidence |  |  | A | R |  |  |  |  | C | C |  |  |  |  | R
9 | ISMS-ST2-007 | Certification Recommendation Report | A |  | C | R | [10 empty] | C
PHASE 10 — Certification, Surveillance & Reporting
10 | ISMS-CRT-001 | Certification Decision Record | A |  | C | R
10 | ISMS-CRT-002 | ISO 27001 Certificate (mock) | A |  | R | R
10 | ISMS-CRT-003 | Surveillance Audit Schedule |  |  | A | R
10 | ISMS-CRT-004 | Power BI Dashboard Suite | I |  | C | A/R | [10 empty] | R
10 | ISMS-CRT-005 | Executive Summary Report | A |  | C | R | [10 empty] | R
10 | ISMS-CRT-006 | Project Closure Report | A |  | C | R | [10 empty] | R
10 | ISMS-CRT-007 | Lessons Learned & Recommendations | I |  | C | A/R | [10 empty] | R

## Legend & Key
ISMS-INI-004 ¦ RACI Matrix — Legend & Key
Document Owner: Meera Iyer, Head of GRC & Compliance / ISMS Manager ¦ Version 1.0 ¦ Issued 25 February 2026 ¦ Classification: Confidential – Internal Use Only
RACI Code Definitions
| R — Responsible | Does the work. One or more per row.
| A — Accountable | Owns the output and signs off. Exactly one per row.
| C — Consulted | Provides input before work is finalised. Two-way.
| I — Informed | Told of outcome once done. One-way.
| A/R | Same person is both Accountable and Responsible — used where the role both does the work and owns it.
| (blank) | Not involved in this deliverable.
How to Read the Matrix
| By row | Each row is one deliverable. Read across to see every role involved.
| By column | Each column is one role. Read down to see every deliverable that role touches.
| Exactly one A per row | If a deliverable has no Accountable, or more than one, that is a gap.
| Gating deliverables | Highlighted in ISMS-INI-002 Section 4.2. The Accountable on those rows cannot slip beyond the 15-day tolerance.
| Procurement (vacant) | Head of Procurement role is unfilled at issue date. ISMS Manager holds all A/R entries for that role until the appointment is confirmed.
| Department Security Champions | Named at the end of Phase 2. R entries in column 13 belong to that function collectively until individuals are confirmed.
| Internal Audit Lead | Must be independent of the controls audited (Phases 5–6). Column 16 is intentionally blank for Phase 5 rows.
| Updates | The RACI Matrix is reissued alongside ISMS-INI-003 Stakeholder Register whenever a named role changes.