## Legal & Regulatory Register
ISMS-INI-010 ¦ Legal & Regulatory Register ¦ Project HealthSec — ISO/IEC 27001:2022 ¦ MediSync Technologies Pvt. Ltd.
Owner: Omar Al Mansoori (Head of Legal & Compliance, UAE) with Meera Iyer (ISMS Manager) ¦ Version 1.0 ¦ Issued 10 March 2026 ¦ Clause 4.2 / 6.1.3 ¦ Classification: Confidential – Internal Use Only
NOTE: This register maps specific legal and contractual obligations to ISMS controls. It is reviewed at each phase gate, at every management review, and whenever a new law, regulation or contract type is introduced. Contractual obligations are generalised — per-contract specifics are held in the contract management system.
ID | Jurisdiction | Law / Obligation | Specific Requirement | Applies To | ISMS Control / Document | Compliance Status | Gap / Action Required | Owner | Review Cadence
INDIA
IND-01 | India | DPDP Act, 2023 — Data Processor Obligations | Implement reasonable security safeguards for digital personal data processed on behalf of Data Fiduciaries (hospital and clinic customers). Support Fiduciary in meeting data principal rights (access, correction). | All products; all India customer data | ISMS-PLN-006 (SoA); ISMS-OPS-001; ISMS-LDR-001 (Policy) | Partial — gap | ISMS certification will constitute "reasonable safeguards." Data principal rights support process to be documented in ISMS-OPS-001 by Phase 5. | Omar Al Mansoori | Phase gate + annual
IND-02 | India | DPDP Act, 2023 — Breach Notification | As Data Processor, MediSync must notify the Data Fiduciary (customer) of a breach without undue delay so the Fiduciary can fulfil its notification obligation to the Data Protection Board of India. | All India customer contracts | ISMS-OPS-005 (Incident Mgmt); ISMS-INI-010 | Partial — gap | Customer-notification path defined in ISMS-OPS-005. Contractual breach-notification SLAs must be reviewed per enterprise contract and included in ISMS-INI-010 contract annex. | Omar Al Mansoori | Phase 5 + annual
IND-03 | India | DPDP Act, 2023 — Data Retention and Deletion | Personal data must not be retained beyond the purpose for which it was processed. Processor must support erasure instructions from the Fiduciary. | All products storing India patient data | ISMS-OPS-001 (data retention procedure); ISMS-PLN-003 (Asset Register) | Partial — gap | Retention schedule per data category to be documented in ISMS-OPS-001. Deletion mechanism for customer-instructed erasure to be confirmed with Engineering by Phase 5. | Meera Iyer / Ridhima Kapoor | Phase 5 + annual
IND-04 | India | IT Act, 2000 — Section 43A (Negligent Data Handling) | Body corporates handling sensitive personal data must implement and maintain reasonable security practices. Failure creating wrongful loss or gain creates civil liability. | All MediSync operations (India) | ISMS-PLN-006 (SoA); ISMS-LDR-001; ISMS-OPS-002 (Evidence Log) | Partial — gap | ISMS certification and SoA provide the documented reasonable-practices evidence. Gap: access review cadence must be formalised and evidenced before certification. | Omar Al Mansoori | Annual
IND-05 | India | CERT-In Rules, 2022 — Mandatory Incident Reporting | Report certain cyber incidents (data breaches, ransomware, unauthorised system access, etc.) to CERT-In within six hours of becoming aware. Maintain logs for 180 days and produce on request. | All MediSync India operations | ISMS-OPS-005 (Incident Mgmt — CERT-In track); ISMS-OPS-006 (Incident Log) | Partial — gap | CERT-In reporting track documented as a separate path in ISMS-OPS-005 (distinct from DPDP Fiduciary notification). 180-day log retention requirement to be confirmed against current SIEM retention settings. | Neha Choudhury / Omar Al Mansoori | Phase 5 + annual
IND-06 | India | ABDM / Health Data Management Policy | Where MediSync platforms connect to India's Ayushman Bharat Digital Mission ecosystem, data exchange must use ABDM-compliant interoperability standards and consent frameworks. | EHR-CORE, TELE-PLT (ABDM integrations only) | ISMS-INI-011 (Scope — ABDM boundary); ISMS-OPS-001 | Partial — gap | ABDM connectivity scope to be explicitly defined in ISMS-INI-011. ISMS-OPS-001 must document consent-management controls for ABDM-connected data flows. | Dr. Ahmed Al Balushi / Meera Iyer | On ABDM standard update + annual
IND-07 | India | MoHFW EHR Standards | EHR-CORE must structure, store and exchange clinical data in accordance with MoHFW Electronic Health Record Standards (2016 and subsequent updates). | EHR-CORE | ISMS-OPS-001 (EHR-CORE data handling); ISMS-PLN-003 | Compliant | Current EHR-CORE implementation already follows MoHFW standards. ISMS-OPS-001 must document this for audit evidence. No new control required. | Dr. Ahmed Al Balushi | On MoHFW standard update + annual
IND-08 | India | Telemedicine Practice Guidelines, 2020 | TELE-PLT consultation and documentation workflows must comply with MoHFW / NMC Telemedicine Practice Guidelines — covering patient consent, prescription handling and record-keeping. | TELE-PLT | ISMS-OPS-001 (TELE-PLT procedure); ISMS-PLN-003 | Compliant | Current TELE-PLT implementation compliant. ISMS-OPS-001 must document compliance for audit evidence. Review on any MoHFW guideline update. | Dr. Ahmed Al Balushi | On guideline update + annual
IND-09 | India | National Medical Commission — Physician Confidentiality | NMC ethical obligations require physicians to maintain patient confidentiality. MediSync platforms are the technical means by which physician customers meet this duty — a MediSync breach is attributable to the physician. | All products with patient record access | ISMS-OPS-009 (Access Control); ISMS-LDR-001; ISMS-PLN-004 (Risk Register) | Compliant | Access controls and encryption directly support physician confidentiality obligations. No gap identified. Physician account access review cadence (IND-04) is the primary risk. | Vikram Sundaram | Annual
UAE
UAE-01 | UAE | PDPL — Federal Decree-Law No. 45 of 2021 — Lawful Basis | Processing of UAE data subjects' personal data requires a valid lawful basis (consent, contract, legal obligation or legitimate interest). MediSync as processor must operate only under documented instruction from the controller (UAE customer). | All UAE customer data; UAE operations | ISMS-INI-010 (contract annex); ISMS-OPS-001; ISMS-PLN-006 | Partial — gap | Lawful basis documented per UAE customer contract in contract management system. ISMS-INI-010 must confirm that all UAE contracts include a valid processing basis clause. Review during Phase 1 by Omar Al Mansoori. | Omar Al Mansoori | Phase 1 + on new UAE contract
UAE-02 | UAE | PDPL — Data Subject Rights | UAE data subjects have rights of access, correction, deletion and objection. MediSync must be able to support the UAE customer (controller) in responding to data subject rights requests affecting data held on MediSync systems. | All UAE customer data | ISMS-OPS-001 (data subject rights support procedure); ISMS-INI-010 | Partial — gap | Rights-support process to be documented in ISMS-OPS-001 by Phase 5. Process must cover how MediSync receives and executes a rights request from a UAE customer. | Omar Al Mansoori | Phase 5 + annual
UAE-03 | UAE | PDPL — Cross-Border Data Transfer | Personal data of UAE data subjects may only be transferred outside the UAE where the destination jurisdiction provides adequate protection or appropriate safeguards are in place. | UAE customer data; any cross-border integration | ISMS-INI-010; ISMS-OPS-001; ISMS-PLN-006 | Compliant | UAE customer data stays in Azure UAE North. No clinical data crosses the border. Corporate data (billing, contracts) assessed by legal as permissible. New integration partners must be assessed before onboarding. | Omar Al Mansoori / Sana Al Farsi | On new integration + annual
UAE-04 | UAE | PDPL — Data Protection Officer | Organisations that process personal data on a large scale or process sensitive data categories may be required to appoint a DPO. Threshold assessment is required. | MediSync UAE operations | ISMS-INI-010; ISMS-LDR-005 (Roles Register) | Partial — gap | DPO threshold assessment to be completed by Omar Al Mansoori in Phase 1. If threshold is met, DPO appointment documented in ISMS-LDR-005. Assessment outcome to be recorded in this register. | Omar Al Mansoori | Phase 1 (assessment); annual thereafter
UAE-05 | UAE | PDPL — Breach Notification | Data breaches affecting UAE data subjects must be notified to the UAE PDPL supervisory authority without undue delay. Notification timeline and content requirements apply. | All UAE customer data | ISMS-OPS-005 (Incident Mgmt — UAE track) | Partial — gap | UAE supervisory authority notification path to be documented in ISMS-OPS-005 as a separate track from India paths. Timeline and content requirements to be confirmed with Omar Al Mansoori by Phase 5. | Omar Al Mansoori / Neha Choudhury | Phase 5 + annual
UAE-06 | UAE | UAE Healthcare Sector Obligations (emirate / free-zone specific) | Healthcare data governance requirements vary by emirate and free zone (e.g., Dubai Health Authority, Abu Dhabi DOH, DHCC). Obligations apply per UAE customer contract and operating jurisdiction. | UAE hospital and clinic customers | ISMS-INI-010 (contract annex, per customer); ISMS-OPS-001 | Partial — gap | Obligations mapped per UAE customer contract — not assumed uniformly. Current UAE customers to be reviewed by Omar Al Mansoori in Phase 1. New UAE customers assessed at onboarding. | Omar Al Mansoori / Dr. Ahmed Al Balushi | On new UAE contract + annual
CONTRACTUAL
CON-01 | Contractual | Enterprise security schedules (India and UAE) | Enterprise contracts include security schedules specifying minimum controls — typically: MFA, encrypted storage, access reviews at defined frequency, patch management, vulnerability scanning, incident notification to the customer within a defined SLA. | Enterprise hospital group customers (~14) | ISMS-PLN-006 (SoA); ISMS-OPS-002 (Evidence Log); ISMS-OPS-005 | Partial — gap | Control requirements mapped to SoA. Gap: access review cadence not yet formally documented. Incident notification SLAs vary per contract — each must be captured in this register's contract annex and cross-referenced to ISMS-OPS-005. | Meera Iyer / Divya Nair | Contract renewal + annual
CON-02 | Contractual | ISO/IEC 27001:2022 certification requirement (UAE enterprise) | Named UAE enterprise contracts (and the 2 active prospects) require ISO/IEC 27001:2022 certification as an explicit precondition to contract signature or renewal. | UAE enterprise customers and prospects | ISMS-CRT-002 (Certificate); ISMS-INI-002 (Project Plan — schedule) | Partial — gap | Certification is the primary output of Project HealthSec. Gap: certificate does not exist yet. Milestone M-10 (April 2027) closes this gap. No contract may claim certification before ISMS-CRT-002 is issued. | Karan Bhatia / Meera Iyer | M-10 milestone; per UAE contract renewal
CON-03 | Contractual | Right-to-audit clauses | Enterprise customers (India and UAE) may conduct or commission a security audit of MediSync systems and processes. MediSync must cooperate within agreed notice periods and scope. | Enterprise customers with right-to-audit clauses | ISMS-OPS-002 (Evidence Log); ISMS-INI-003 (SK-04) | Compliant | Evidence log maintained continuously. Right-to-audit requests routed through Customer Success (ISMS-INI-003 SK-04). Scheduling constraint: audit requests should not coincide with ISMS phase gate windows. | Divya Nair / Meera Iyer | Per audit request + annual
CON-04 | Contractual | Breach notification timelines (contractual — stricter than regulatory) | Several enterprise contracts specify customer breach notification within 24–48 hours of MediSync becoming aware — stricter than the DPDP Act "without undue delay" standard. Contractual obligation governs. | Enterprise contracts with defined notification SLAs | ISMS-OPS-005 (Incident Mgmt — per-customer SLA track) | Partial — gap | ISMS-OPS-005 must include per-customer notification SLA logic. Individual SLAs to be documented in this register's contract annex. Contractual timelines override regulatory minimums where stricter. | Omar Al Mansoori / Neha Choudhury | Contract review + annual
CON-05 | Contractual | Data processing agreements (DPDP Act / UAE PDPL) | Written data processing agreements (DPAs) must exist with all customers for whom MediSync processes personal data, establishing the lawful basis, scope and obligations of each party. | All India and UAE customer contracts | ISMS-INI-010 (DPA status annex); ISMS-PLN-006 | Partial — gap | DPA status to be reviewed per customer in Phase 1. Customers without a current DPA to be prioritised for renewal. Template DPA reviewed against DPDP Act and UAE PDPL by Omar Al Mansoori. | Omar Al Mansoori | Phase 1 (review); on new contract
CON-06 | Contractual | Supplier / sub-processor security requirements | Where MediSync engages sub-processors (vendors who access customer personal data), enterprise contracts typically require that sub-processors meet equivalent security standards and that customers are notified before adding or replacing a sub-processor. | Tier 1 vendors with customer data access (VaultArchive, SentinelWatch, MedLink Gulf) | ISMS-OPS-003 / 004 (Vendor Assessments); ISMS-INI-010 | Partial — gap | Tier 1 sub-processors identified. VaultArchive and MedLink Gulf not yet formally assessed. Customer notification obligation for sub-processor changes to be confirmed per enterprise contract and documented here. | ISMS Manager (interim) | Vendor assessment cycle + on sub-processor change
FRAMEWORK
FRM-01 | Framework | ISO/IEC 27001:2022 — All Clauses 4–10 | Full implementation of the standard — context, leadership, planning, support, operation, performance evaluation and improvement — to achieve and maintain certification. | All MediSync operations within scope | All ISMS documents (ISMS-INI-001 through ISMS-CRT-007) | Partial — gap | Implementation in progress — Project HealthSec. Gap closes at M-10 (April 2027) when certificate is issued. Each phase gate closes a specific set of clause requirements. | Meera Iyer / Vikram Sundaram | Phase gate + annual management review
FRM-02 | Framework | ISO/IEC 27001:2022 — Annex A Controls | All Annex A controls marked applicable in the Statement of Applicability must be implemented and evidenced. Exclusions must be justified. | Per SoA scope | ISMS-PLN-006 (SoA); ISMS-OPS-002 (Evidence Log) | Partial — gap | SoA produced in Phase 3. Control implementation in Phase 5. Evidence captured continuously. Exclusions documented with justification in ISMS-PLN-007. | Vikram Sundaram / Meera Iyer | Phase 3 (SoA); Phase 5 (implementation)
Status key: | Compliant | Partial — gap | Not assessed | N/A

## Notification Paths
ISMS-INI-010 ¦ Breach and Incident Notification Paths ¦ MediSync Technologies Pvt. Ltd.
CRITICAL: Each notification path is a separate track with a different recipient, timeline and trigger. They may fire simultaneously from the same incident. ISMS-OPS-005 must implement each as a distinct procedure step.
Path Ref | Trigger | Recipient | Timeline | Content Required | ISMS Document | MediSync Owner | Track
NP-01 | Breach of India personal data — data principal data affected | Data Fiduciary (customer/hospital) — MediSync notifies the customer who then notifies the Data Protection Board | Without undue delay (no statutory hour limit for processor-to-Fiduciary; Fiduciary then notifies Board) | Nature of breach, categories and volume of data affected, likely consequences, measures taken | ISMS-OPS-005 Section [DPDP track] | Omar Al Mansoori / Neha Choudhury | DPDP Act
NP-02 | Reportable cyber incident per CERT-In Rules 2022 (ransomware, unauthorised access, data breach, targeted scanning, etc.) | CERT-In (cert-in.org.in) — directly, not via customer | Within 6 hours of becoming aware | System name, type of incident, affected systems, number of users impacted, attack vector, action taken, supporting evidence | ISMS-OPS-005 Section [CERT-In track] | Neha Choudhury / Omar Al Mansoori | IT Act / CERT-In Rules
NP-03 | Breach of UAE personal data — data subjects affected | UAE PDPL Supervisory Authority — and the data subjects if high risk to their rights | Without undue delay (guidance on timeline expected from UAE authority) | Nature of breach, categories of data, approximate number of data subjects, likely consequences, measures taken or proposed | ISMS-OPS-005 Section [UAE PDPL track] | Omar Al Mansoori / Neha Choudhury | UAE PDPL
NP-04 | Any security incident affecting customer data or systems — per contractual definition (broader than regulatory) | Affected enterprise customer(s) — via Customer Success account manager | 24–48 hours per contract (STRICTER than regulatory — contractual timeline governs) | Per security schedule in each contract — typically: incident description, affected data, immediate containment actions, timeline for resolution | ISMS-OPS-005 Section [per-customer SLA track] | Divya Nair / Neha Choudhury | Contractual
NP-05 | Any incident rated High or above (per ISMS-OPS-005 severity matrix), or any incident triggering an external notification | ISMS Steering Committee (CEO, CISO, ISMS Manager) | Within 2 hours of incident declaration for High; same business day for Medium | Incident summary, severity rating, external notifications triggered, containment status, resource requirements | ISMS-OPS-005 Section [internal escalation] | CISO (Vikram Sundaram) | Internal governance

## Compliance Summary
ISMS-INI-010 ¦ Compliance Summary ¦ Status as at 10 March 2026
Updated at each phase gate. Drives management review input (ISMS-PEV-008) and corrective action tracking (ISMS-IMP-004).
Jurisdiction / Category | Total | Compliant | Partial/Gap | Priority Gap (closes by)
India (IND) | 9 | 3 | 6 | Access review cadence (IND-04) — Phase 5; CERT-In 180-day log retention (IND-05) — Phase 5; ABDM scope (IND-06) — Phase 1
UAE (UAE) | 6 | 1 | 5 | DPO threshold assessment (UAE-04) — Phase 1; UAE customer DPA review (CON-05) — Phase 1; Per-customer healthcare obligations (UAE-06) — Phase 1
Contractual (CON) | 6 | 1 | 5 | Per-contract breach notification SLAs (CON-04) — Phase 5; DPA status review (CON-05) — Phase 1; Sub-processor notification obligation (CON-06) — Phase 5
Framework (FRM) | 2 | 0 | 2 | ISO 27001 certification (FRM-01) — M-10 April 2027; SoA and Annex A implementation (FRM-02) — Phase 3/5
TOTAL | 23 | 5 | 18 | Five obligations compliant at baseline. Eighteen require action across Phases 1–5 and certification milestone.