## Gap Analysis Matrix
ISMS-INI-013 ¦ Gap Analysis Matrix ¦ Project HealthSec — ISO/IEC 27001:2022 ¦ MediSync Technologies Pvt. Ltd.
Owner: Meera Iyer, ISMS Manager ¦ Version 1.0 ¦ Assessment Period: 2–20 March 2026 ¦ Issued: 25 March 2026 ¦ Classification: Confidential – Internal Use Only
Companion to ISMS-INI-012 Gap Assessment Report. This matrix is the clause-by-clause evidence record. Status key: Compliant ¦ Partial ¦ Gap ¦ N/A
Ref / Clause | Control or Requirement | Status | Current State (Evidence) | Gap / Action Required | Owner | Phase / Gate | Gap Ref
Clause
4.1 | Understanding the organisation and its context | Compliant | ISMS-INI-006 Context Analysis, ISMS-INI-007 SWOT, ISMS-INI-008 PESTLE — all completed and approved. | None. | Meera Iyer | Ph 1 | —
4.2 | Understanding needs of interested parties | Compliant | ISMS-INI-009 Interested Parties Register completed. 23 parties documented with requirements and ISMS mappings. | None. | Meera Iyer | Ph 1 | —
4.3 | Determining the scope | Compliant | ISMS-INI-011 Scope Document approved by Steering Committee. All eight products, both regions, four offices in scope. | None. | Meera Iyer | Ph 1 | —
4.4 | ISMS established and maintained | Partial | Project HealthSec constitutes the establishment. ISMS is being built — not yet operational or certified. | ISMS must be fully operational and evidenced by M-10. Track via phase gate reviews. | Meera Iyer | Ph 1–10 | —
5.1 | Leadership and commitment | Partial | CEO signed Charter; Steering Committee constituted; CISO appointed. Policy suite not yet issued. | Information Security Policy (ISMS-LDR-001) and supporting policies required by M-02. | Ananya Rao / Vikram Sundaram | Ph 2 | G-08
5.2 | Policy | Gap | Policies exist but authored independently; inconsistent terminology; no single approved owner per policy; one contradictory definition of sensitive data confirmed. | Issue unified policy suite with named owners by M-02. ISMS-LDR-001 to LDR-009. | Vikram Sundaram | Ph 2 | G-08
5.3 | Roles, responsibilities and authorities | Partial | CISO appointed (ISMS-LDR-007). ISMS Manager function created. Steering Committee constituted. Department owners identified in ISMS-INI-004. | ISMS-LDR-005 Roles Register to be produced in Phase 2. | Meera Iyer | Ph 2 | —
6.1.1 | Actions to address risks and opportunities | Gap | No organisational risk assessment has been conducted. Risk assessment has only occurred at project level. | Risk methodology (ISMS-PLN-001) and risk register (ISMS-PLN-004) required by M-03. | Vikram Sundaram | Ph 3 | G-02
6.1.2 | Information security risk assessment | Gap | No risk assessment process defined. No risk criteria or scoring methodology exists. | ISMS-PLN-001 Risk Assessment Methodology and ISMS-PLN-002 Risk Appetite Document required by M-03. | Vikram Sundaram | Ph 3 | G-02
6.1.3 | Information security risk treatment | Gap | No risk treatment plan and no Statement of Applicability. | ISMS-PLN-005 Risk Treatment Plan and ISMS-PLN-006 SoA required by M-03. | Vikram Sundaram | Ph 3 | G-03
6.2 | Information security objectives | Partial | Business objectives defined in ISMS-CSD-001. ISMS-specific measurable objectives not yet formally documented. | ISMS-LDR-002 IS Objectives Document required in Phase 2. | Vikram Sundaram | Ph 2 | —
7.1 | Resources | Partial | Project budget approved (₹1.71 Cr). Resource allocation plan not yet finalised. | ISMS-SUP-001 Resource Allocation Plan required in Phase 4. | Farhan Ahmed | Ph 4 | —
7.2 | Competence | Partial | CISO and ISMS Manager roles filled. Department champions not yet named. No competence matrix. | ISMS-SUP-002 Competence Matrix and ISMS-SUP-003 Training Needs Analysis required in Phase 4. | Priya Subramaniam | Ph 4 | —
7.3 | Awareness | Gap | Security awareness training exists for Engineering only. Sales, Customer Success, Finance and Hyderabad office not covered. | ISMS-SUP-005 Awareness Programme must reach all departments by M-04. Finance anti-phishing mandatory. | Priya Subramaniam | Ph 4 | G-10
7.4 | Communication | Partial | ISMS-INI-005 Communication Plan issued. Formal communication channels now defined. | Execute per Communication Plan schedule from Phase 2 onward. | Meera Iyer | Ph 2+ | —
7.5 | Documented information | Partial | Document control process established via Charter and this series. Most operational documents not yet produced. | Operational documents (ISMS-OPS series) produced in Phase 5. Document register maintained throughout. | Meera Iyer | Ph 5 | —
8.1 | Operational planning and control | Gap | No documented operational procedures for ISMS controls. Practices exist but are not written down. | ISMS-OPS-001 Operational Procedures required across all control domains by M-05. | Vikram Sundaram | Ph 5 | G-09
8.2 | Information security risk assessment (operation) | Gap | No operational risk assessment process. Risk assessment has not occurred at organisational level. | Operational risk assessment to follow the methodology in ISMS-PLN-001 from Phase 3. | Vikram Sundaram | Ph 3 | G-02
8.3 | Information security risk treatment (operation) | Gap | No risk treatment plan. | ISMS-PLN-005 required by M-03. | Vikram Sundaram | Ph 3 | G-03
9.1 | Monitoring, measurement, analysis and evaluation | Partial | SIEM and EDR monitoring operational. No documented monitoring plan or measurement criteria. | ISMS-PEV-001 Monitoring & Measurement Plan required in Phase 6. | Meera Iyer | Ph 6 | —
9.2 | Internal audit | Gap | No internal audit has been conducted. No audit programme exists. | ISMS-PEV-003 Internal Audit Programme required in Phase 6. Audit team must be independent. | Meera Iyer | Ph 6 | —
9.3 | Management review | Gap | No management review has been conducted in relation to ISMS. | First management review (ISMS-PEV-008) required in Phase 6 before Stage 1 audit. | Meera Iyer | Ph 6 | —
10.1 | Continual improvement | Partial | Continual improvement concept acknowledged in Charter. No formal mechanism yet. | ISMS-IMP-006 Continual Improvement Log established in Phase 7. | Meera Iyer | Ph 7 | —
10.2 | Nonconformity and corrective action | Partial | No formal nonconformity process. Gap register (this document) is the starting point. | ISMS-IMP-001 Nonconformity Register and ISMS-IMP-002 CAR process established in Phase 7. | Meera Iyer | Ph 7 | —
Annex A — Organisational Controls
5.1 | Policies for information security | Gap | Policies exist but inconsistent, unauthored, contradictory in places. | ISMS-LDR-001 and supporting policy suite by M-02. | Vikram Sundaram | Ph 2 | G-08
5.9 | Inventory of information and other assets | Gap | No centralised asset inventory. Three partial lists across Engineering, IT Ops and Product — none authoritative. | ISMS-PLN-003 Information Asset Register required by M-03. Shared platform layer first. | Meera Iyer | Ph 3 | G-01
5.10 | Acceptable use of information | Partial | Informal acceptable-use norms exist within Engineering. Not documented for all staff. | Acceptable use policy included in ISMS-LDR-001 suite. | Vikram Sundaram | Ph 2 | G-08
5.15 | Access control | Partial | MFA and Entra ID in place — strong. Access review cadence not met. Last full admin review >12 months ago. | Formalise access review schedule. Conduct overdue review before M-05. ISMS-OPS-009. | Vikram Sundaram | Ph 5 | G-04
5.19 | Information security in supplier relationships | Partial | Some vendors assessed at onboarding; some not at all. VaultArchive (backup archives) never assessed. | Tier all vendors. Tier 1 assessments complete by M-05. ISMS-OPS-003 / 004. | ISMS Mgr (interim) | Ph 5 | G-07
5.24 | Information security incident management planning | Gap | Plan exists (2024). Never tested. Does not include CERT-In 6-hr path or UAE PDPL path. | Rewrite ISMS-OPS-005 with all three notification tracks. Tabletop test before M-05. | Neha Choudhury | Ph 5 | G-05
5.29 | Information security during disruption | Gap | Backups operational. End-to-end DR not tested. RTO unknown. | ISMS-OPS-007 BCDR Plan + full DR test (incl. customer notice) by M-05. | Sana Al Farsi | Ph 5 | G-06
5.31 | Legal, statutory, regulatory requirements | Partial | Obligations tracked per-deal. ISMS-INI-010 now established centrally. DPA review and DPO assessment outstanding. | Complete DPO assessment and DPA review in Phase 1 (G-12). CERT-In path in Phase 5 (G-13). | Omar Al Mansoori | Ph 1/5 | G-12,G-13
Annex A — People Controls
6.3 | Information security awareness, education and training | Gap | Training exists for Engineering only. ~276 staff (Sales, CS, Finance, HR, Hyderabad) not covered. | ISMS-SUP-005 awareness programme covering all staff by M-04. 95% completion required. | Priya Subramaniam | Ph 4 | G-10
Annex A — Physical Controls
7.1 | Physical security perimeters | Partial | Office access control and CCTV in place. Controls not documented. Cloud DC physical controls inherited from AWS/Azure. | Document office physical controls in ISMS-OPS-001. Clean-desk, screen-lock, visitor management. | IT Ops Lead | Ph 5 | G-17
Annex A — Technological Controls
8.2 | Privileged access rights | Partial | Entra ID PIM in use for some admin roles. Privileged account inventory not complete. | Complete privileged access inventory as part of ISMS-PLN-003 asset register. Review PIM coverage. | Vikram Sundaram | Ph 3/5 | G-04
8.7 | Protection against malware | Compliant | CrowdStrike Falcon deployed across all ~460 managed endpoints. Alert coverage confirmed. | None. | Neha Choudhury | Ph 5 | —
8.12 | Data leakage prevention | Partial | No formal DLP tooling in place. API-GW data minimisation enforced for external calls. | Data classification and access controls are primary DLP mechanisms. Document in ISMS-OPS-001. | Vikram Sundaram | Ph 5 | —
8.16 | Monitoring activities | Partial | Sentinel SIEM and Falcon EDR deployed and operational. No documented alert coverage standard or review cadence. | SOC procedures documenting alert rules, review cadence and escalation path required in ISMS-OPS-001. | Neha Choudhury | Ph 5 | G-09
8.24 | Use of cryptography | Partial | Encryption at rest (AWS KMS / Azure Key Vault / PostgreSQL TDE) and in transit (TLS enforced) — strong. | Key management procedure and rotation schedule to be documented in ISMS-OPS-001. | Sana Al Farsi | Ph 5 | G-14
8.25 | Secure development life cycle | Partial | GitHub branch protection, mandatory code review, DevSecOps CI/CD pipeline security checks — all in practice. | Formalise SDLC security procedure in ISMS-OPS-001. Evidence gathered from existing practice. | Advait Deshmukh | Ph 5 | G-16
8.29 | Security testing in development and acceptance | Partial | Security scanning in CI/CD pipeline. No formal penetration test record for the past 12 months. | Document security testing approach in ISMS-OPS-001. Penetration test to be commissioned before Stage 2. | Advait Deshmukh | Ph 5 | —
8.34 | Protection of information systems during audit testing | Partial | No formal policy for controlling access during internal audit. | Internal audit access controls documented in ISMS-PEV-003 audit programme. | Meera Iyer | Ph 6 | —
Status key: | Compliant | Partial | Gap | N/A